## Report
Status | Cx Step | Project | Equipment Name | Equipment Description | SOW | Forecast Start | Forecast Finish | Actual Start | Actual Finish | Building | Milestone | Milestone Parent | UPN | Discipline | Cx Upload Unique Number
Passed | ARCH CC | JE DUNN-ALOHA | 15058567-01-F15-Ballroom 555 Roomready | walls, bubble mirror, signage, floor tiles | 15058567-01 | Dec/07/2022 | Dec/07/2022 | Dec/13/2022 | Dec/13/2022 | F15 | F15 Ballroom Conversion |  | RR | ROOM/AREA/BAY-READY | E-623ca33882a1a6ef7a9cebef
Passed | RR CC/GT | JE DUNN-ALOHA | 15058567-01-F15-Ballroom 555 Roomready | walls, bubble mirror, signage, floor tiles | 15058567-01 | Mar/06/2023 | Mar/06/2023 | Jan/10/2023 | Feb/03/2023 | F15 | F15 Ballroom Conversion |  | RR | ROOM/AREA/BAY-READY | E-623ca33882a1a6ef7a9cebef
Passed | RR OA/BT | JE DUNN-ALOHA | 15058567-01-F15-Ballroom 555 Roomready | walls, bubble mirror, signage, floor tiles | 15058567-01 | Mar/20/2023 | Apr/17/2023 | Feb/28/2023 | Feb/28/2023 | F15 | F15 Ballroom Conversion |  | RR | ROOM/AREA/BAY-READY | E-623ca33882a1a6ef7a9cebef
Passed | EHS | JE DUNN-ALOHA | 15058567-01-F15-Ballroom 555 Roomready | walls, bubble mirror, signage, floor tiles | 15058567-01 | Dec/30/2022 | Dec/30/2022 | Jan/04/2023 | Jan/04/2023 | F15 | F15 Ballroom Conversion |  | RR | ROOM/AREA/BAY-READY | E-623ca33882a1a6ef7a9cebef
Passed | FAT | JE DUNN-ALOHA | 15058567-01-F15-Ballroom 555 Roomready | walls, bubble mirror, signage, floor tiles | 15058567-01 | Mar/20/2023 | Apr/17/2023 | Feb/28/2023 | Feb/28/2023 | F15 | F15 Ballroom Conversion |  | RR | ROOM/AREA/BAY-READY | E-623ca33882a1a6ef7a9cebef
Passed | ARCH DV | JE DUNN-ALOHA | 15058567-01-F15-Ballroom 555 Roomready | walls, bubble mirror, signage, floor tiles | 15058567-01 | Dec/15/2022 | Dec/15/2022 | Dec/19/2022 | Dec/19/2022 | F15 | F15 Ballroom Conversion |  | RR | ROOM/AREA/BAY-READY | E-623ca33882a1a6ef7a9cebef
Passed | EHS | JE DUNN-ALOHA | 15058567-01-F15-708-SSH-4 | Safety Shower with Eyewash | 15058567-01 | Dec/30/2022 | Dec/30/2022 | Jan/06/2023 | Jan/06/2023 | F15 | F15 Ballroom 555 Conversion |  | 708 | WASTE | E-623ca33882a1a65a4b9cebec
Passed | EQ CC/GT | JE DUNN-ALOHA | 15058567-01-F15-708-SSH-4 | Safety Shower with Eyewash | 15058567-01 | Mar/06/2023 | Mar/06/2023 | Sep/30/2022 | Feb/08/2023 | F15 | F15 Ballroom 555 Conversion |  | 708 | WASTE | E-623ca33882a1a65a4b9cebec
Passed | MECH W CC | JE DUNN-ALOHA | 15058567-01-F15-708-SSH-4 | Safety Shower with Eyewash | 15058567-01 |  |  | Jul/06/2022 | Jul/13/2022 | F15 | F15 Ballroom 555 Conversion |  | 708 | WASTE | E-623ca33882a1a65a4b9cebec
Passed | FAT | JE DUNN-ALOHA | 15058567-01-F15-708-SSH-4 | Safety Shower with Eyewash | 15058567-01 | Mar/06/2023 | Apr/03/2023 | Feb/24/2023 | Feb/24/2023 | F15 | F15 Ballroom 555 Conversion |  | 708 | WASTE | E-623ca33882a1a65a4b9cebec
Passed | EQ OA/BT | JE DUNN-ALOHA | 15058567-01-F15-708-SSH-4 | Safety Shower with Eyewash | 15058567-01 | Mar/06/2023 | Apr/03/2023 | Feb/24/2023 | Feb/24/2023 | F15 | F15 Ballroom 555 Conversion |  | 708 | WASTE | E-623ca33882a1a65a4b9cebec
Passed | MECH D CC | JE DUNN-ALOHA | 15058567-01-F15-Ballroom 555-Filters | Half Filters (2x2) | 15058567-01 | Dec/14/2022 | Dec/14/2022 | Dec/20/2022 | Dec/20/2022 | F15 |  |  | RR | ROOM/AREA/BAY-READY | E-623ca33882a1a645089cebed
Passed | MECH D DV | JE DUNN-ALOHA | 15058567-01-F15-Ballroom 555-Filters | Half Filters (2x2) | 15058567-01 | Dec/21/2022 | Dec/21/2022 | Dec/20/2022 | Dec/20/2022 | F15 |  |  | RR | ROOM/AREA/BAY-READY | E-623ca33882a1a645089cebed
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-603-3R1G6B | Branch Panel | 15053514-03 | Jan/30/2023 | Feb/16/2023 | Jan/31/2023 | Jan/31/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 603 | ELECTRICAL | E-62b243be06a93a781174f985
Passed | ELECT OAT | JE DUNN-ALOHA | 15053514-03-AL3-603-3R1G6B | Branch Panel | 15053514-03 | Dec/23/2022 | Dec/23/2022 | Nov/16/2022 | Dec/13/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 603 | ELECTRICAL | E-62b243be06a93a781174f985
Passed | ELECT CC | JE DUNN-ALOHA | 15053514-03-AL3-603-3R1G6B | Branch Panel | 15053514-03 | Dec/23/2022 | Dec/23/2022 | Dec/14/2022 | Dec/14/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 603 | ELECTRICAL | E-62b243be06a93a781174f985
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-603-3R1G6B | Branch Panel | 15053514-03 | Jan/13/2023 | Jan/13/2023 | Dec/21/2022 | Dec/21/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 603 | ELECTRICAL | E-62b243be06a93a781174f985
Passed | FAT | JE DUNN-ALOHA | 15053514-03-AL3-MECH131-DIFFUSER/GRILLE/DAMPER | Single line for CSA sign off for this package | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/24/2023 | Feb/24/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 131 | MECHANICAL EXHAUST | E-62b243be06a93ab25374f988
Passed | MECH D CC | JE DUNN-ALOHA | 15053514-03-AL3-MECH131-DIFFUSER/GRILLE/DAMPER | Single line for CSA sign off for this package | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/17/2023 | Jan/17/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 131 | MECHANICAL EXHAUST | E-62b243be06a93ab25374f988
Passed | MECH D DV | JE DUNN-ALOHA | 15053514-03-AL3-MECH131-DIFFUSER/GRILLE/DAMPER | Single line for CSA sign off for this package | 15053514-03 | Jan/23/2023 | Jan/23/2023 | Jan/18/2023 | Jan/18/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 131 | MECHANICAL EXHAUST | E-62b243be06a93ab25374f988
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-MECH131-DIFFUSER/GRILLE/DAMPER | Single line for CSA sign off for this package | 15053514-03 | Jan/27/2023 | Jan/27/2023 | Jan/19/2023 | Jan/30/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 131 | MECHANICAL EXHAUST | E-62b243be06a93ab25374f988
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-MECH131-DIFFUSER/GRILLE/DAMPER | Single line for CSA sign off for this package | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/24/2023 | Feb/24/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 131 | MECHANICAL EXHAUST | E-62b243be06a93ab25374f988
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-SKD151-00 System Level | SKID System Level Sign Off | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/17/2023 | Feb/17/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a0c1174f98a
Passed | I&C CC | JE DUNN-ALOHA | 15053514-03-AL3-SKD151-00 System Level | SKID System Level Sign Off | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/12/2023 | Jan/12/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a0c1174f98a
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15053514-03-AL3-SKD151-00 System Level | SKID System Level Sign Off | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/26/2023 | Jan/26/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a0c1174f98a
Passed | FAT | JE DUNN-ALOHA | 15053514-03-AL3-SKD151-00 System Level | SKID System Level Sign Off | 15053514-03 | Feb/06/2023 | Feb/23/2023 | Feb/07/2023 | Feb/07/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a0c1174f98a
Passed | EHS | JE DUNN-ALOHA | 15053514-03-AL3-SKD151-00 System Level | SKID System Level Sign Off | 15053514-03 | Jan/23/2023 | Jan/23/2023 | Feb/02/2023 | Feb/02/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a0c1174f98a
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-SKD151-00 System Level | SKID System Level Sign Off | 15053514-03 | Feb/03/2023 | Feb/03/2023 | Feb/06/2023 | Feb/06/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a0c1174f98a
Passed | I&C DV | JE DUNN-ALOHA | 15053514-03-AL3-SKD151-00 System Level | SKID System Level Sign Off | 15053514-03 | Jan/06/2023 | Jan/06/2023 | Dec/30/2022 | Dec/30/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a0c1174f98a
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-1-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/27/2023 | Jan/27/2023 | Jan/30/2023 | Jan/30/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a49be74f98b
Passed | I&C CC | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-1-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/09/2023 | Jan/12/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a49be74f98b
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-1-00 | City Water Booster Pump VFD Panel | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/17/2023 | Feb/17/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a49be74f98b
Passed | ELECT CC | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-1-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/12/2023 | Jan/12/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a49be74f98b
Passed | ELECT OAT | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-1-00 | City Water Booster Pump VFD Panel | 15053514-03 | Dec/23/2022 | Dec/23/2022 | Nov/16/2022 | Dec/13/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a49be74f98b
Passed | ELECT DV | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-1-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/06/2023 | Jan/06/2023 | Dec/29/2022 | Dec/29/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a49be74f98b
Passed | I&C DV | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-1-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/06/2023 | Jan/06/2023 | Dec/30/2022 | Dec/30/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a49be74f98b
Passed | FAT | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-1-00 | City Water Booster Pump VFD Panel | 15053514-03 | Feb/06/2023 | Feb/23/2023 | Feb/07/2023 | Feb/07/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a49be74f98b
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-2-00 | City Water Booster Pump | 15053514-03 | Jan/27/2023 | Jan/27/2023 | Jan/30/2023 | Jan/30/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a362a74f98e
Passed | MECH W DV | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-2-00 | City Water Booster Pump | 15053514-03 | Jan/23/2023 | Jan/23/2023 | Jan/18/2023 | Jan/18/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a362a74f98e
Passed | ELECT OAT | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-2-00 | City Water Booster Pump | 15053514-03 | Dec/23/2022 | Dec/23/2022 | Nov/16/2022 | Dec/13/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a362a74f98e
Passed | ELECT DV | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-2-00 | City Water Booster Pump | 15053514-03 | Jan/06/2023 | Jan/06/2023 | Dec/29/2022 | Dec/29/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a362a74f98e
Passed | ELECT CC | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-2-00 | City Water Booster Pump | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/12/2023 | Jan/12/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a362a74f98e
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-2-00 | City Water Booster Pump | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/17/2023 | Feb/17/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a362a74f98e
Passed | MECH W CC | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-2-00 | City Water Booster Pump | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/25/2023 | Jan/25/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a362a74f98e
Passed | FAT | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-2-00 | City Water Booster Pump | 15053514-03 | Feb/06/2023 | Feb/23/2023 | Feb/07/2023 | Feb/07/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a362a74f98e
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-TK151-1-10 | City Water Booster Pump Skid Surge Tank | 15053514-03 | Jan/27/2023 | Jan/27/2023 | Jan/30/2023 | Jan/30/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a1cf574f98f
Passed | MECH W CC | JE DUNN-ALOHA | 15053514-03-AL3-TK151-1-10 | City Water Booster Pump Skid Surge Tank | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/25/2023 | Jan/25/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a1cf574f98f
Passed | FAT | JE DUNN-ALOHA | 15053514-03-AL3-TK151-1-10 | City Water Booster Pump Skid Surge Tank | 15053514-03 | Feb/06/2023 | Feb/23/2023 | Feb/07/2023 | Feb/07/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a1cf574f98f
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-TK151-1-10 | City Water Booster Pump Skid Surge Tank | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/17/2023 | Feb/17/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a1cf574f98f
Passed | MECH W DV | JE DUNN-ALOHA | 15053514-03-AL3-TK151-1-10 | City Water Booster Pump Skid Surge Tank | 15053514-03 | Jan/23/2023 | Jan/23/2023 | Jan/18/2023 | Jan/18/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a1cf574f98f
Passed | ELECT DV | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-1-00 | City Water Booster Pump | 15053514-03 | Jan/06/2023 | Jan/06/2023 | Dec/29/2022 | Dec/29/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93adc8b74f98d
Passed | MECH W DV | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-1-00 | City Water Booster Pump | 15053514-03 | Jan/23/2023 | Jan/23/2023 | Jan/18/2023 | Jan/18/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93adc8b74f98d
Passed | ELECT CC | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-1-00 | City Water Booster Pump | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/12/2023 | Jan/12/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93adc8b74f98d
Passed | ELECT OAT | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-1-00 | City Water Booster Pump | 15053514-03 | Dec/23/2022 | Dec/23/2022 | Nov/16/2022 | Dec/13/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93adc8b74f98d
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-1-00 | City Water Booster Pump | 15053514-03 | Jan/27/2023 | Jan/27/2023 | Jan/30/2023 | Jan/30/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93adc8b74f98d
Passed | MECH W CC | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-1-00 | City Water Booster Pump | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/25/2023 | Jan/25/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93adc8b74f98d
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-1-00 | City Water Booster Pump | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/17/2023 | Feb/17/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93adc8b74f98d
Passed | FAT | JE DUNN-ALOHA | 15053514-03-AL3-PMP151-1-00 | City Water Booster Pump | 15053514-03 | Feb/06/2023 | Feb/23/2023 | Feb/07/2023 | Feb/07/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93adc8b74f98d
Passed | INST FAT | JE DUNN-ALOHA | 15053514-03-AL3-PIT151-1-00A | Pressure Transmitter | 15053514-03 | Jan/27/2023 | Jan/27/2023 | Jan/25/2023 | Jan/25/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93aff5574f990
Passed | I&C OAT | JE DUNN-ALOHA | 15053514-03-AL3-PIT151-1-00A | Pressure Transmitter | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/12/2023 | Jan/12/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93aff5574f990
Passed | ELECT OAT | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-2-00 | City Water Booster Pump VFD Panel | 15053514-03 | Dec/23/2022 | Dec/23/2022 | Nov/16/2022 | Dec/13/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a30f974f98c
Passed | ELECT CC | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-2-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/12/2023 | Jan/12/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a30f974f98c
Passed | FAT | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-2-00 | City Water Booster Pump VFD Panel | 15053514-03 | Feb/06/2023 | Feb/23/2023 | Feb/07/2023 | Feb/07/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a30f974f98c
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-2-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/27/2023 | Jan/27/2023 | Jan/30/2023 | Jan/30/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a30f974f98c
Passed | I&C DV | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-2-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/06/2023 | Jan/06/2023 | Dec/30/2022 | Dec/30/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a30f974f98c
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-2-00 | City Water Booster Pump VFD Panel | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/17/2023 | Feb/17/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a30f974f98c
Passed | I&C CC | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-2-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/09/2023 | Jan/09/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a30f974f98c
Passed | ELECT DV | JE DUNN-ALOHA | 15053514-03-AL3-VFD151-2-00 | City Water Booster Pump VFD Panel | 15053514-03 | Jan/06/2023 | Jan/06/2023 | Dec/30/2022 | Dec/30/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 151 | MECHANICAL PROCESS | E-62b243be06a93a30f974f98c
Passed | ELECT OAT | JE DUNN-ALOHA | 15053514-03-AL3-603-3T1G6B | Low-Voltage Dry-Type Transformer | 15053514-03 | Dec/23/2022 | Dec/23/2022 | Nov/16/2022 | Dec/13/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 603 | ELECTRICAL | E-62b243be06a93a653874f989
Passed | EQ CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-603-3T1G6B | Low-Voltage Dry-Type Transformer | 15053514-03 | Jan/13/2023 | Jan/13/2023 | Dec/21/2022 | Dec/21/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 603 | ELECTRICAL | E-62b243be06a93a653874f989
Passed | ELECT CC | JE DUNN-ALOHA | 15053514-03-AL3-603-3T1G6B | Low-Voltage Dry-Type Transformer | 15053514-03 | Dec/23/2022 | Dec/23/2022 | Dec/14/2022 | Dec/14/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | 603 | ELECTRICAL | E-62b243be06a93a653874f989
Passed | EQ OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-603-3T1G6B | Low-Voltage Dry-Type Transformer | 15053514-03 | Jan/30/2023 | Feb/16/2023 | Jan/31/2023 | Jan/31/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | 603 | ELECTRICAL | E-62b243be06a93a653874f989
Passed | EQ CC/GT | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 | Apr/27/2023 | Apr/27/2023 | Apr/26/2023 | Apr/26/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | I&C DV | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | ELECT DV | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | LSS OAT | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | FAT | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 | Apr/28/2023 | Jun/07/2023 | May/24/2023 | May/24/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | ELECT CC | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | LSS CC | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | EER Final Approval | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Oct/11/2022 | Oct/12/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | MECH W DV | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | EHS | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 | Nov/16/2022 | Nov/16/2022 | Oct/13/2022 | Oct/20/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | MECH D CC | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | MECH D DV | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | EQ OA/BT | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 | Apr/28/2023 | Jun/07/2023 | May/24/2023 | May/24/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | I&C CC | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | MECH W CC | JE DUNN-ALOHA | A0203-AL3-MAH101-4-10 | blah blah | A0203 |  |  | Sep/29/2022 | Sep/29/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-62cdfd342f77c621599955de
Passed | MECH W CC | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 |  |  | Sep/09/2022 | Sep/09/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | I&C CC | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Sep/19/2022 | Sep/19/2022 | Sep/22/2022 | Sep/26/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | EQ CC/GT | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Dec/29/2022 | Dec/29/2022 | Dec/12/2022 | Dec/13/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | FAT | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Dec/19/2022 | Jan/18/2023 | Dec/29/2022 | Dec/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | EHS | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Nov/18/2022 | Nov/18/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | EQ OA/BT | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Dec/19/2022 | Jan/18/2023 | Dec/29/2022 | Dec/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | ELECT CC | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Sep/19/2022 | Sep/19/2022 | Sep/26/2022 | Sep/26/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | I&C DV | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Sep/20/2022 | Sep/20/2022 | Sep/23/2022 | Sep/23/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | ELECT OAT | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Sep/19/2022 | Sep/19/2022 | Sep/22/2022 | Sep/22/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | MECH D CC | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Sep/19/2022 | Sep/19/2022 | Oct/04/2022 | Oct/04/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | MECH D DV | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Sep/20/2022 | Sep/20/2022 | Sep/28/2022 | Sep/28/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | MECH W DV | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Sep/20/2022 | Sep/20/2022 | Sep/28/2022 | Sep/28/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | ELECT DV | JE DUNN-ALOHA | A0104-AL4-RAH002-1-10 | RAH | A0104 | Sep/20/2022 | Sep/20/2022 | Sep/28/2022 | Sep/28/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c621879955f4
Passed | ELECT DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/10/2023 | Feb/10/2023 | Feb/14/2023 | Feb/15/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/16/2023 | Feb/16/2023 | Feb/16/2023 | Feb/16/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/09/2023 | Feb/09/2023 | Feb/16/2023 | Feb/16/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/16/2023 | Feb/16/2023 | Feb/23/2023 | Feb/23/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/09/2023 | Feb/09/2023 | Sep/28/2022 | Feb/08/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/17/2023 | Mar/21/2023 | Feb/23/2023 | Feb/23/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | ELECT CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/09/2023 | Feb/09/2023 | Sep/28/2022 | Feb/08/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/10/2023 | Feb/10/2023 | Feb/14/2023 | Feb/14/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-08 | RIO | 15048483-01 | Feb/17/2023 | Mar/21/2023 | Feb/23/2023 | Feb/23/2023 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6fba59955fd
Passed | MECH W CC | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | ELECT OAT | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | EER Final Approval | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 | Nov/11/2022 | Nov/11/2022 | Oct/11/2022 | Nov/03/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | I&C DV | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | MECH W DV | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | EHS | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/13/2022 | Oct/20/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | ELECT CC | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | EQ OA/BT | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 | Dec/22/2022 | Jan/23/2023 | Dec/29/2022 | Dec/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | ELECT DV | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | MECH D CC | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | I&C CC | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | EQ CC/GT | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 | Dec/29/2022 | Dec/29/2022 | Dec/29/2022 | Dec/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | MECH D DV | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | FAT | JE DUNN-ALOHA | A0104-AL4-RAH002-2-10 | RAH | A0104 | Dec/22/2022 | Jan/23/2023 | Dec/29/2022 | Dec/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c64c239955ff
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Oct/13/2022 | Oct/13/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Sep/15/2022 | Sep/15/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Sep/29/2022 | Sep/29/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | ELECT CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Sep/15/2022 | Sep/15/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Oct/25/2022 | Oct/25/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Oct/10/2022 | Oct/10/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Sep/21/2022 | Sep/21/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | ELECT DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Sep/28/2022 | Sep/28/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-404-04 | RIO | 15048483-01 |  |  | Oct/18/2022 | Oct/18/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6103b995606
Passed | ELECT CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Sep/20/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Oct/25/2022 | Oct/25/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | ELECT DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Sep/28/2022 | Sep/28/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Oct/18/2022 | Oct/18/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Oct/13/2022 | Oct/13/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Sep/21/2022 | Sep/21/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Sep/29/2022 | Sep/29/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Oct/10/2022 | Oct/10/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-07 | RIO | 15048483-01 |  |  | Sep/20/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c64c9b9955fc
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Sep/21/2022 | Sep/21/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | ELECT DV | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Sep/28/2022 | Sep/28/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Oct/18/2022 | Oct/18/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Sep/29/2022 | Sep/29/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Sep/20/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Oct/10/2022 | Oct/10/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Oct/25/2022 | Oct/25/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Oct/13/2022 | Oct/13/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | ELECT CC | JE DUNN-ALOHA | 15048483-01-F15-RIO650-402-02 | RIO | 15048483-01 |  |  | Sep/20/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c623069955fe
Passed | ELECT CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Sep/20/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Sep/21/2022 | Sep/21/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Oct/13/2022 | Oct/13/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Oct/18/2022 | Oct/18/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Oct/25/2022 | Oct/25/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Sep/29/2022 | Sep/29/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Oct/10/2022 | Oct/10/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | ELECT DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Sep/28/2022 | Sep/28/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-403-02 | RIO | 15048483-01 |  |  | Sep/15/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c63067995602
Passed | EQ OA/BT | JE DUNN-ALOHA | A0104-AL4-VFD002-1-10 | VFD for RAH | A0104 | Dec/05/2022 | Dec/05/2022 | Nov/10/2022 | Nov/17/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6962599560c
Passed | FAT | JE DUNN-ALOHA | A0104-AL4-VFD002-1-10 | VFD for RAH | A0104 | Nov/18/2022 | Nov/18/2022 | Nov/10/2022 | Nov/10/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6962599560c
Passed | EQ CC/GT | JE DUNN-ALOHA | A0104-AL4-VFD002-1-10 | VFD for RAH | A0104 | Oct/11/2022 | Oct/11/2022 | Oct/13/2022 | Oct/13/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6962599560c
Passed | I&C DV | JE DUNN-ALOHA | A0104-AL4-VFD002-1-10 | VFD for RAH | A0104 | Sep/21/2022 | Sep/21/2022 | Sep/28/2022 | Sep/28/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6962599560c
Passed | I&C CC | JE DUNN-ALOHA | A0104-AL4-VFD002-1-10 | VFD for RAH | A0104 | Sep/20/2022 | Sep/20/2022 | Sep/26/2022 | Sep/26/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6962599560c
Passed | ELECT OAT | JE DUNN-ALOHA | A0104-AL4-VFD002-1-10 | VFD for RAH | A0104 | Sep/20/2022 | Sep/20/2022 | Sep/22/2022 | Sep/22/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6962599560c
Passed | ELECT DV | JE DUNN-ALOHA | A0104-AL4-VFD002-1-10 | VFD for RAH | A0104 | Sep/21/2022 | Sep/21/2022 | Sep/29/2022 | Sep/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6962599560c
Passed | ELECT CC | JE DUNN-ALOHA | A0104-AL4-VFD002-1-10 | VFD for RAH | A0104 | Sep/20/2022 | Sep/20/2022 | Sep/26/2022 | Sep/26/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6962599560c
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Sep/21/2022 | Sep/21/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | ELECT DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Sep/28/2022 | Sep/28/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Oct/13/2022 | Oct/13/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Sep/30/2022 | Oct/10/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | ELECT CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Sep/20/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Sep/20/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Sep/28/2022 | Sep/28/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Oct/18/2022 | Oct/18/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-401-04 | RIO | 15048483-01 |  |  | Oct/25/2022 | Oct/25/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c67cb89955fa
Passed | EER Final Approval | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 | Nov/11/2022 | Nov/11/2022 | Oct/11/2022 | Nov/03/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | I&C CC | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | ELECT DV | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | ELECT OAT | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | MECH D CC | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | EHS | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/13/2022 | Oct/20/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | EQ OA/BT | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 | Dec/22/2022 | Jan/23/2023 | Dec/29/2022 | Dec/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | EQ CC/GT | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 | Dec/29/2022 | Dec/29/2022 | Dec/29/2022 | Dec/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | I&C DV | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | MECH W DV | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | MECH W CC | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | ELECT CC | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | FAT | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 | Dec/22/2022 | Jan/23/2023 | Dec/29/2022 | Dec/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | MECH D DV | JE DUNN-ALOHA | A0104-AL4-RAH002-3-10 | RAH | A0104 |  |  | Oct/11/2022 | Oct/11/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62cdfd342f77c6ebf199560a
Passed | ELECT DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/13/2022 | Oct/13/2022 | Oct/26/2022 | Oct/26/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/13/2022 | Oct/13/2022 | Oct/13/2022 | Oct/13/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/12/2022 | Oct/12/2022 | Oct/18/2022 | Oct/18/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/12/2022 | Oct/12/2022 | Sep/27/2022 | Oct/12/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/20/2022 | Oct/28/2022 | Nov/03/2022 | Nov/03/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/13/2022 | Oct/13/2022 | Nov/03/2022 | Nov/03/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/19/2022 | Oct/19/2022 | Nov/03/2022 | Nov/03/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | ELECT CC | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/12/2022 | Oct/12/2022 | Sep/27/2022 | Oct/12/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-650-RIO-405-02 | RIO | 15048483-01 | Oct/20/2022 | Oct/28/2022 | Oct/13/2022 | Nov/03/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c6070c995608
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Sep/15/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | ELECT CC | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Sep/20/2022 | Sep/20/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Oct/10/2022 | Oct/10/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Sep/21/2022 | Sep/21/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Oct/25/2022 | Oct/25/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Oct/13/2022 | Oct/13/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Oct/18/2022 | Oct/18/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | ELECT DV | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Sep/28/2022 | Sep/28/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-RIO650-401-06 | RIO | 15048483-01 |  |  | Sep/29/2022 | Sep/29/2022 | F15 | PLC5 Phase 1 |  | 650 | FACILITIES MONITORING SYSTEM | E-62cdfd342f77c629a399560b
Passed | I&C OAT | JE DUNN-ALOHA | A0104-AL4-IS002-1-10A | AL4 RAH UPGRADES | A0104 |  |  | Aug/12/2022 | Aug/12/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598d1634a59bbc
Passed | INST FAT | JE DUNN-ALOHA | A0104-AL4-TCV002-1-10 | AL4 RAH UPGRADES | A0104 | Sep/20/2022 | Sep/20/2022 | Sep/21/2022 | Sep/21/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598ddc42a59bb5
Passed | I&C OAT | JE DUNN-ALOHA | A0104-AL4-TCV002-1-10 | AL4 RAH UPGRADES | A0104 |  |  | Aug/17/2022 | Aug/17/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598ddc42a59bb5
Passed | PROC CC | JE DUNN-ALOHA | A0104-AL4-TCV002-1-10 | AL4 RAH UPGRADES | A0104 | Sep/13/2022 | Sep/13/2022 | Sep/29/2022 | Sep/29/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598ddc42a59bb5
Passed | I&C OAT | JE DUNN-ALOHA | A0104-AL4-HS002-1-10B | AL4 RAH UPGRADES | A0104 |  |  | Aug/12/2022 | Aug/12/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598d83b2a59bba
Passed | I&C OAT | JE DUNN-ALOHA | A0104-AL4-HSI002-1-10A | AL4 RAH UPGRADES | A0104 |  |  | Aug/12/2022 | Aug/12/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598d80d8a59bbb
Passed | INST FAT | JE DUNN-ALOHA | A0104-AL4-HSI002-1-10A | AL4 RAH UPGRADES | A0104 | Sep/21/2022 | Sep/21/2022 | Sep/20/2022 | Sep/20/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598d80d8a59bbb
Passed | PROC CC | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1A | UPW Dist. EOL | 15048483-01 |  |  | Sep/02/2022 | Sep/02/2022 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-62d0f03f51f6d4f21c9e21bc
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1A | UPW Dist. EOL | 15048483-01 | Jan/24/2023 | May/26/2023 | May/12/2023 | May/12/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-62d0f03f51f6d4f21c9e21bc
Passed | I&C OAT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1A | UPW Dist. EOL | 15048483-01 | Feb/08/2023 | Feb/08/2023 | Feb/07/2023 | Feb/07/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-62d0f03f51f6d4f21c9e21bc
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1A | UPW Dist. EOL | 15048483-01 | Jan/24/2023 | Jun/02/2023 | May/22/2023 | May/22/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-62d0f03f51f6d4f21c9e21bc
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1A | UPW Dist. EOL | 15048483-01 | Feb/10/2023 | Mar/14/2023 | Feb/07/2023 | Feb/16/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-62d0f03f51f6d4f21c9e21bc
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1A | UPW Dist. EOL | 15048483-01 | Feb/15/2023 | Feb/15/2023 | Feb/09/2023 | Feb/09/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-62d0f03f51f6d4f21c9e21bc
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1A | UPW Dist. EOL | 15048483-01 | Feb/08/2023 | Feb/08/2023 | Feb/07/2023 | Feb/07/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-62d0f03f51f6d4f21c9e21bc
Passed | I&C OAT | JE DUNN-ALOHA | A0104-AL4-SCO02-1-10A | AL4 RAH UPGRADES | A0104 |  |  | Aug/12/2022 | Aug/12/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598d76a2a59bab
Passed | I&C OAT | JE DUNN-ALOHA | A0104-AL4-HS002-1-10A | AL4 RAH UPGRADES | A0104 |  |  | Aug/12/2022 | Aug/12/2022 | AL4 | AL4 RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d5c9711d598d6af4a59bac
Passed | I&C OAT | JE DUNN-ALOHA | A0104-AL4-QS002-1-10A | RAH UPGRADES | A0104 |  |  | Aug/12/2022 | Aug/12/2022 | AL4 | RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d6150c9f2c1a83e89e8aab
Passed | INST FAT | JE DUNN-ALOHA | A0104-AL4-QS002-1-10A | RAH UPGRADES | A0104 | Sep/21/2022 | Sep/21/2022 | Sep/20/2022 | Sep/20/2022 | AL4 | RAH UPGRADES |  | 102 | MECHANICAL DRY | E-62d6150c9f2c1a83e89e8aab
Passed | PROC CC | JE DUNN-ALOHA | 15059001-02-F15-AWN-261-Lateral Q.5s | AWN Lateral at Q.5s | 15059001-02 | Dec/15/2022 | Dec/15/2022 | Dec/15/2022 | Dec/15/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 261 | WASTE | E-62e9bb2f374137541033e035
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-02-F15-AWN-261-Lateral Q.5s | AWN Lateral at Q.5s | 15059001-02 | Dec/22/2022 | Dec/22/2022 | Dec/20/2022 | Dec/20/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 261 | WASTE | E-62e9bb2f374137541033e035
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-02-F15-AWN-261-Lateral Q.5s | AWN Lateral at Q.5s | 15059001-02 | Dec/28/2022 | Jan/23/2023 | Jan/17/2023 | Jan/17/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 261 | WASTE | E-62e9bb2f374137541033e035
Passed | PROC CC | JE DUNN-ALOHA | 15059001-02-F15-CSW-270-Lateral Q.5s | CSW Lateral at Q.5s | 15059001-02 | Oct/17/2022 | Oct/17/2022 | Oct/20/2022 | Oct/20/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 270 | WASTE | E-62ec07140d26f52b04ad9a4a
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-02-F15-CSW-270-Lateral Q.5s | CSW Lateral at Q.5s | 15059001-02 | Oct/24/2022 | Nov/02/2022 | Nov/07/2022 | Nov/07/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 270 | WASTE | E-62ec07140d26f52b04ad9a4a
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-02-F15-CSW-270-Lateral Q.5s | CSW Lateral at Q.5s | 15059001-02 | Oct/24/2022 | Oct/24/2022 | Oct/20/2022 | Oct/20/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 270 | WASTE | E-62ec07140d26f52b04ad9a4a
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-02-F15-C4DMW-275-Lateral G14 | C4DMW Lateral at G14 | 15059001-02 | Dec/15/2022 | Dec/15/2022 | Dec/20/2022 | Dec/20/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 275 | WASTE | E-62ec07140d26f59877ad9a4b
Passed | PROC CC | JE DUNN-ALOHA | 15059001-02-F15-C4DMW-275-Lateral G14 | C4DMW Lateral at G14 | 15059001-02 | Dec/08/2022 | Dec/08/2022 | Oct/12/2022 | Dec/19/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 275 | WASTE | E-62ec07140d26f59877ad9a4b
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-02-F15-C4DMW-275-Lateral G14 | C4DMW Lateral at G14 | 15059001-02 | Dec/21/2022 | Jan/23/2023 | Jan/17/2023 | Jan/17/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 275 | WASTE | E-62ec07140d26f59877ad9a4b
Passed | PROC CC | JE DUNN-ALOHA | 15059001-02-F15-C4CMW-276-Lateral G14 | C4CMW Lateral at G14 | 15059001-02 | Dec/08/2022 | Dec/08/2022 | Oct/14/2022 | Dec/19/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 276 | WASTE | E-62ec07140d26f52c1ead9a4d
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-02-F15-C4CMW-276-Lateral G14 | C4CMW Lateral at G14 | 15059001-02 | Dec/15/2022 | Dec/15/2022 | Dec/20/2022 | Dec/20/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 276 | WASTE | E-62ec07140d26f52c1ead9a4d
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-02-F15-C4CMW-276-Lateral G14 | C4CMW Lateral at G14 | 15059001-02 | Dec/21/2022 | Jan/23/2023 | Jan/17/2023 | Jan/17/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 276 | WASTE | E-62ec07140d26f52c1ead9a4d
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-02-F15-C4DMW-275-W19 | C4DMW Lateral at W19 | 15059001-02 | Feb/10/2023 | Mar/03/2023 | Mar/08/2023 | Mar/08/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 275 | WASTE | E-62ec07140d26f547bead9a4c
Passed | PROC CC | JE DUNN-ALOHA | 15059001-02-F15-C4DMW-275-W19 | C4DMW Lateral at W19 | 15059001-02 | Jan/27/2023 | Jan/27/2023 | Dec/21/2022 | Jan/24/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 275 | WASTE | E-62ec07140d26f547bead9a4c
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-02-F15-C4DMW-275-W19 | C4DMW Lateral at W19 | 15059001-02 | Feb/03/2023 | Feb/03/2023 | Jan/26/2023 | Jan/26/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 275 | WASTE | E-62ec07140d26f547bead9a4c
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-02-F15-GSW-269-Lateral Q.5s | GSW Lateral at Q.5s | 15059001-02 | Oct/24/2022 | Nov/02/2022 | Nov/07/2022 | Nov/07/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 269 | WASTE | E-62ec07140d26f503d2ad9a4f
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-02-F15-GSW-269-Lateral Q.5s | GSW Lateral at Q.5s | 15059001-02 | Oct/24/2022 | Oct/24/2022 | Oct/20/2022 | Oct/20/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 269 | WASTE | E-62ec07140d26f503d2ad9a4f
Passed | PROC CC | JE DUNN-ALOHA | 15059001-02-F15-GSW-269-Lateral Q.5s | GSW Lateral at Q.5s | 15059001-02 | Oct/17/2022 | Oct/17/2022 | Oct/20/2022 | Oct/20/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 269 | WASTE | E-62ec07140d26f503d2ad9a4f
Passed | PROC CC | JE DUNN-ALOHA | 15059001-02-F15-HFW-266-Lateral Q.5s | HFW Lateral at Q.5s | 15059001-02 | Dec/15/2022 | Dec/15/2022 | Dec/15/2022 | Dec/15/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 266 | WASTE | E-62ec07140d26f51561ad9a50
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-02-F15-HFW-266-Lateral Q.5s | HFW Lateral at Q.5s | 15059001-02 | Dec/22/2022 | Dec/22/2022 | Dec/20/2022 | Dec/20/2022 | F15 | F15 WW51 LOR Waste Laterals |  | 266 | WASTE | E-62ec07140d26f51561ad9a50
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-02-F15-HFW-266-Lateral Q.5s | HFW Lateral at Q.5s | 15059001-02 | Dec/21/2022 | Jan/23/2023 | Jan/17/2023 | Jan/17/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 266 | WASTE | E-62ec07140d26f51561ad9a50
Passed | PROC CC | JE DUNN-ALOHA | 15059001-02-F15-C4CMW-276-Lateral W19 | C4CMW Lateral at W19 | 15059001-02 | Jan/27/2023 | Jan/27/2023 | Jan/25/2023 | Jan/25/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 276 | WASTE | E-62ec07140d26f509d1ad9a4e
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-02-F15-C4CMW-276-Lateral W19 | C4CMW Lateral at W19 | 15059001-02 | Feb/10/2023 | Feb/10/2023 | Feb/09/2023 | Feb/09/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 276 | WASTE | E-62ec07140d26f509d1ad9a4e
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-02-F15-C4CMW-276-Lateral W19 | C4CMW Lateral at W19 | 15059001-02 | Feb/10/2023 | Mar/03/2023 | Mar/08/2023 | Mar/08/2023 | F15 | F15 WW51 LOR Waste Laterals |  | 276 | WASTE | E-62ec07140d26f509d1ad9a4e
Passed | ELECT DV | JE DUNN-ALOHA | 15058484-01-S1R1V18A-17 | CO2 GC eV Heater | 15058484-01 | Nov/17/2022 | Nov/17/2022 | Nov/28/2022 | Nov/28/2022 | F15 | CO2 Heat Trace | 15058484-01 | 500 | SPECIALTY GAS SYSTEMS | E-62ffb5eb0f995b272268b5fb
Passed | EQ CC/GT | JE DUNN-ALOHA | 15058484-01-S1R1V18A-17 | CO2 GC eV Heater | 15058484-01 | Dec/07/2022 | Dec/07/2022 | Dec/13/2022 | Dec/13/2022 | F15 | CO2 Heat Trace | 15058484-01 | 500 | SPECIALTY GAS SYSTEMS | E-62ffb5eb0f995b272268b5fb
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-01-S1R1V18A-17 | CO2 GC eV Heater | 15058484-01 | Nov/16/2022 | Nov/16/2022 | Nov/23/2022 | Nov/23/2022 | F15 | CO2 Heat Trace | 15058484-01 | 500 | SPECIALTY GAS SYSTEMS | E-62ffb5eb0f995b272268b5fb
Passed | FAT | JE DUNN-ALOHA | 15058484-01-S1R1V18A-17 | CO2 GC eV Heater | 15058484-01 | Dec/07/2022 | Jan/23/2023 | Jan/18/2023 | Jan/18/2023 | F15 | CO2 Heat Trace | 15058484-01 | 500 | SPECIALTY GAS SYSTEMS | E-62ffb5eb0f995b272268b5fb
Passed | EQ OA/BT | JE DUNN-ALOHA | 15058484-01-S1R1V18A-17 | CO2 GC eV Heater | 15058484-01 | Dec/07/2022 | Jan/23/2023 | Jan/24/2023 | Jan/24/2023 | F15 | CO2 Heat Trace | 15058484-01 | 500 | SPECIALTY GAS SYSTEMS | E-62ffb5eb0f995b272268b5fb
Passed | ELECT OAT | JE DUNN-ALOHA | 15058484-01-S1R1V18A-17 | CO2 GC eV Heater | 15058484-01 | Nov/16/2022 | Nov/16/2022 | Nov/23/2022 | Nov/23/2022 | F15 | CO2 Heat Trace | 15058484-01 | 500 | SPECIALTY GAS SYSTEMS | E-62ffb5eb0f995b272268b5fb
Passed | INST FAT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/08/2023 | Feb/16/2023 | Feb/09/2023 | Feb/09/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | EQ OA/BT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/09/2023 | Mar/03/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | PROC CC | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Jan/31/2023 | Jan/31/2023 | Feb/06/2023 | Feb/06/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | I&C OAT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/08/2023 | Feb/08/2023 | Feb/02/2023 | Feb/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | EQ CC/GT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/08/2023 | Feb/08/2023 | Feb/08/2023 | Feb/08/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/08/2023 | Feb/08/2023 | Feb/02/2023 | Feb/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | I&C CC | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Jan/31/2023 | Jan/31/2023 | Feb/06/2023 | Feb/06/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | FAT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/09/2023 | Mar/03/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | I&C DV | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/09/2023 | Feb/09/2023 | Feb/03/2023 | Feb/03/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | PROC DV | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-3 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/01/2023 | Feb/01/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f4751e923fb
Passed | PROC CC | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-Q.5s | HPN2 Lateral | 15059001-01 | Jan/31/2023 | Jan/31/2023 | Nov/14/2022 | Feb/06/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f7f46e923fe
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-Q.5s | HPN2 Lateral | 15059001-01 | Feb/20/2023 | Feb/28/2023 | Feb/16/2023 | Feb/16/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f7f46e923fe
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-Q.5s | HPN2 Lateral | 15059001-01 | Feb/08/2023 | Feb/08/2023 | Feb/08/2023 | Feb/08/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f7f46e923fe
Passed | PROC CC | JE DUNN-ALOHA | 15059001-01-F15-500BGS-5%H2/He-18F/G-N.5n | BGS Lateral | 15059001-01 | Aug/24/2022 | Aug/24/2022 | Sep/20/2022 | Sep/20/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 500 | SPECIALTY GAS SYSTEMS | E-62ffbfedb7658f7735e92401
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-01-F15-500BGS-5%H2/He-18F/G-N.5n | BGS Lateral | 15059001-01 | Sep/28/2022 | Sep/28/2022 | Sep/23/2022 | Oct/12/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 500 | SPECIALTY GAS SYSTEMS | E-62ffbfedb7658f7735e92401
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-01-F15-500BGS-5%H2/He-18F/G-N.5n | BGS Lateral | 15059001-01 | Oct/13/2022 | Oct/19/2022 | Oct/26/2022 | Oct/26/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 500 | SPECIALTY GAS SYSTEMS | E-62ffbfedb7658f7735e92401
Passed | PROC CC | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Jan/31/2023 | Jan/31/2023 | Feb/06/2023 | Feb/06/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | PROC DV | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/01/2023 | Feb/01/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | I&C OAT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/08/2023 | Feb/08/2023 | Feb/02/2023 | Feb/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | FAT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/09/2023 | Mar/03/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | INST FAT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/08/2023 | Feb/16/2023 | Feb/09/2023 | Feb/09/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | I&C CC | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Jan/31/2023 | Jan/31/2023 | Feb/06/2023 | Feb/06/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | EQ OA/BT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/09/2023 | Mar/03/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/08/2023 | Feb/08/2023 | Feb/02/2023 | Feb/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | EQ CC/GT | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/08/2023 | Feb/08/2023 | Feb/08/2023 | Feb/08/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | I&C DV | JE DUNN-ALOHA | 15059001-01-F15-PIT408-10-4 | HPN2 Lateral End-Of-Lateral Pressure Transmitter | 15059001-01 | Feb/09/2023 | Feb/09/2023 | Feb/02/2023 | Feb/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658fdcd3e923fc
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-R.5s | HPN2 Lateral | 15059001-01 | Dec/05/2022 | Dec/05/2022 | Sep/22/2022 | Sep/22/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f43bce923fd
Passed | PROC CC | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-R.5s | HPN2 Lateral | 15059001-01 | Jan/24/2023 | Jan/24/2023 | Sep/06/2022 | Sep/06/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f43bce923fd
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-R.5s | HPN2 Lateral | 15059001-01 | Sep/23/2022 | Oct/14/2022 | Oct/13/2022 | Oct/13/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f43bce923fd
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-M.5s | HPN2 Lateral | 15059001-01 |  |  | Sep/19/2022 | Sep/22/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f0788e923ff
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-M.5s | HPN2 Lateral | 15059001-01 | Sep/23/2022 | Oct/21/2022 | Oct/13/2022 | Oct/13/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f0788e923ff
Passed | PROC CC | JE DUNN-ALOHA | 15059001-01-F15-408HPN2-M.5s | HPN2 Lateral | 15059001-01 |  |  | Sep/06/2022 | Sep/06/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 408 | BULK GAS SYSTEMS | E-62ffbfedb7658f0788e923ff
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059001-01-F15-500BGS-5%H2/He-I8F/G-F.5n | BGS Lateral | 15059001-01 | Sep/28/2022 | Sep/28/2022 | Oct/12/2022 | Oct/12/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 500 | SPECIALTY GAS SYSTEMS | E-62ffbfedb7658f4773e92402
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059001-01-F15-500BGS-5%H2/He-I8F/G-F.5n | BGS Lateral | 15059001-01 | Oct/13/2022 | Oct/19/2022 | Oct/26/2022 | Oct/26/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 500 | SPECIALTY GAS SYSTEMS | E-62ffbfedb7658f4773e92402
Passed | PROC CC | JE DUNN-ALOHA | 15059001-01-F15-500BGS-5%H2/He-I8F/G-F.5n | BGS Lateral | 15059001-01 | Sep/21/2022 | Sep/21/2022 | Sep/20/2022 | Oct/12/2022 | F15 | F15 WW51 LOR-Gas Laterals |  | 500 | SPECIALTY GAS SYSTEMS | E-62ffbfedb7658f4773e92402
Passed | ELECT OAT | JE DUNN-ALOHA | 15052533-859 860-A4T1E1A | 480:208/120V 300KVA XFMR | 15052533-859 860 |  |  | Sep/15/2022 | Sep/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae88925883a4
Passed | EQ OA/BT | JE DUNN-ALOHA | 15052533-859 860-A4T1E1A | 480:208/120V 300KVA XFMR | 15052533-859 860 |  |  | Oct/13/2022 | Oct/13/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae88925883a4
Passed | ELECT CC | JE DUNN-ALOHA | 15052533-859 860-A4T1E1A | 480:208/120V 300KVA XFMR | 15052533-859 860 |  |  | Sep/15/2022 | Sep/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae88925883a4
Passed | EQ CC/GT | JE DUNN-ALOHA | 15052533-859 860-A4T1E1A | 480:208/120V 300KVA XFMR | 15052533-859 860 |  |  | Sep/30/2022 | Oct/06/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae88925883a4
Passed | ELECT OAT | JE DUNN-ALOHA | 15052533-859 860-A4T1H1A | 480:208/120V 300KVA XFMR | 15052533-859 860 | Oct/13/2022 | Oct/13/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae65545883a5
Passed | ELECT CC | JE DUNN-ALOHA | 15052533-859 860-A4T1H1A | 480:208/120V 300KVA XFMR | 15052533-859 860 | Oct/13/2022 | Oct/13/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae65545883a5
Passed | EQ OA/BT | JE DUNN-ALOHA | 15052533-859 860-A4T1H1A | 480:208/120V 300KVA XFMR | 15052533-859 860 | Oct/21/2022 | Oct/27/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae65545883a5
Passed | EQ CC/GT | JE DUNN-ALOHA | 15052533-859 860-A4T1H1A | 480:208/120V 300KVA XFMR | 15052533-859 860 | Oct/20/2022 | Oct/20/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae65545883a5
Passed | DIST OA/BT | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-TP2 | Lateral S/R | 15052533-859 860 |  |  | Oct/03/2022 | Oct/03/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-6307df410a9daeebfc5883a7
Passed | MECH W CC | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-TP2 | Lateral S/R | 15052533-859 860 |  |  | Aug/30/2022 | Aug/30/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-6307df410a9daeebfc5883a7
Passed | FAT | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-TP2 | Lateral S/R | 15052533-859 860 |  |  | Oct/03/2022 | Oct/03/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-6307df410a9daeebfc5883a7
Passed | DIST CC/GT | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-TP2 | Lateral S/R | 15052533-859 860 |  |  | Sep/30/2022 | Sep/30/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-6307df410a9daeebfc5883a7
Passed | ELECT CC | JE DUNN-ALOHA | 15052533-859 860-A4D1E1A | 208V D-BOARD | 15052533-859 860 |  |  | Sep/15/2022 | Sep/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae60d65883ab
Passed | ELECT OAT | JE DUNN-ALOHA | 15052533-859 860-A4D1E1A | 208V D-BOARD | 15052533-859 860 |  |  | Sep/15/2022 | Sep/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae60d65883ab
Passed | EQ OA/BT | JE DUNN-ALOHA | 15052533-859 860-A4D1E1A | 208V D-BOARD | 15052533-859 860 |  |  | Oct/13/2022 | Oct/13/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae60d65883ab
Passed | EQ CC/GT | JE DUNN-ALOHA | 15052533-859 860-A4D1E1A | 208V D-BOARD | 15052533-859 860 |  |  | Sep/30/2022 | Oct/06/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae60d65883ab
Passed | EQ CC/GT | JE DUNN-ALOHA | 15052533-859 860-A4D1H1A | 208V D-BOARD | 15052533-859 860 | Oct/20/2022 | Oct/20/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae57bd5883ac
Passed | ELECT CC | JE DUNN-ALOHA | 15052533-859 860-A4D1H1A | 208V D-BOARD | 15052533-859 860 | Oct/13/2022 | Oct/13/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae57bd5883ac
Passed | EQ OA/BT | JE DUNN-ALOHA | 15052533-859 860-A4D1H1A | 208V D-BOARD | 15052533-859 860 | Oct/21/2022 | Oct/27/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae57bd5883ac
Passed | ELECT OAT | JE DUNN-ALOHA | 15052533-859 860-A4D1H1A | 208V D-BOARD | 15052533-859 860 | Oct/13/2022 | Oct/13/2022 | Oct/20/2022 | Oct/20/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae57bd5883ac
Passed | EQ OA/BT | JE DUNN-ALOHA | 15052533-859 860-A4D1G1B | 208V D-BOARD | 15052533-859 860 | Oct/01/2022 | Oct/07/2022 | Oct/13/2022 | Oct/13/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae6eb85883ad
Passed | ELECT CC | JE DUNN-ALOHA | 15052533-859 860-A4D1G1B | 208V D-BOARD | 15052533-859 860 | Sep/23/2022 | Sep/23/2022 | Sep/22/2022 | Sep/22/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae6eb85883ad
Passed | ELECT OAT | JE DUNN-ALOHA | 15052533-859 860-A4D1G1B | 208V D-BOARD | 15052533-859 860 | Sep/23/2022 | Sep/23/2022 | Sep/22/2022 | Sep/22/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae6eb85883ad
Passed | EQ CC/GT | JE DUNN-ALOHA | 15052533-859 860-A4D1G1B | 208V D-BOARD | 15052533-859 860 | Sep/30/2022 | Sep/30/2022 | Sep/28/2022 | Oct/06/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9dae6eb85883ad
Passed | EQ OA/BT | JE DUNN-ALOHA | 15052533-859 860-A4T1E2A | 480:208/120V 300KVA XFMR | 15052533-859 860 |  |  | Oct/13/2022 | Oct/13/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9daed25f5883ae
Passed | ELECT OAT | JE DUNN-ALOHA | 15052533-859 860-A4T1E2A | 480:208/120V 300KVA XFMR | 15052533-859 860 |  |  | Sep/15/2022 | Sep/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9daed25f5883ae
Passed | ELECT CC | JE DUNN-ALOHA | 15052533-859 860-A4T1E2A | 480:208/120V 300KVA XFMR | 15052533-859 860 |  |  | Sep/15/2022 | Sep/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9daed25f5883ae
Passed | EQ CC/GT | JE DUNN-ALOHA | 15052533-859 860-A4T1E2A | 480:208/120V 300KVA XFMR | 15052533-859 860 |  |  | Sep/30/2022 | Oct/06/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9daed25f5883ae
Passed | DIST OA/BT | JE DUNN-ALOHA | 15052533-859 860-AL4-221PV-T6 | Lateral | 15052533-859 860 |  |  | Oct/18/2022 | Oct/18/2022 | AL4 |  |  | 221 | MECHANICAL PROCESS | E-6307e40b64165c1f04888e59
Passed | PROC CC | JE DUNN-ALOHA | 15052533-859 860-AL4-221PV-T6 | Lateral | 15052533-859 860 |  |  | Aug/30/2022 | Aug/30/2022 | AL4 |  |  | 221 | MECHANICAL PROCESS | E-6307e40b64165c1f04888e59
Passed | DIST CC/GT | JE DUNN-ALOHA | 15052533-859 860-AL4-221PV-T6 | Lateral | 15052533-859 860 |  |  | Oct/13/2022 | Oct/13/2022 | AL4 |  |  | 221 | MECHANICAL PROCESS | E-6307e40b64165c1f04888e59
Passed | PROC CC | JE DUNN-ALOHA | 15052533-859 860-AL4-212OFA-TP5 | Lateral | 15052533-859 860 |  |  | Aug/25/2022 | Aug/25/2022 | AL4 | Phase 4 Bays 859/860 |  | 212 | MECHANICAL PROCESS | E-6307df410a9daed09a5883a9
Passed | DIST CC/GT | JE DUNN-ALOHA | 15052533-859 860-AL4-212OFA-TP5 | Lateral | 15052533-859 860 |  |  | Sep/30/2022 | Sep/30/2022 | AL4 | Phase 4 Bays 859/860 |  | 212 | MECHANICAL PROCESS | E-6307df410a9daed09a5883a9
Passed | DIST OA/BT | JE DUNN-ALOHA | 15052533-859 860-AL4-212OFA-TP5 | Lateral | 15052533-859 860 |  |  | Oct/03/2022 | Oct/03/2022 | AL4 | Phase 4 Bays 859/860 |  | 212 | MECHANICAL PROCESS | E-6307df410a9daed09a5883a9
Passed | EQ OA/BT | JE DUNN-ALOHA | 15052533-859 860-A4D1E2A | 208V D-BOARD | 15052533-859 860 |  |  | Oct/13/2022 | Oct/13/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9daecd235883aa
Passed | ELECT CC | JE DUNN-ALOHA | 15052533-859 860-A4D1E2A | 208V D-BOARD | 15052533-859 860 |  |  | Sep/15/2022 | Sep/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9daecd235883aa
Passed | EQ CC/GT | JE DUNN-ALOHA | 15052533-859 860-A4D1E2A | 208V D-BOARD | 15052533-859 860 |  |  | Sep/30/2022 | Oct/06/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9daecd235883aa
Passed | ELECT OAT | JE DUNN-ALOHA | 15052533-859 860-A4D1E2A | 208V D-BOARD | 15052533-859 860 |  |  | Sep/15/2022 | Sep/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 603 | ELECTRICAL | E-6307df410a9daecd235883aa
Passed | MECH D CC | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Oct/11/2022 | Oct/11/2022 | Oct/13/2022 | Oct/13/2022 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | MECH D DV | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Feb/08/2023 | Feb/08/2023 | Feb/14/2023 | Feb/14/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Jan/30/2023 | Jan/30/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | ELECT DV | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Feb/08/2023 | Feb/08/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | ARCH CC | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Jan/30/2023 | Jan/30/2023 | Feb/01/2023 | Feb/01/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | ARCH DV | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Feb/08/2023 | Feb/08/2023 | Feb/06/2023 | Feb/14/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | LSS OAT | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Jan/30/2023 | Jan/30/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | LSS CC | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Jan/30/2023 | Jan/30/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | EHS | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Feb/08/2023 | Feb/08/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | RR CC/GT | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Feb/14/2023 | Feb/14/2023 | Feb/16/2023 | Feb/16/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | FAT | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Feb/20/2023 | Mar/20/2023 | Feb/28/2023 | Feb/28/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | LSS DV | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Feb/08/2023 | Feb/08/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | RR OA/BT | JE DUNN-ALOHA | 15058484-02-F15-CSA-Baylet 559W DEMO | Baylet 559W DEMO | 15058484-02 | Feb/20/2023 | Mar/20/2023 | Feb/28/2023 | Feb/28/2023 | F15 | F15 WW51 LOR - Baylet 559 Deinstall |  | RR | ROOM/AREA/BAY-READY | E-630785dc0f995b8a8f6b0bd5
Passed | DIST OA/BT | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-TP1 | Lateral S/R | 15052533-859 860 |  |  | Oct/03/2022 | Oct/03/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-6307df410a9dae4bf75883a3
Passed | MECH W CC | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-TP1 | Lateral S/R | 15052533-859 860 |  |  | Aug/30/2022 | Aug/30/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-6307df410a9dae4bf75883a3
Passed | FAT | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-TP1 | Lateral S/R | 15052533-859 860 |  |  | Oct/03/2022 | Oct/03/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-6307df410a9dae4bf75883a3
Passed | DIST CC/GT | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-TP1 | Lateral S/R | 15052533-859 860 |  |  | Sep/30/2022 | Sep/30/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-6307df410a9dae4bf75883a3
Passed | RR OA/BT | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Feb/06/2023 | Mar/06/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | ELECT DV | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Jan/02/2023 | Jan/02/2023 | Dec/12/2022 | Dec/27/2022 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | MECH D CC | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Nov/01/2022 | Nov/01/2022 | Nov/03/2022 | Nov/03/2022 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Dec/30/2022 | Dec/30/2022 | Nov/08/2022 | Jan/04/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | EHS | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Jan/23/2023 | Jan/23/2023 | Jan/18/2023 | Jan/18/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | FAT | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Feb/06/2023 | Mar/06/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | ARCH DV | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Jan/02/2023 | Jan/02/2023 | Dec/10/2022 | Jan/06/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | MECH D DV | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Dec/01/2022 | Dec/01/2022 | Dec/12/2022 | Dec/13/2022 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | ARCH CC | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Nov/30/2022 | Nov/30/2022 | Nov/03/2022 | Dec/12/2022 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | RR CC/GT | JE DUNN-ALOHA | 15058484-04-F15-CSA-501/502 Bay Upgrade | Bay Upgrade: New Wall, Windows, return air grills, filters, | 15058484-04 | Feb/03/2023 | Feb/03/2023 | Feb/03/2023 | Feb/03/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | ROOM/AREA/BAY-READY | E-630fc1d264165cca488aa13b
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-05-F15-CH3F-H.5/18.5 VMB | VMB | 15058484-05 | Nov/03/2022 | Nov/09/2022 | Oct/13/2022 | Nov/09/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f50239fd7b34a
Passed | MECH D CC | JE DUNN-ALOHA | 15058484-05-F15-CH3F-H.5/18.5 VMB | VMB | 15058484-05 | Nov/03/2022 | Nov/09/2022 | Nov/10/2022 | Nov/10/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f50239fd7b34a
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-05-F15-CH3F-H.5/18.5 VMB | VMB | 15058484-05 | Feb/02/2023 | Feb/10/2023 | Feb/06/2023 | Feb/06/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f50239fd7b34a
Passed | SL1 | JE DUNN-ALOHA | 15058484-05-F15-CH3F-H.5/18.5 VMB | VMB | 15058484-05 | Feb/07/2023 | Apr/28/2023 | Apr/19/2023 | Apr/19/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f50239fd7b34a
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058484-05-F15-CH3F-H.5/18.5 VMB | VMB | 15058484-05 | Feb/07/2023 | Apr/28/2023 | Apr/19/2023 | Apr/19/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f50239fd7b34a
Passed | PROC CC | JE DUNN-ALOHA | 15058484-05-F15-CH3F-H.5/18.5 VMB | VMB | 15058484-05 | Oct/17/2022 | Oct/17/2022 | Sep/13/2022 | Oct/12/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f50239fd7b34a
Passed | SL2 | JE DUNN-ALOHA | 15058484-05-F15-CH3F-H.5/18.5 VMB | VMB | 15058484-05 | Feb/07/2023 | Apr/28/2023 | Apr/19/2023 | Apr/19/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f50239fd7b34a
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058484-05-F15-Staging Cabinet-Y.3/19.3 | Staging Cabinet | 15058484-05 | Feb/07/2023 | Apr/19/2023 | May/04/2023 | May/04/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f509916d7b34c
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-05-F15-Staging Cabinet-Y.3/19.3 | Staging Cabinet | 15058484-05 | Nov/03/2022 | Nov/09/2022 | Oct/13/2022 | Nov/09/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f509916d7b34c
Passed | PROC CC | JE DUNN-ALOHA | 15058484-05-F15-Staging Cabinet-Y.3/19.3 | Staging Cabinet | 15058484-05 | Oct/17/2022 | Oct/17/2022 | Sep/13/2022 | Oct/12/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f509916d7b34c
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-05-F15-Staging Cabinet-Y.3/19.3 | Staging Cabinet | 15058484-05 | Feb/10/2023 | Feb/10/2023 | Feb/06/2023 | Feb/06/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f509916d7b34c
Passed | MECH D CC | JE DUNN-ALOHA | 15058484-05-F15-Staging Cabinet-Y.3/19.3 | Staging Cabinet | 15058484-05 | Nov/03/2022 | Nov/09/2022 | Nov/10/2022 | Nov/10/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f509916d7b34c
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058484-05-F15-CH3F-C3-C/D GC | Gas Cabinet | 15058484-05 | Feb/07/2023 | Apr/28/2023 | Apr/19/2023 | Apr/19/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f5034b8d7b34b
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-05-F15-CH3F-C3-C/D GC | Gas Cabinet | 15058484-05 | Nov/03/2022 | Nov/09/2022 | Oct/13/2022 | Nov/09/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f5034b8d7b34b
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-05-F15-CH3F-C3-C/D GC | Gas Cabinet | 15058484-05 | Feb/10/2023 | Feb/10/2023 | Feb/06/2023 | Feb/06/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f5034b8d7b34b
Passed | PROC CC | JE DUNN-ALOHA | 15058484-05-F15-CH3F-C3-C/D GC | Gas Cabinet | 15058484-05 | Oct/17/2022 | Oct/17/2022 | Sep/13/2022 | Oct/12/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f5034b8d7b34b
Passed | SL1 | JE DUNN-ALOHA | 15058484-05-F15-CH3F-C3-C/D GC | Gas Cabinet | 15058484-05 | Feb/07/2023 | Apr/28/2023 | Apr/19/2023 | Apr/19/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f5034b8d7b34b
Passed | MECH D CC | JE DUNN-ALOHA | 15058484-05-F15-CH3F-C3-C/D GC | Gas Cabinet | 15058484-05 | Nov/03/2022 | Nov/09/2022 | Nov/10/2022 | Nov/10/2022 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f5034b8d7b34b
Passed | SL2 | JE DUNN-ALOHA | 15058484-05-F15-CH3F-C3-C/D GC | Gas Cabinet | 15058484-05 | Feb/07/2023 | Apr/28/2023 | Apr/19/2023 | Apr/19/2023 | F15 | CH3F for PAT501 |  | 500 | SPECIALTY GAS SYSTEMS | E-630f8303805f5034b8d7b34b
Passed | I&C OAT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1A | UPW Dist. EOL | 15048483-01 | Feb/02/2023 | Feb/02/2023 | Feb/07/2023 | Feb/07/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-631229628262abfdb9a22719
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1A | UPW Dist. EOL | 15048483-01 | Feb/09/2023 | Feb/09/2023 | Feb/09/2023 | Feb/09/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-631229628262abfdb9a22719
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1A | UPW Dist. EOL | 15048483-01 | Jan/24/2023 | Jun/02/2023 | May/12/2023 | May/24/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-631229628262abfdb9a22719
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1A | UPW Dist. EOL | 15048483-01 | Jan/04/2023 | Jan/04/2023 | Jan/16/2023 | Jan/16/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-631229628262abfdb9a22719
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1A | UPW Dist. EOL | 15048483-01 | Feb/02/2023 | Feb/02/2023 | Feb/07/2023 | Feb/07/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-631229628262abfdb9a22719
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1A | UPW Dist. EOL | 15048483-01 | Feb/03/2023 | Feb/03/2023 | Feb/07/2023 | Feb/16/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-631229628262abfdb9a22719
Passed | PROC CC | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1A | UPW Dist. EOL | 15048483-01 | Nov/28/2022 | Nov/28/2022 | Oct/17/2022 | Oct/17/2022 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-631229628262abfdb9a22719
In Progress | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1A | UPW Dist. EOL | 15048483-01 | Jan/24/2023 | Jul/06/2023 | May/22/2023 |  | F15 | PLC5 Phase 1 |  | 245 | UPW | E-631229628262abfdb9a22719
Passed | RR OA/BT | JE DUNN-ALOHA | 15053514-03-AL3-RR-CSA-Mech Room 3224 | Room Modification | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/28/2023 | Feb/28/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | RR | ROOM/AREA/BAY-READY | E-6319228feab4af7c05975185
Passed | ARCH DV | JE DUNN-ALOHA | 15053514-03-AL3-RR-CSA-Mech Room 3224 | Room Modification | 15053514-03 | Jan/06/2023 | Jan/06/2023 | Dec/28/2022 | Dec/28/2022 | AL3 | ODP WW42 LRP IW Booster Pump |  | RR | ROOM/AREA/BAY-READY | E-6319228feab4af7c05975185
Passed | EHS | JE DUNN-ALOHA | 15053514-03-AL3-RR-CSA-Mech Room 3224 | Room Modification | 15053514-03 | Jan/30/2023 | Jan/30/2023 | Feb/07/2023 | Feb/07/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | RR | ROOM/AREA/BAY-READY | E-6319228feab4af7c05975185
Passed | ARCH CC | JE DUNN-ALOHA | 15053514-03-AL3-RR-CSA-Mech Room 3224 | Room Modification | 15053514-03 | Jan/20/2023 | Jan/20/2023 | Jan/25/2023 | Jan/25/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | RR | ROOM/AREA/BAY-READY | E-6319228feab4af7c05975185
Passed | FAT | JE DUNN-ALOHA | 15053514-03-AL3-RR-CSA-Mech Room 3224 | Room Modification | 15053514-03 | Feb/07/2023 | Feb/23/2023 | Feb/28/2023 | Feb/28/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | RR | ROOM/AREA/BAY-READY | E-6319228feab4af7c05975185
Passed | RR CC/GT | JE DUNN-ALOHA | 15053514-03-AL3-RR-CSA-Mech Room 3224 | Room Modification | 15053514-03 | Feb/03/2023 | Feb/03/2023 | Feb/08/2023 | Feb/08/2023 | AL3 | ODP WW42 LRP IW Booster Pump |  | RR | ROOM/AREA/BAY-READY | E-6319228feab4af7c05975185
Passed | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | May/16/2023 | May/16/2023 | Apr/24/2023 | May/16/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Passed | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | May/16/2023 | May/16/2023 | Apr/13/2023 | May/17/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Not Started | SL1 | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | May/02/2023 | May/02/2023 | Apr/13/2023 | May/08/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Passed | MECH D CC | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | May/02/2023 | May/02/2023 | Apr/18/2023 | May/01/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Passed | TELE CC | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | May/02/2023 | May/02/2023 | May/08/2023 | May/08/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Not Started | SL2 | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | Jun/02/2023 | Jun/02/2023 | Jun/01/2023 | Jun/01/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-CPE-CDM-1 | Chemical Distribution Module | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af650b97bb14
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-T-CUPUR-M.1/17.7-S | Aqueous Valve Box | 15058484-03 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af7f4797bb16
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-T-CUPUR-M.1/17.7-S | Aqueous Valve Box | 15058484-03 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af7f4797bb16
Not Started | SL2 | JE DUNN-ALOHA | 15058484-03-F15-T-CUPUR-M.1/17.7-S | Aqueous Valve Box | 15058484-03 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af7f4797bb16
Not Started | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-T-CUPUR-M.1/17.7-S | Aqueous Valve Box | 15058484-03 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af7f4797bb16
Not Started | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-T-CUPUR-M.1/17.7-S | Aqueous Valve Box | 15058484-03 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af7f4797bb16
Not Started | SL1 | JE DUNN-ALOHA | 15058484-03-F15-T-CUPUR-M.1/17.7-S | Aqueous Valve Box | 15058484-03 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af7f4797bb16
Passed | I&C OAT | JE DUNN-ALOHA | 15058484-03-F15-XV269-3A-01A | SOLENOID VALVE | 15058484-03 | May/16/2023 | May/16/2023 | May/17/2023 | May/17/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af2d7597bb22
Passed | I&C OAT | JE DUNN-ALOHA | 15058484-03-F15-LSHH269-3-01A | LEVEL SWITCH HIGH HIGH | 15058484-03 | May/10/2023 | May/10/2023 | May/17/2023 | May/17/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af1f3697bb0e
Not Started | INST FAT | JE DUNN-ALOHA | 15058484-03-F15-LSHH269-3-01A | LEVEL SWITCH HIGH HIGH | 15058484-03 | May/25/2023 | May/25/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af1f3697bb0e
Not Started | SL2 | JE DUNN-ALOHA | 15058484-03-F15-T-UNSTAB30%H2O2-M.1/17.3-S | Aqueous Valve Box | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af3dc797bb13
In Progress | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-T-UNSTAB30%H2O2-M.1/17.3-S | Aqueous Valve Box | 15058484-03 | Jun/02/2023 | Jun/02/2023 | May/11/2023 |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af3dc797bb13
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-T-UNSTAB30%H2O2-M.1/17.3-S | Aqueous Valve Box | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af3dc797bb13
Passed | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-T-UNSTAB30%H2O2-M.1/17.3-S | Aqueous Valve Box | 15058484-03 | May/26/2023 | May/26/2023 | Apr/07/2023 | Jun/01/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af3dc797bb13
Passed | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-T-UNSTAB30%H2O2-M.1/17.3-S | Aqueous Valve Box | 15058484-03 | Apr/24/2023 | Apr/24/2023 | Apr/17/2023 | Apr/17/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af3dc797bb13
Not Started | SL1 | JE DUNN-ALOHA | 15058484-03-F15-T-UNSTAB30%H2O2-M.1/17.3-S | Aqueous Valve Box | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af3dc797bb13
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | May/16/2023 | May/16/2023 | May/18/2023 | May/18/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
Passed | I&C DV | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | May/17/2023 | May/17/2023 | May/15/2023 | May/15/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
Passed | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | May/16/2023 | May/16/2023 | May/17/2023 | May/17/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | Jun/02/2023 | Jun/02/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
Passed | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | May/16/2023 | May/16/2023 | May/11/2023 | May/16/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
In Progress | EHS | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | May/29/2023 | May/29/2023 | May/25/2023 |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
Not Started | FAT | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
Passed | PROC DV | JE DUNN-ALOHA | 15058484-03-F15-TK269-3-01 | Waste Collection Tank | 15058484-03 | May/09/2023 | May/09/2023 | May/10/2023 | May/10/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af348997bb19
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-T-SULATS-M.1/17.8-S | Aqueous Valve Box | 15058484-03 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afceac97bb1c
Not Started | SL1 | JE DUNN-ALOHA | 15058484-03-F15-T-SULATS-M.1/17.8-S | Aqueous Valve Box | 15058484-03 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afceac97bb1c
Not Started | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-T-SULATS-M.1/17.8-S | Aqueous Valve Box | 15058484-03 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afceac97bb1c
Not Started | SL2 | JE DUNN-ALOHA | 15058484-03-F15-T-SULATS-M.1/17.8-S | Aqueous Valve Box | 15058484-03 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afceac97bb1c
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-T-SULATS-M.1/17.8-S | Aqueous Valve Box | 15058484-03 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afceac97bb1c
Not Started | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-T-SULATS-M.1/17.8-S | Aqueous Valve Box | 15058484-03 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afceac97bb1c
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-SVB (relable) | Solvent Valve Box(Repurposed) | 15058484-03 | Feb/21/2023 | Mar/15/2023 | Mar/22/2023 | Mar/22/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af58d797bb1e
Passed | SL1 | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-SVB (relable) | Solvent Valve Box(Repurposed) | 15058484-03 | Feb/21/2023 | Mar/10/2023 | Mar/10/2023 | Mar/10/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af58d797bb1e
Passed | SL2 | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-SVB (relable) | Solvent Valve Box(Repurposed) | 15058484-03 | Feb/21/2023 | Mar/10/2023 | Mar/10/2023 | Mar/10/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af58d797bb1e
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-SVB (relable) | Solvent Valve Box(Repurposed) | 15058484-03 | Jan/27/2023 | Jan/27/2023 | Feb/09/2023 | Feb/09/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af58d797bb1e
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-SVB (relable) | Solvent Valve Box(Repurposed) | 15058484-03 | Feb/21/2023 | Feb/21/2023 | Feb/20/2023 | Feb/20/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af58d797bb1e
Passed | I&C OAT | JE DUNN-ALOHA | 15058484-03-F15-XV269-3B-01A | SOLENOID VALE | 15058484-03 | May/16/2023 | May/16/2023 | May/17/2023 | May/17/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af786897bb23
Passed | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3B-00 | Waste Collection Lift Pumps | 15058484-03 | May/16/2023 | May/16/2023 | May/11/2023 | May/16/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4afdd5497bb25
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3B-00 | Waste Collection Lift Pumps | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4afdd5497bb25
Passed | PROC DV | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3B-00 | Waste Collection Lift Pumps | 15058484-03 | May/09/2023 | May/09/2023 | May/10/2023 | May/10/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4afdd5497bb25
Passed | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3B-00 | Waste Collection Lift Pumps | 15058484-03 | May/16/2023 | May/16/2023 | May/18/2023 | May/18/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4afdd5497bb25
Passed | EQ CC/GT | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3B-00 | Waste Collection Lift Pumps | 15058484-03 | Jun/02/2023 | Jun/02/2023 | Jun/01/2023 | Jun/01/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4afdd5497bb25
Not Started | FAT | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3B-00 | Waste Collection Lift Pumps | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4afdd5497bb25
Not Started | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-M-NIBAR-L.3/14.7-S | Aqueous Valve Box | 15058484-03 | Aug/07/2023 | Aug/07/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af32d597bb18
Not Started | SL1 | JE DUNN-ALOHA | 15058484-03-F15-M-NIBAR-L.3/14.7-S | Aqueous Valve Box | 15058484-03 | Aug/15/2023 | Aug/23/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af32d597bb18
Not Started | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-M-NIBAR-L.3/14.7-S | Aqueous Valve Box | 15058484-03 | Aug/07/2023 | Aug/07/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af32d597bb18
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-M-NIBAR-L.3/14.7-S | Aqueous Valve Box | 15058484-03 | Aug/14/2023 | Aug/14/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af32d597bb18
Not Started | SL2 | JE DUNN-ALOHA | 15058484-03-F15-M-NIBAR-L.3/14.7-S | Aqueous Valve Box | 15058484-03 | Aug/15/2023 | Aug/23/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af32d597bb18
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-M-NIBAR-L.3/14.7-S | Aqueous Valve Box | 15058484-03 | Aug/15/2023 | Aug/23/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4af32d597bb18
Passed | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3A-00 | Waste Collection Lift Pumps | 15058484-03 | May/16/2023 | May/16/2023 | May/18/2023 | May/18/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af4e5897bb24
Not Started | FAT | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3A-00 | Waste Collection Lift Pumps | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af4e5897bb24
Passed | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3A-00 | Waste Collection Lift Pumps | 15058484-03 | May/16/2023 | May/16/2023 | May/11/2023 | May/16/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af4e5897bb24
Passed | PROC DV | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3A-00 | Waste Collection Lift Pumps | 15058484-03 | May/09/2023 | May/09/2023 | May/10/2023 | May/10/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af4e5897bb24
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3A-00 | Waste Collection Lift Pumps | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af4e5897bb24
Passed | EQ CC/GT | JE DUNN-ALOHA | 15058484-03-F15-PMP269-3A-00 | Waste Collection Lift Pumps | 15058484-03 | Jun/02/2023 | Jun/02/2023 | Jun/01/2023 | Jun/01/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4af4e5897bb24
Passed | INST FAT | JE DUNN-ALOHA | 15058484-03-F15-LIT269-3-01A | LEVEL INDICATING TRANSMITTER | 15058484-03 | May/17/2023 | May/17/2023 | May/24/2023 | May/24/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4afc0a197bb03
Passed | I&C OAT | JE DUNN-ALOHA | 15058484-03-F15-LIT269-3-01A | LEVEL INDICATING TRANSMITTER | 15058484-03 | May/10/2023 | May/10/2023 | Apr/13/2023 | May/17/2023 | F15 | F15 WW51 LOR:CDM |  | 269 | WASTE | E-631a3597eab4afc0a197bb03
Not Started | SL2 | JE DUNN-ALOHA | 15058484-03-F15-S-CPE-L/15.4-S | Solvent Valve Box | 15058484-03 | Jun/01/2023 | Jun/20/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afc6b097bb15
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-S-CPE-L/15.4-S | Solvent Valve Box | 15058484-03 | Jun/01/2023 | Jun/20/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afc6b097bb15
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-S-CPE-L/15.4-S | Solvent Valve Box | 15058484-03 | May/23/2023 | May/23/2023 | May/22/2023 | Jun/01/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afc6b097bb15
Not Started | SL1 | JE DUNN-ALOHA | 15058484-03-F15-S-CPE-L/15.4-S | Solvent Valve Box | 15058484-03 | Jun/01/2023 | Jun/20/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afc6b097bb15
Passed | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-S-CPE-L/15.4-S | Solvent Valve Box | 15058484-03 | Apr/27/2023 | Apr/27/2023 | Apr/13/2023 | Apr/13/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afc6b097bb15
Passed | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-S-CPE-L/15.4-S | Solvent Valve Box | 15058484-03 | May/16/2023 | May/16/2023 | Apr/24/2023 | May/16/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afc6b097bb15
Passed | MECH D CC | JE DUNN-ALOHA | 15058484-03-F15-S-CPE-L/15.4-S | Solvent Valve Box | 15058484-03 | May/08/2023 | May/08/2023 | Apr/24/2023 | May/03/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4afc6b097bb15
Not Started | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-T-NIBAR-M.1/17.4-S | Aqueous Valve Box | 15058484-03 | Aug/07/2023 | Aug/07/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4aff9c997bb17
Not Started | I&C CC | JE DUNN-ALOHA | 15058484-03-F15-T-NIBAR-M.1/17.4-S | Aqueous Valve Box | 15058484-03 | Aug/07/2023 | Aug/07/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4aff9c997bb17
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-T-NIBAR-M.1/17.4-S | Aqueous Valve Box | 15058484-03 | Aug/14/2023 | Aug/14/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4aff9c997bb17
Not Started | SL1 | JE DUNN-ALOHA | 15058484-03-F15-T-NIBAR-M.1/17.4-S | Aqueous Valve Box | 15058484-03 | Aug/15/2023 | Aug/23/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4aff9c997bb17
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-T-NIBAR-M.1/17.4-S | Aqueous Valve Box | 15058484-03 | Aug/15/2023 | Aug/23/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4aff9c997bb17
Not Started | SL2 | JE DUNN-ALOHA | 15058484-03-F15-T-NIBAR-M.1/17.4-S | Aqueous Valve Box | 15058484-03 | Aug/15/2023 | Aug/23/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-631a3597eab4aff9c997bb17
Passed | PROC CC | JE DUNN-ALOHA | 15058484-03-F15-212OFA-T.5s | OFA Lateral | 15058484-03 | May/16/2023 | May/16/2023 | May/12/2023 | May/16/2023 | F15 | F15 WW51 LOR:CDM |  | 212 | MECHANICAL PROCESS | E-631a3597eab4af67b197bb1d
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-212OFA-T.5s | OFA Lateral | 15058484-03 | Jun/01/2023 | Jun/20/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 212 | MECHANICAL PROCESS | E-631a3597eab4af67b197bb1d
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-212OFA-T.5s | OFA Lateral | 15058484-03 | May/23/2023 | May/23/2023 | May/22/2023 | May/22/2023 | F15 | F15 WW51 LOR:CDM |  | 212 | MECHANICAL PROCESS | E-631a3597eab4af67b197bb1d
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-04-F15-153FP-Sprinkler and pipe relo | Fire Sprinklers | 15058484-04 | Feb/03/2023 | Feb/03/2023 | Feb/03/2023 | Feb/03/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | FIRE PROTECTION/SSH | E-631f564db7db7490d717f6e3
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058484-04-F15-153FP-Sprinkler and pipe relo | Fire Sprinklers | 15058484-04 | Feb/06/2023 | Mar/06/2023 | Feb/24/2023 | Feb/24/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | FIRE PROTECTION/SSH | E-631f564db7db7490d717f6e3
Passed | PROC CC | JE DUNN-ALOHA | 15058484-04-F15-153FP-Sprinkler and pipe relo | Fire Sprinklers | 15058484-04 | Dec/30/2022 | Dec/30/2022 | Jan/06/2023 | Jan/06/2023 | F15 | F15-CSA-501/502 Bay Upgrade |  | RR | FIRE PROTECTION/SSH | E-631f564db7db7490d717f6e3
Passed | I&C OAT | JE DUNN-ALOHA | 15058567-01-F15-XD-2-15-7 | F15-XD-2-15-7 Solenoid Valve | 15058567-01 | Apr/28/2023 | Apr/28/2023 | Apr/27/2023 | May/01/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a51ef4a26a5
Passed | INST FAT | JE DUNN-ALOHA | 15058567-01-F15-TCV-2-15-7 | F15 RAH-2-15-7 CHW COIL VALVE TCV-2-15-7 | 15058567-01 | Apr/28/2023 | Apr/28/2023 | May/23/2023 | May/23/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5a4c4a26a3
Passed | I&C OAT | JE DUNN-ALOHA | 15058567-01-F15-TCV-2-15-7 | F15 RAH-2-15-7 CHW COIL VALVE TCV-2-15-7 | 15058567-01 | Apr/13/2023 | Apr/13/2023 | Apr/26/2023 | Apr/26/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5a4c4a26a3
Passed | PROC CC | JE DUNN-ALOHA | 15058567-01-F15-TCV-2-15-7 | F15 RAH-2-15-7 CHW COIL VALVE TCV-2-15-7 | 15058567-01 | Apr/24/2023 | Apr/24/2023 | May/01/2023 | May/03/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5a4c4a26a3
Passed | I&C OAT | JE DUNN-ALOHA | 15058567-01-F15-ZS-2-15-(5-8) | SMOKE DAMP ZS-2-15-(5-8) | 15058567-01 | Apr/19/2023 | Apr/19/2023 | Apr/27/2023 | Apr/27/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a42724a26a4
Passed | MECH D CC | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Apr/28/2023 | Apr/28/2023 | May/03/2023 | May/03/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | MECH W CC | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Apr/28/2023 | Apr/28/2023 | May/01/2023 | May/03/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | MECH W DV | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Mar/23/2023 | Mar/23/2023 | Mar/14/2023 | Mar/14/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | ELECT CC | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Apr/13/2023 | Apr/13/2023 | Apr/19/2023 | Apr/19/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | ELECT OAT | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Apr/13/2023 | Apr/13/2023 | Apr/19/2023 | Apr/19/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | MECH D DV | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Mar/23/2023 | Mar/23/2023 | Mar/14/2023 | Mar/14/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | ELECT DV | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Mar/23/2023 | Mar/23/2023 | Feb/15/2023 | Mar/15/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | I&C DV | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Mar/23/2023 | Mar/23/2023 | Mar/14/2023 | Mar/14/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | EHS | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | May/01/2023 | May/01/2023 | Apr/26/2023 | May/03/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | EQ CC/GT | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | May/05/2023 | May/05/2023 | May/04/2023 | May/04/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Not Started | FAT | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | May/05/2023 | Jun/06/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Passed | I&C CC | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | Apr/28/2023 | Apr/28/2023 | Apr/27/2023 | May/01/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-15-7 | RAH Relo | 15058567-01 | May/05/2023 | Jun/06/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63237af83f124a5b394a26a2
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-05-ETAP2F | ETAP | 15048483-02 | Sep/28/2023 | Sep/28/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e2a6ddbe482
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-05-ETAP2F | ETAP | 15048483-02 | Oct/06/2023 | Nov/03/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e2a6ddbe482
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-05-ETAP2F | ETAP | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e2a6ddbe482
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-05-ETAP2F | ETAP | 15048483-02 | Oct/06/2023 | Nov/03/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e2a6ddbe482
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Aug/31/2023 | Aug/31/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Sep/01/2023 | Oct/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Sep/01/2023 | Oct/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Sep/01/2023 | Oct/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-05 | Ultra HDRIO/Step 3 | 15048483-02 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e52b2dbe48d
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/10/2023 | Nov/07/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/16/2023 | Nov/13/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/16/2023 | Nov/13/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/09/2023 | Oct/09/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-PIT65-0-1B | House Vacuum Pressure PIT-65-0-1B | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 222 | MECHANICAL MISC | E-6329da4256dd6e032bdbe490
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/14/2023 | Sep/14/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/08/2023 | Sep/08/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/11/2023 | Oct/09/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/15/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7B | PREHEAT HWR VALVE TCV-28-0-7B | 15048483-02 | Sep/15/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e022adbe4a1
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/08/2023 | Sep/08/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/11/2023 | Oct/09/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/15/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/14/2023 | Sep/14/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-TCV28-0-7A | PREHEAT HWR VALVE TCV-28-7-1 | 15048483-02 | Sep/15/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e6862dbe4a2
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RP650-205-04 | Relay Panel | 15048483-02 | Aug/15/2023 | Aug/15/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e6920dbe4a3
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RP650-205-04 | Relay Panel | 15048483-02 | Aug/23/2023 | Sep/21/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e6920dbe4a3
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RP650-205-04 | Relay Panel | 15048483-02 | Aug/22/2023 | Aug/22/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e6920dbe4a3
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RP650-205-04 | Relay Panel | 15048483-02 | Aug/15/2023 | Aug/15/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e6920dbe4a3
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RP650-205-04 | Relay Panel | 15048483-02 | Aug/23/2023 | Sep/21/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e6920dbe4a3
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RP650-204-04 | Relay Panel | 15048483-02 | Aug/22/2023 | Aug/22/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e5063dbe4a4
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RP650-204-04 | Relay Panel | 15048483-02 | Aug/23/2023 | Sep/21/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e5063dbe4a4
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RP650-204-04 | Relay Panel | 15048483-02 | Aug/23/2023 | Sep/21/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e5063dbe4a4
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RP650-204-04 | Relay Panel | 15048483-02 | Aug/15/2023 | Aug/15/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e5063dbe4a4
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RP650-204-04 | Relay Panel | 15048483-02 | Aug/15/2023 | Aug/15/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e5063dbe4a4
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Oct/24/2023 | Oct/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Nov/01/2023 | Dec/01/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Oct/25/2023 | Oct/25/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Oct/24/2023 | Oct/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Oct/24/2023 | Oct/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Oct/25/2023 | Oct/25/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Oct/24/2023 | Oct/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Nov/01/2023 | Dec/01/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-06 | Ultra HDRIO/Step 16 | 15048483-02 | Nov/01/2023 | Dec/01/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7c32dbe487
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/27/2023 | Oct/25/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/21/2023 | Oct/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/20/2023 | Sep/20/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/27/2023 | Oct/25/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-2-1B | CPCW Return Press F15-PCV202-2-1B | 15048483-02 | Sep/26/2023 | Sep/26/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e72c5dbe491
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/17/2023 | Nov/14/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/23/2023 | Nov/20/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/23/2023 | Nov/20/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-LIT291-1-10B | BSW Lift Tank Level - 0T-18.5 | 15048483-02 | Oct/16/2023 | Oct/16/2023 |  |  | F15 | PLC5-P2 |  | 291 | WASTE | E-6329da4256dd6e635fdbe494
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-LCP-26-3-1-2 | LCP Panel to FCV-26-3-1-2 | 15048483-02 | Sep/26/2023 | Sep/26/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e73f4dbe479
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-LCP-26-3-1-2 | LCP Panel to FCV-26-3-1-2 | 15048483-02 | Sep/27/2023 | Oct/25/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e73f4dbe479
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-LCP-26-3-1-2 | LCP Panel to FCV-26-3-1-2 | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e73f4dbe479
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-LCP-26-3-1-2 | LCP Panel to FCV-26-3-1-2 | 15048483-02 | Sep/27/2023 | Oct/25/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e73f4dbe479
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/08/2023 | Sep/08/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/15/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/11/2023 | Oct/09/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/14/2023 | Sep/14/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/15/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-TET28-0-7B | PREHEAT HWS TEMP TET-28-0-7B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 115 | MECHANICAL WET | E-6329da4256dd6e2d78dbe484
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/13/2023 | Nov/10/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/13/2023 | Nov/10/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/12/2023 | Oct/12/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/13/2023 | Nov/10/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-04 | Ultra HDRIO/Step 14 | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e508fdbe485
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/13/2023 | Nov/10/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/13/2023 | Nov/10/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/12/2023 | Oct/12/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/13/2023 | Nov/10/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-405-03 | Ultra HDRIO/Step 12 | 15048483-02 | Oct/05/2023 | Oct/05/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e4653dbe486
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/09/2023 | Nov/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/03/2023 | Nov/03/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/02/2023 | Nov/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/02/2023 | Nov/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/10/2023 | Dec/12/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/02/2023 | Nov/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/03/2023 | Nov/03/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/02/2023 | Nov/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/10/2023 | Dec/12/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-404-05 | Ultra HDRIO/Step 18 | 15048483-02 | Nov/10/2023 | Dec/12/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e1354dbe488
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/21/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/14/2023 | Aug/14/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/14/2023 | Aug/14/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/21/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-203-04 | Ultra HDRIO/Step 1 | 15048483-02 | Aug/21/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e0f20dbe48a
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-402-05 CRD Install | Digital Output Card | 15048483-02 | Oct/16/2023 | Nov/13/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6ea6eedbe489
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-402-05 CRD Install | Digital Output Card | 15048483-02 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6ea6eedbe489
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-402-05 CRD Install | Digital Output Card | 15048483-02 | Oct/06/2023 | Oct/06/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6ea6eedbe489
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-402-05 CRD Install | Digital Output Card | 15048483-02 | Oct/16/2023 | Nov/13/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6ea6eedbe489
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/08/2023 | Sep/08/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/15/2023 | Sep/15/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/11/2023 | Sep/11/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/11/2023 | Sep/11/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/18/2023 | Oct/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/08/2023 | Sep/08/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/08/2023 | Sep/08/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/18/2023 | Oct/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/18/2023 | Oct/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-04 | Ultra HDRIO/Step 5 | 15048483-02 | Sep/08/2023 | Sep/08/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e7ac0dbe48b
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Oct/05/2023 | Nov/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Sep/27/2023 | Sep/27/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Sep/27/2023 | Sep/27/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Sep/27/2023 | Sep/27/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Oct/05/2023 | Nov/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Sep/27/2023 | Sep/27/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Oct/04/2023 | Oct/04/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Sep/28/2023 | Sep/28/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Oct/05/2023 | Nov/02/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-202-03 | Ultra HDRIO/Step 10 | 15048483-02 | Sep/28/2023 | Sep/28/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6e9d91dbe48c
Not Started | ELECT CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/18/2023 | Sep/18/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | FMS | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/26/2023 | Oct/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/26/2023 | Oct/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/26/2023 | Oct/24/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | ELECT OAT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/18/2023 | Sep/18/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/18/2023 | Sep/18/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/18/2023 | Sep/18/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | ELECT DV | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-RIO650-201-04 | Ultra HDRIO/Step 8 | 15048483-02 | Sep/25/2023 | Sep/25/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-6329da4256dd6eee07dbe48e
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/15/2023 | Aug/15/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/15/2023 | Aug/15/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/23/2023 | Sep/21/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/15/2023 | Aug/15/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/15/2023 | Aug/15/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/22/2023 | Aug/22/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/23/2023 | Sep/21/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-TET25-4-4-1B | Temp | 15048483-02 | Aug/17/2023 | Sep/15/2023 |  |  | F15 | PLC5-P2 |  | 111 | MECHANICAL WET | E-6329da4256dd6ea703dbe48f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/27/2023 | Oct/25/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/26/2023 | Sep/26/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/21/2023 | Oct/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/19/2023 | Sep/19/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/20/2023 | Sep/20/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-PCV202-0-3B | CPCW Return Pressure IW Makeup Valve PCV202-0-3B - 1W-4 | 15048483-02 | Sep/27/2023 | Oct/25/2023 |  |  | F15 | PLC5-P2 |  | 202 | MECHANICAL WET | E-6329da4256dd6e6d98dbe492
Not Started | I&C DV | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/08/2023 | Sep/08/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/11/2023 | Oct/09/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/14/2023 | Sep/14/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Not Started | FAT | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/15/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/15/2023 | Oct/13/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Not Started | PROC CC | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Not Started | I&C CC | JE DUNN-ALOHA | 15048483-02-F15-TET119-0-10B | GLYCOL RETURN TEMP TET-119-0-10B | 15048483-02 | Sep/07/2023 | Sep/07/2023 |  |  | F15 | PLC5-P2 |  | 119 | MECHANICAL WET | E-6329da4256dd6e9fb4dbe49a
Passed | MECH D CC | JE DUNN-ALOHA | 15060021-01-F15-138EXVO-Rsn | EXVO Lateral | 15060021-01 | Jan/05/2023 | Jan/05/2023 | Dec/27/2022 | Dec/27/2022 | F15 | F15 DST502 EXVO Lateral |  | 138 | MECHANICAL EXHAUST | E-632c72a556dd6e1dafdcfc53
Passed | DIST OA/BT | JE DUNN-ALOHA | 15060021-01-F15-138EXVO-Rsn | EXVO Lateral | 15060021-01 | Feb/10/2023 | Feb/20/2023 | Jan/27/2023 | Jan/27/2023 | F15 | F15 DST502 EXVO Lateral |  | 138 | MECHANICAL EXHAUST | E-632c72a556dd6e1dafdcfc53
Passed | DIST CC/GT | JE DUNN-ALOHA | 15060021-01-F15-138EXVO-Rsn | EXVO Lateral | 15060021-01 | Jan/19/2023 | Jan/19/2023 | Jan/06/2023 | Jan/06/2023 | F15 | F15 DST502 EXVO Lateral |  | 138 | MECHANICAL EXHAUST | E-632c72a556dd6e1dafdcfc53
Passed | PROC CC | JE DUNN-ALOHA | 15059929-01-AL4-152DHW-AL4 Interfloor Stocker-Piping J/9 | New piping | 15059929-01 | Dec/27/2022 | Dec/27/2022 | Dec/28/2022 | Dec/28/2022 | AL4 | AL4 Interfloor Stocker |  | 152 | MECHANICAL MISC | E-6331cdebe383c88c44455929
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059929-01-AL4-152DHW-AL4 Interfloor Stocker-Piping J/9 | New piping | 15059929-01 | Jun/07/2023 | Jul/06/2023 | May/24/2023 | May/24/2023 | AL4 | AL4 Interfloor Stocker |  | 152 | MECHANICAL MISC | E-6331cdebe383c88c44455929
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059929-01-AL4-152DHW-AL4 Interfloor Stocker-Piping J/9 | New piping | 15059929-01 | Jun/06/2023 | Jun/06/2023 | Apr/26/2023 | Apr/26/2023 | AL4 | AL4 Interfloor Stocker |  | 152 | MECHANICAL MISC | E-6331cdebe383c88c44455929
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15059929-01-AL4-101MAH-AL4 Interfloor Stocker Tie In | Stocker duct | 15059929-01 | Jun/06/2023 | Jun/06/2023 |  |  | AL4 | AL4 Interfloor Stocker |  | 103 | MECHANICAL DRY | E-6331cdebe383c84b1f455927
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15059929-01-AL4-101MAH-AL4 Interfloor Stocker Tie In | Stocker duct | 15059929-01 | Jun/07/2023 | Jul/06/2023 |  |  | AL4 | AL4 Interfloor Stocker |  | 103 | MECHANICAL DRY | E-6331cdebe383c84b1f455927
In Progress | MECH D CC | JE DUNN-ALOHA | 15059929-01-AL4-101MAH-AL4 Interfloor Stocker Tie In | Stocker duct | 15059929-01 | May/30/2023 | May/30/2023 | Dec/28/2022 |  | AL4 | AL4 Interfloor Stocker |  | 103 | MECHANICAL DRY | E-6331cdebe383c84b1f455927
Passed | MECH D CC | JE DUNN-ALOHA | 15059929-01-AL4-103GMAH-AL4 Interfloor Stocker Duct Relo | Header | 15059929-01 | Dec/27/2022 | Dec/27/2022 | Dec/28/2022 | Dec/28/2022 | AL4 | AL4 Interfloor Stocker |  | 103 | MECHANICAL DRY | E-6331cdebe383c8b074455928
Passed | DIST OA/BT | JE DUNN-ALOHA | 15059929-01-AL4-103GMAH-AL4 Interfloor Stocker Duct Relo | Header | 15059929-01 | Jun/07/2023 | Jul/06/2023 | May/24/2023 | May/24/2023 | AL4 | AL4 Interfloor Stocker |  | 103 | MECHANICAL DRY | E-6331cdebe383c8b074455928
Passed | DIST CC/GT | JE DUNN-ALOHA | 15059929-01-AL4-103GMAH-AL4 Interfloor Stocker Duct Relo | Header | 15059929-01 | Jun/06/2023 | Jun/06/2023 | Apr/28/2023 | Apr/28/2023 | AL4 | AL4 Interfloor Stocker |  | 103 | MECHANICAL DRY | E-6331cdebe383c8b074455928
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/24/2023 | Jun/02/2023 | Feb/23/2023 | May/24/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-6335e6bd293305af1e1af976
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/24/2023 | Jul/06/2023 |  |  | F15 | PLC5 Phase 1 |  | 245 | UPW | E-6335e6bd293305af1e1af976
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/20/2023 | Jan/20/2023 | Jan/24/2023 | Jan/24/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-6335e6bd293305af1e1af976
Passed | I&C OAT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1B | UPW Dist. EOL | 15048483-01 |  |  | Sep/30/2022 | Sep/30/2022 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-6335e6bd293305af1e1af976
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/16/2023 | Jan/16/2023 | Jan/10/2023 | Feb/09/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-6335e6bd293305af1e1af976
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1B | UPW Dist. EOL | 15048483-01 |  |  | Sep/29/2022 | Sep/29/2022 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-6335e6bd293305af1e1af976
Passed | PROC CC | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/13/2023 | Jan/13/2023 | Nov/14/2022 | Jan/20/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-6335e6bd293305af1e1af976
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-PCV55-580-1B | UPW Dist. EOL | 15048483-01 |  |  | Sep/29/2022 | Sep/30/2022 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-6335e6bd293305af1e1af976
Passed | MECH W CC | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-DEMO | Lateral S/R | 15052533-859 860 | Nov/11/2022 | Nov/11/2022 | Nov/15/2022 | Nov/15/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-633efa607d74fbaea3318207
Passed | DIST OA/BT | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-DEMO | Lateral S/R | 15052533-859 860 | Nov/19/2022 | Dec/30/2022 | Dec/29/2022 | Dec/29/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-633efa607d74fbaea3318207
Passed | DIST CC/GT | JE DUNN-ALOHA | 15052533-859 860-AL4-201PCW-DEMO | Lateral S/R | 15052533-859 860 | Nov/18/2022 | Nov/18/2022 | Dec/12/2022 | Dec/13/2022 | AL4 | Phase 4 Bays 859/860 |  | 201 | MECHANICAL WET | E-633efa607d74fbaea3318207
Not Started | EHS | JE DUNN-ALOHA | 15061108-01-F15-RR-CSA-ATS & MCC Housekeeping Pad | ATS & MCC Housekeeping Pad | 15061108-01 | Apr/10/2025 | Apr/10/2025 |  |  | F15 | WW05 LOR: ATS |  | RR | ROOM/AREA/BAY-READY | E-634ed0a68d959e2b120304c0
Not Started | STRUCT DV | JE DUNN-ALOHA | 15061108-01-F15-RR-CSA-ATS & MCC Housekeeping Pad | ATS & MCC Housekeeping Pad | 15061108-01 | Apr/10/2025 | Apr/10/2025 |  |  | F15 | WW05 LOR: ATS |  | RR | ROOM/AREA/BAY-READY | E-634ed0a68d959e2b120304c0
Not Started | FAT | JE DUNN-ALOHA | 15061108-01-F15-RR-CSA-ATS & MCC Housekeeping Pad | ATS & MCC Housekeeping Pad | 15061108-01 | Apr/17/2025 | May/15/2025 |  |  | F15 | WW05 LOR: ATS |  | RR | ROOM/AREA/BAY-READY | E-634ed0a68d959e2b120304c0
Not Started | STRUCT CC | JE DUNN-ALOHA | 15061108-01-F15-RR-CSA-ATS & MCC Housekeeping Pad | ATS & MCC Housekeeping Pad | 15061108-01 | Apr/09/2025 | Apr/09/2025 |  |  | F15 | WW05 LOR: ATS |  | RR | ROOM/AREA/BAY-READY | E-634ed0a68d959e2b120304c0
Not Started | RR CC/GT | JE DUNN-ALOHA | 15061108-01-F15-RR-CSA-ATS & MCC Housekeeping Pad | ATS & MCC Housekeeping Pad | 15061108-01 | Apr/16/2025 | Apr/16/2025 |  |  | F15 | WW05 LOR: ATS |  | RR | ROOM/AREA/BAY-READY | E-634ed0a68d959e2b120304c0
Not Started | RR OA/BT | JE DUNN-ALOHA | 15061108-01-F15-RR-CSA-ATS & MCC Housekeeping Pad | ATS & MCC Housekeeping Pad | 15061108-01 | Apr/17/2025 | May/15/2025 |  |  | F15 | WW05 LOR: ATS |  | RR | ROOM/AREA/BAY-READY | E-634ed0a68d959e2b120304c0
Passed | MECH D CC | JE DUNN-ALOHA | 15058524-01-F15-138EXVO-Duct | New duct | 15058524-01 | Jan/13/2023 | Jan/13/2023 | Jan/17/2023 | Jan/17/2023 | F15 | Polymide |  | 138 | MECHANICAL EXHAUST | E-63599f7677875ad91fd92c7c
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058524-01-F15-138EXVO-Duct | New duct | 15058524-01 | Jan/20/2023 | Jan/20/2023 | Jan/19/2023 | Jan/19/2023 | F15 | Polymide |  | 138 | MECHANICAL EXHAUST | E-63599f7677875ad91fd92c7c
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058524-01-F15-138EXVO-Duct | New duct | 15058524-01 | Feb/03/2023 | Feb/09/2023 | Jan/27/2023 | Jan/27/2023 | F15 | Polymide |  | 138 | MECHANICAL EXHAUST | E-63599f7677875ad91fd92c7c
Passed | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-XV278-1-00A | Polyimide Solvent Waste Collection - Solenoid Valve | 15058524-01 | Jan/05/2023 | Jan/09/2023 | Jan/05/2023 | Jan/05/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a7ed8d92c84
Not Started | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-XV278-1-00A | Polyimide Solvent Waste Collection - Solenoid Valve | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a7ed8d92c84
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058524-01-F15-PLC278-1-00 (DEMO) | Polyimide Solvent Waste Collection- Control Panel (DEMO) | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polyimide |  | 650 | FACILITIES MONITORING SYSTEM | E-63599f7677875a005ad92c87
Not Started | ELECT CC | JE DUNN-ALOHA | 15058524-01-F15-PLC278-1-00 (DEMO) | Polyimide Solvent Waste Collection- Control Panel (DEMO) | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polyimide |  | 650 | FACILITIES MONITORING SYSTEM | E-63599f7677875a005ad92c87
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058524-01-F15-PLC278-1-00 (DEMO) | Polyimide Solvent Waste Collection- Control Panel (DEMO) | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polyimide |  | 650 | FACILITIES MONITORING SYSTEM | E-63599f7677875a005ad92c87
Not Started | FAT | JE DUNN-ALOHA | 15058524-01-F15-PLC278-1-00 (DEMO) | Polyimide Solvent Waste Collection- Control Panel (DEMO) | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polyimide |  | 650 | FACILITIES MONITORING SYSTEM | E-63599f7677875a005ad92c87
Not Started | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-XV278-3-00A | Polyimide Solvent Waste Collection -Solenoid Valve | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a701ad92c8b
Not Started | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-XV278-3-00A | Polyimide Solvent Waste Collection -Solenoid Valve | 15058524-01 | Jan/05/2024 | Feb/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a701ad92c8b
Not Started | PROC DV | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | FAT | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | I&C DV | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | I&C CC | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | EHS | JE DUNN-ALOHA | 15058524-01-F15-TK278-3-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a5614d92c7d
Not Started | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01A | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Jan/19/2023 | Jan/19/2023 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875af80bd92c8d
Passed | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01A | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Jan/04/2023 | Jan/05/2023 | Jan/05/2023 | Jan/05/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875af80bd92c8d
Passed | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01A | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Jan/18/2023 | Jan/18/2023 | Jan/18/2023 | Jan/18/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875af80bd92c8d
Passed | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-278PSW-N.5s (IA) | Lateral | 15058524-01 | Jan/13/2023 | Jan/13/2023 | Jan/17/2023 | Jan/18/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a04ebd92c91
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-N.5s (IA) | Lateral | 15058524-01 | Jan/20/2023 | Jan/20/2023 | Jan/19/2023 | Jan/19/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a04ebd92c91
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-N.5s (IA) | Lateral | 15058524-01 | Jan/26/2023 | Feb/01/2023 | Jan/24/2023 | Jan/24/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a04ebd92c91
Not Started | FAT | JE DUNN-ALOHA | 15058524-01-F15-LSH269-1-10A | LSH RELO | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a095dd92c96
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058524-01-F15-LSH269-1-10A | LSH RELO | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a095dd92c96
Passed | I&C DV | JE DUNN-ALOHA | 15058524-01-F15-LSH269-1-10A | LSH RELO | 15058524-01 | Jan/02/2023 | Jan/02/2023 | Jan/06/2023 | Jan/06/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a095dd92c96
Not Started | I&C CC | JE DUNN-ALOHA | 15058524-01-F15-LSH269-1-10A | LSH RELO | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a095dd92c96
Passed | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-LSH269-1-10A | LSH RELO | 15058524-01 | Feb/06/2023 | Feb/06/2023 | Jan/03/2023 | Jan/03/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a095dd92c96
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058524-01-F15-LSH269-1-10A | LSH RELO | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a095dd92c96
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Not Started | I&C CC | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Passed | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jul/05/2023 | Jul/05/2023 | Jan/13/2023 | Jan/13/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Not Started | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Passed | I&C DV | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Feb/07/2023 | Feb/07/2023 | Jan/06/2023 | Jan/06/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Not Started | EHS | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Passed | EER | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jul/12/2023 | Jul/12/2023 | Jan/04/2023 | Jan/13/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Not Started | FAT | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
In Progress | PROC DV | JE DUNN-ALOHA | 15058524-01-F15-TK278-2-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/05/2024 | Jan/05/2024 | Jan/09/2023 |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a6933d92c97
Passed | EER | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jul/12/2023 | Jul/12/2023 | Jan/04/2023 | Jan/13/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | I&C CC | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | FAT | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
In Progress | PROC DV | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/05/2024 | Jan/05/2024 | Jan/09/2023 |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Passed | I&C DV | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Feb/07/2023 | Feb/07/2023 | Jan/06/2023 | Jan/06/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | EHS | JE DUNN-ALOHA | 15058524-01-F15-TK278-1-00 | Polyimide Solvent Waste Collection Tote | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a15bdd92c7e
Not Started | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-WIT278-2-00A | Polyimide Solvent Waste Collection Tote weight Transmitter | 15058524-01 | Dec/29/2023 | Dec/29/2023 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a316dd92c80
Not Started | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-WIT278-2-00A | Polyimide Solvent Waste Collection Tote weight Transmitter | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a316dd92c80
Not Started | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-WIT278-3-00A | Polyimide Solvent Waste Collection Tote weight Transmitter | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a0cd7d92c81
Not Started | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-WIT278-3-00A | Polyimide Solvent Waste Collection Tote weight Transmitter | 15058524-01 | Dec/29/2023 | Dec/29/2023 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a0cd7d92c81
Not Started | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-LIT278-3-00A | Polyimide Solvent Waste Collection Tote Level Transmitter | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a7df8d92c89
In Progress | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-LIT278-3-00A | Polyimide Solvent Waste Collection Tote Level Transmitter | 15058524-01 | Dec/29/2023 | Dec/29/2023 | Jan/04/2023 |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a7df8d92c89
Not Started | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01B | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Jan/19/2023 | Jan/19/2023 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875ab2f6d92c8e
Passed | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01B | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Jan/18/2023 | Jan/18/2023 | Jan/18/2023 | Jan/18/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875ab2f6d92c8e
Passed | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01B | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Jan/04/2023 | Jan/05/2023 | Jan/05/2023 | Jan/05/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875ab2f6d92c8e
Not Started | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01C | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a4fc1d92c8f
Passed | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01C | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Dec/26/2022 | Dec/27/2022 | Jan/05/2023 | Jan/05/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a4fc1d92c8f
Passed | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-LSH278-1-01C | Polyimide Solvent Waste Collection - Level Switch | 15058524-01 | Jan/09/2023 | Jan/09/2023 | Jan/18/2023 | Jan/18/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a4fc1d92c8f
Not Started | ARCH DV | JE DUNN-ALOHA | 15058524-01-F15-RR-CSA-Polymide Tote Coral | Tote Coral and CRC | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | RR | ROOM/AREA/BAY-READY | E-63599f7677875a817cd92c90
Not Started | FAT | JE DUNN-ALOHA | 15058524-01-F15-RR-CSA-Polymide Tote Coral | Tote Coral and CRC | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | RR | ROOM/AREA/BAY-READY | E-63599f7677875a817cd92c90
Passed | ARCH CC | JE DUNN-ALOHA | 15058524-01-F15-RR-CSA-Polymide Tote Coral | Tote Coral and CRC | 15058524-01 | Jan/13/2023 | Jan/13/2023 | Jan/18/2023 | Jan/18/2023 | F15 | Polymide |  | RR | ROOM/AREA/BAY-READY | E-63599f7677875a817cd92c90
Passed | ELECT CC | JE DUNN-ALOHA | 15058524-01-F15-RR-CSA-Polymide Tote Coral | Tote Coral and CRC | 15058524-01 | Jan/18/2023 | Jan/18/2023 | Jan/23/2023 | Jan/23/2023 | F15 | Polymide |  | RR | ROOM/AREA/BAY-READY | E-63599f7677875a817cd92c90
Not Started | RR OA/BT | JE DUNN-ALOHA | 15058524-01-F15-RR-CSA-Polymide Tote Coral | Tote Coral and CRC | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | RR | ROOM/AREA/BAY-READY | E-63599f7677875a817cd92c90
Not Started | RR CC/GT | JE DUNN-ALOHA | 15058524-01-F15-RR-CSA-Polymide Tote Coral | Tote Coral and CRC | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | RR | ROOM/AREA/BAY-READY | E-63599f7677875a817cd92c90
Passed | ELECT DV | JE DUNN-ALOHA | 15058524-01-F15-RR-CSA-Polymide Tote Coral | Tote Coral and CRC | 15058524-01 | Jan/16/2023 | Jan/16/2023 | Jan/19/2023 | Jan/19/2023 | F15 | Polymide |  | RR | ROOM/AREA/BAY-READY | E-63599f7677875a817cd92c90
Not Started | EHS | JE DUNN-ALOHA | 15058524-01-F15-RR-CSA-Polymide Tote Coral | Tote Coral and CRC | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | RR | ROOM/AREA/BAY-READY | E-63599f7677875a817cd92c90
Not Started | ELECT CC | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 2 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a9b91d92c93
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 2 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a9b91d92c93
Not Started | ELECT OAT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 2 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a9b91d92c93
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 2 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a9b91d92c93
Not Started | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-WIT278-1-00A | Polyimide Solvent Waste Collection Tote weight Transmitter | 15058524-01 | Dec/29/2023 | Dec/29/2023 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875acfb8d92c7f
Not Started | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-WIT278-1-00A | Polyimide Solvent Waste Collection Tote weight Transmitter | 15058524-01 | Jan/05/2024 | Jan/05/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875acfb8d92c7f
Passed | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-LIT278-1-00A | Polyimide Solvent Waste Collection Tote Level Transmitter | 15058524-01 | Feb/13/2023 | Feb/13/2023 | Jan/03/2023 | Jan/03/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a38ccd92c82
Passed | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-LIT278-1-00A | Polyimide Solvent Waste Collection Tote Level Transmitter | 15058524-01 | Feb/06/2023 | Feb/06/2023 | Jan/03/2023 | Jan/03/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a38ccd92c82
Passed | INST FAT | JE DUNN-ALOHA | 15058524-01-F15-LIT278-2-00A | Polyimide Solvent Waste Collection Tote Level Transmitter | 15058524-01 | Feb/13/2023 | Feb/13/2023 | Jan/03/2023 | Jan/03/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a2d0dd92c85
Passed | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-LIT278-2-00A | Polyimide Solvent Waste Collection Tote Level Transmitter | 15058524-01 | Feb/06/2023 | Feb/06/2023 | Jan/03/2023 | Jan/03/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a2d0dd92c85
Not Started | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-XV278-2-00A | Polyimide Solvent Waste Collection -Solenoid Valve | 15058524-01 | Feb/09/2023 | Feb/09/2023 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a68f5d92c88
Passed | I&C OAT | JE DUNN-ALOHA | 15058524-01-F15-XV278-2-00A | Polyimide Solvent Waste Collection -Solenoid Valve | 15058524-01 | Jan/05/2023 | Jan/05/2023 | Jan/05/2023 | Jan/05/2023 | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a68f5d92c88
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 1 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a0a8bd92c92
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 1 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a0a8bd92c92
Not Started | ELECT CC | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 1 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a0a8bd92c92
Not Started | ELECT CC | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 3 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a1e14d92c94
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 3 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a1e14d92c94
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Scale 3 | PSW - U-shaped Tote Scale | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63599f7677875a1e14d92c94
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-2-10 | RAH102-2-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e23e9ef737c
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-2-10 | RAH102-2-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e23e9ef737c
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-2-10 | RAH102-2-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e23e9ef737c
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-2-10 | RAH102-2-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e23e9ef737c
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-VFD102-2-10 | RAH102-2-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e23e9ef737c
Not Started | MECH W DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | ELECT DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | LSS DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | I&C CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | MECH D DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | MECH D CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | MECH W CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | LSS CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | LSS OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | I&C DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | EHS | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-1-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e27fcef7379
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-7-10 | RAH102-7-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e63f7ef737e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-7-10 | RAH102-7-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e63f7ef737e
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-VFD102-7-10 | RAH102-7-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e63f7ef737e
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-7-10 | RAH102-7-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e63f7ef737e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-7-10 | RAH102-7-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e63f7ef737e
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-153-FP-F15 Ballroom 508 Conversion_Sprinkler Re-rout | Sprinkler Rerout | 15060600-01 | Nov/22/2023 | Dec/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | FIRE PROTECTION/SSH | E-63642edba7f77e6ed2ef7382
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-153-FP-F15 Ballroom 508 Conversion_Sprinkler Re-rout | Sprinkler Rerout | 15060600-01 | Nov/22/2023 | Dec/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | FIRE PROTECTION/SSH | E-63642edba7f77e6ed2ef7382
Passed | MECH W CC | JE DUNN-ALOHA | 15060600-01-F15-153-FP-F15 Ballroom 508 Conversion_Sprinkler Re-rout | Sprinkler Rerout | 15060600-01 | Aug/15/2023 | Aug/15/2023 | Jan/06/2023 | Jan/06/2023 | F15 | F15 Ballroom 508 Conversion |  | RR | FIRE PROTECTION/SSH | E-63642edba7f77e6ed2ef7382
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-153-FP-F15 Ballroom 508 Conversion_Sprinkler Re-rout | Sprinkler Rerout | 15060600-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | FIRE PROTECTION/SSH | E-63642edba7f77e6ed2ef7382
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-221PV-DMW-02-01s | Lateral | 15060600-01 | Aug/04/2023 | Aug/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 221 | MECHANICAL WET | E-63642edba7f77e442cef7387
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-221PV-DMW-02-01s | Lateral | 15060600-01 | Jul/27/2023 | Jul/27/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 221 | MECHANICAL WET | E-63642edba7f77e442cef7387
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-221PV-DMW-02-01s | Lateral | 15060600-01 | Aug/03/2023 | Aug/03/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 221 | MECHANICAL WET | E-63642edba7f77e442cef7387
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-245UPWS-DI-NorthWn-14 | Lateral | 15060600-01 | Jun/30/2023 | Jul/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 245 | UPW | E-63642edba7f77e574eef738b
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-245UPWS-DI-NorthWn-14 | Lateral | 15060600-01 | Jun/29/2023 | Jun/29/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 245 | UPW | E-63642edba7f77e574eef738b
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-245UPWS-DI-NorthWn-14 | Lateral | 15060600-01 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 245 | UPW | E-63642edba7f77e574eef738b
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-231IW-11.8e | Lateral | 15060600-01 | Jul/13/2023 | Jul/13/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 231 | UPW | E-63642edba7f77e1327ef7388
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-231IW-11.8e | Lateral | 15060600-01 | Jul/20/2023 | Jul/20/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 231 | UPW | E-63642edba7f77e1327ef7388
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-231IW-11.8e | Lateral | 15060600-01 | Jul/21/2023 | Jul/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 231 | UPW | E-63642edba7f77e1327ef7388
Not Started | STRUCT CC | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Catwalk | New Catwalk | 15060600-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77e1ebbef7393
Not Started | ARCH DV | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Catwalk | New Catwalk | 15060600-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77e1ebbef7393
Not Started | RR OA/BT | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Catwalk | New Catwalk | 15060600-01 | Nov/22/2023 | Dec/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77e1ebbef7393
Not Started | ARCH CC | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Catwalk | New Catwalk | 15060600-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77e1ebbef7393
Not Started | EHS | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Catwalk | New Catwalk | 15060600-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77e1ebbef7393
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Catwalk | New Catwalk | 15060600-01 | Nov/22/2023 | Dec/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77e1ebbef7393
Not Started | RR CC/GT | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Catwalk | New Catwalk | 15060600-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77e1ebbef7393
Not Started | STRUCT DV | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Catwalk | New Catwalk | 15060600-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77e1ebbef7393
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | I&C DV | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/14/2023 | Aug/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | I&C CC | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/21/2023 | Sep/19/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/21/2023 | Sep/19/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | ELECT DV | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/14/2023 | Aug/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | FMS | JE DUNN-ALOHA | 15060600-01-F15-PLC650-306-00 | DATA CONCENTRATOR TRAIN PLC | 15060600-01 | Aug/21/2023 | Sep/19/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 650 | FACILITIES MONITORING SYSTEM | E-63642edba7f77ed011ef7391
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-8-10 | RAH102-8-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e62d6ef737f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-8-10 | RAH102-8-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e62d6ef737f
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-VFD102-8-10 | RAH102-8-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e62d6ef737f
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-8-10 | RAH102-8-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e62d6ef737f
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-8-10 | RAH102-8-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e62d6ef737f
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-5-10 | RAH102-5-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e69f9ef737d
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-5-10 | RAH102-5-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e69f9ef737d
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-5-10 | RAH102-5-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e69f9ef737d
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-VFD102-5-10 | RAH102-5-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e69f9ef737d
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-5-10 | RAH102-5-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e69f9ef737d
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-245UPWR-DI-NorthWn-14 | Lateral | 15060600-01 | Jun/29/2023 | Jun/29/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 245 | UPW | E-63642edba7f77e652fef738a
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-245UPWR-DI-NorthWn-14 | Lateral | 15060600-01 | Jun/30/2023 | Jul/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 245 | UPW | E-63642edba7f77e652fef738a
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-245UPWR-DI-NorthWn-14 | Lateral | 15060600-01 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 245 | UPW | E-63642edba7f77e652fef738a
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-212OFA-10.9e | sublateral | 15060600-01 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 212 | MECHANICAL PROCESS | E-63642edba7f77ede5eef7385
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-212OFA-10.9e | sublateral | 15060600-01 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 212 | MECHANICAL PROCESS | E-63642edba7f77ede5eef7385
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-212OFA-10.9e | sublateral | 15060600-01 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 212 | MECHANICAL PROCESS | E-63642edba7f77ede5eef7385
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-261AWN-V.5n | Lateral | 15060600-01 | Jun/09/2023 | Jun/09/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77efe93ef738e
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-261AWN-V.5n | Lateral | 15060600-01 | Jun/19/2023 | Jun/27/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77efe93ef738e
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-261AWN-V.5n | Lateral | 15060600-01 | Jun/16/2023 | Jun/16/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77efe93ef738e
Not Started | MECH W DV | JE DUNN-ALOHA | 15060600-01-F15-708SSH-Relo | Relocate Safety Shower | 15060600-01 | Jun/23/2023 | Jun/23/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 708 | LIFE SAFETY SYSTEM | E-63642edba7f77edf6bef7392
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-708SSH-Relo | Relocate Safety Shower | 15060600-01 | Jun/29/2023 | Jun/29/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 708 | LIFE SAFETY SYSTEM | E-63642edba7f77edf6bef7392
Not Started | LSS CC | JE DUNN-ALOHA | 15060600-01-F15-708SSH-Relo | Relocate Safety Shower | 15060600-01 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 708 | LIFE SAFETY SYSTEM | E-63642edba7f77edf6bef7392
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-708SSH-Relo | Relocate Safety Shower | 15060600-01 | Jun/30/2023 | Jul/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 708 | LIFE SAFETY SYSTEM | E-63642edba7f77edf6bef7392
Not Started | LSS DV | JE DUNN-ALOHA | 15060600-01-F15-708SSH-Relo | Relocate Safety Shower | 15060600-01 | Jun/23/2023 | Jun/23/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 708 | LIFE SAFETY SYSTEM | E-63642edba7f77edf6bef7392
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-708SSH-Relo | Relocate Safety Shower | 15060600-01 | Jun/30/2023 | Jul/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 708 | LIFE SAFETY SYSTEM | E-63642edba7f77edf6bef7392
Not Started | MECH W CC | JE DUNN-ALOHA | 15060600-01-F15-708SSH-Relo | Relocate Safety Shower | 15060600-01 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 708 | LIFE SAFETY SYSTEM | E-63642edba7f77edf6bef7392
Not Started | I&C OAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-7-01A | RAH102-7-10 DISCHARGE TEMPERATURE | 15060600-01 | Oct/25/2023 | Oct/25/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0276ef739f
Not Started | INST FAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-7-01A | RAH102-7-10 DISCHARGE TEMPERATURE | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0276ef739f
Not Started | I&C OAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-2-01A | RAH102-2-10 DISCHARGE TEMPERATURE | 15060600-01 | Oct/25/2023 | Oct/25/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77ee570ef739d
Not Started | INST FAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-2-01A | RAH102-2-10 DISCHARGE TEMPERATURE | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77ee570ef739d
Not Started | EHS | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | LSS OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | MECH W DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | MECH W CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | MECH D CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | LSS CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | LSS DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | I&C DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | ELECT DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | I&C CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | MECH D DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-7-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e4694ef739a
Not Started | I&C OAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-5-01A | RAH102-5-10 DISCHARGE TEMPERATURE | 15060600-01 | Oct/25/2023 | Oct/25/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e42d8ef739e
Not Started | INST FAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-5-01A | RAH102-5-10 DISCHARGE TEMPERATURE | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e42d8ef739e
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-133EXSC-New Duct | New duct | 15060600-01 | Jun/16/2023 | Jun/16/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 133 | MECHANICAL EXHAUST | E-63642edba7f77e2fc3ef7381
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-133EXSC-New Duct | New duct | 15060600-01 | Jun/19/2023 | Jun/27/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 133 | MECHANICAL EXHAUST | E-63642edba7f77e2fc3ef7381
Not Started | MECH D CC | JE DUNN-ALOHA | 15060600-01-F15-133EXSC-New Duct | New duct | 15060600-01 | Jun/09/2023 | Jun/09/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 133 | MECHANICAL EXHAUST | E-63642edba7f77e2fc3ef7381
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-201PCW(S/R)-V.5n-02w | Supply and return laterals | 15060600-01 | Jul/12/2023 | Jul/20/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 201 | MECHANICAL WET | E-63642edba7f77e526bef7383
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-201PCW(S/R)-V.5n-02w | Supply and return laterals | 15060600-01 | Jul/04/2023 | Jul/04/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 201 | MECHANICAL WET | E-63642edba7f77e526bef7383
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-201PCW(S/R)-V.5n-02w | Supply and return laterals | 15060600-01 | Jul/11/2023 | Jul/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 201 | MECHANICAL WET | E-63642edba7f77e526bef7383
Not Started | EHS | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | MECH D CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | LSS DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | ELECT DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | MECH D DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | MECH W DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | LSS OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | LSS CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | MECH W CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | I&C DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | I&C CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-2-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e0da7ef7384
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-212OFA-11.9w | Lateral | 15060600-01 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 212 | MECHANICAL PROCESS | E-63642edba7f77e731cef7386
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-212OFA-11.9w | Lateral | 15060600-01 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 212 | MECHANICAL PROCESS | E-63642edba7f77e731cef7386
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-212OFA-11.9w | Lateral | 15060600-01 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 212 | MECHANICAL PROCESS | E-63642edba7f77e731cef7386
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-261AWN-12w-Vn | sublateral | 15060600-01 | Jun/16/2023 | Jun/16/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77eed12ef738c
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-261AWN-12w-Vn | sublateral | 15060600-01 | Jun/19/2023 | Jun/27/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77eed12ef738c
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-261AWN-12w-Vn | sublateral | 15060600-01 | Jun/09/2023 | Jun/09/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77eed12ef738c
Not Started | ARCH DV | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | TELE CC | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | STRUCT DV | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | ARCH CC | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | ELECT DV | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | TELE DV | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | EHS | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | RR CC/GT | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/22/2023 | Dec/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | RR OA/BT | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/22/2023 | Dec/22/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | STRUCT CC | JE DUNN-ALOHA | 15060600-01-F15-CSA-Ballroom 508 Room Ready | Ballroom 508 Modifications | 15060600-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | RR | ROOM/AREA/BAY-READY | E-63642edba7f77ed355ef7394
Not Started | ELECT DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | LSS OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | LSS DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | MECH W DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | I&C DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | MECH W CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | MECH D CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | I&C CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | MECH D DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | LSS CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-8-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e11fcef739b
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-132EXGF-14" | EXGF Lateral | 15060600-01 | Jun/12/2023 | Jun/12/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 132 | MECHANICAL EXHAUST | E-63642edba7f77e2729ef7380
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-132EXGF-14" | EXGF Lateral | 15060600-01 | Jun/13/2023 | Jun/21/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 132 | MECHANICAL EXHAUST | E-63642edba7f77e2729ef7380
In Progress | MECH D CC | JE DUNN-ALOHA | 15060600-01-F15-132EXGF-14" | EXGF Lateral | 15060600-01 | Jun/05/2023 | Jun/05/2023 | Apr/17/2023 |  | F15 | F15 Ballroom 508 Conversion |  | 132 | MECHANICAL EXHAUST | E-63642edba7f77e2729ef7380
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-1-10 | RAH102-1-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e6026ef737b
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-VFD102-1-10 | RAH102-1-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e6026ef737b
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-1-10 | RAH102-1-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e6026ef737b
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-1-10 | RAH102-1-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e6026ef737b
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-VFD102-1-10 | RAH102-1-10 FAN VARIABLE FREQUENCY DRIVE AND LOCAL CONTROL | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e6026ef737b
Not Started | I&C OAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-8-01A | RAH102-8-10 DISCHARGE TEMPERATURE | 15060600-01 | Oct/25/2023 | Oct/25/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e5266ef737a
Not Started | INST FAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-8-01A | RAH102-8-10 DISCHARGE TEMPERATURE | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e5266ef737a
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-261AWN-V.2n | Lateral | 15060600-01 | Jun/16/2023 | Jun/16/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77e4d72ef738d
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-261AWN-V.2n | Lateral | 15060600-01 | Jun/09/2023 | Jun/09/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77e4d72ef738d
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-261AWN-V.2n | Lateral | 15060600-01 | Jun/19/2023 | Jun/27/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 261 | WASTE | E-63642edba7f77e4d72ef738d
Not Started | PROC CC | JE DUNN-ALOHA | 15060600-01-F15-231IW-11e | Lateral | 15060600-01 | Jul/13/2023 | Jul/13/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 231 | UPW | E-63642edba7f77e2a43ef7389
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060600-01-F15-231IW-11e | Lateral | 15060600-01 | Jul/21/2023 | Jul/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 231 | UPW | E-63642edba7f77e2a43ef7389
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060600-01-F15-231IW-11e | Lateral | 15060600-01 | Jul/20/2023 | Jul/20/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 231 | UPW | E-63642edba7f77e2a43ef7389
Not Started | MECH W CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | MECH W DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/08/2023 | Dec/08/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | LSS DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | MECH D CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | I&C DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | MECH D DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | ELECT DV | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | EHS | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | LSS CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Nov/07/2023 | Nov/07/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | LSS OAT | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | I&C CC | JE DUNN-ALOHA | 15060600-01-F15-RAH102-5-10 | Existing RAH Upgrades | 15060600-01 | Oct/31/2023 | Oct/31/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77e72bfef738f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15060600-01-F15-STX306-1-01 | STRATIX SWITCH PANEL | 15060600-01 | Aug/21/2023 | Sep/19/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 603 | ELECTRICAL | E-63642edba7f77e393eef7390
Not Started | ELECT CC | JE DUNN-ALOHA | 15060600-01-F15-STX306-1-01 | STRATIX SWITCH PANEL | 15060600-01 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 603 | ELECTRICAL | E-63642edba7f77e393eef7390
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15060600-01-F15-STX306-1-01 | STRATIX SWITCH PANEL | 15060600-01 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 603 | ELECTRICAL | E-63642edba7f77e393eef7390
Not Started | ELECT OAT | JE DUNN-ALOHA | 15060600-01-F15-STX306-1-01 | STRATIX SWITCH PANEL | 15060600-01 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 603 | ELECTRICAL | E-63642edba7f77e393eef7390
Not Started | FAT | JE DUNN-ALOHA | 15060600-01-F15-STX306-1-01 | STRATIX SWITCH PANEL | 15060600-01 | Aug/21/2023 | Sep/19/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 603 | ELECTRICAL | E-63642edba7f77e393eef7390
Not Started | ELECT DV | JE DUNN-ALOHA | 15060600-01-F15-STX306-1-01 | STRATIX SWITCH PANEL | 15060600-01 | Aug/14/2023 | Aug/14/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 603 | ELECTRICAL | E-63642edba7f77e393eef7390
Not Started | I&C OAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-1-01A | RAH102-1-10 DISCHARGE TEMPERATURE | 15060600-01 | Oct/25/2023 | Oct/25/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77ec2eeef739c
Not Started | INST FAT | JE DUNN-ALOHA | 15060600-01-F15-TET102-1-01A | RAH102-1-10 DISCHARGE TEMPERATURE | 15060600-01 | Nov/01/2023 | Nov/01/2023 |  |  | F15 | F15 Ballroom 508 Conversion |  | 102 | MECHANICAL DRY | E-63642edba7f77ec2eeef739c
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-L.5s | Recommission Lateral | 15058524-01 | Jan/21/2023 | Jan/30/2023 | Jan/24/2023 | Jan/24/2023 | F15 | Polymide |  | 278 | WASTE | E-63975baa72d632f489cd2f54
Passed | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-278PSW-L.5s | Recommission Lateral | 15058524-01 | Jan/13/2023 | Jan/13/2023 | Jan/18/2023 | Jan/18/2023 | F15 | Polymide |  | 278 | WASTE | E-63975baa72d632f489cd2f54
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-L.5s | Recommission Lateral | 15058524-01 | Jan/20/2023 | Jan/20/2023 | Jan/19/2023 | Jan/19/2023 | F15 | Polymide |  | 278 | WASTE | E-63975baa72d632f489cd2f54
Passed | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-278PSW-U.5s | Recommission Lateral | 15058524-01 | Jan/13/2023 | Jan/13/2023 | Jan/18/2023 | Jan/18/2023 | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326b16cd2f59
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-U.5s | Recommission Lateral | 15058524-01 | Jan/20/2023 | Jan/20/2023 | Jan/19/2023 | Jan/19/2023 | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326b16cd2f59
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-U.5s | Recommission Lateral | 15058524-01 | Jan/26/2023 | Feb/01/2023 | Jan/24/2023 | Jan/24/2023 | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326b16cd2f59
Passed | STRUCT DV | JE DUNN-ALOHA | 15060332A-F15-RR-Munters Pad CSA | Munters Pad | 15060332A | Apr/21/2023 | Apr/21/2023 | Apr/26/2023 | Apr/26/2023 | F15 | F15-Munters 4 |  | RR | ROOM/AREA/BAY-READY | E-639744db359e60123612f6dc
Not Started | RR OA/BT | JE DUNN-ALOHA | 15060332A-F15-RR-Munters Pad CSA | Munters Pad | 15060332A | Apr/28/2023 | Jun/05/2023 |  |  | F15 | F15-Munters 4 |  | RR | ROOM/AREA/BAY-READY | E-639744db359e60123612f6dc
Passed | ARCH CC | JE DUNN-ALOHA | 15060332A-F15-RR-Munters Pad CSA | Munters Pad | 15060332A | Apr/20/2023 | Apr/20/2023 | Apr/25/2023 | Apr/25/2023 | F15 | F15-Munters 4 |  | RR | ROOM/AREA/BAY-READY | E-639744db359e60123612f6dc
Passed | RR CC/GT | JE DUNN-ALOHA | 15060332A-F15-RR-Munters Pad CSA | Munters Pad | 15060332A | Apr/27/2023 | Apr/27/2023 | Apr/26/2023 | Apr/26/2023 | F15 | F15-Munters 4 |  | RR | ROOM/AREA/BAY-READY | E-639744db359e60123612f6dc
Not Started | FAT | JE DUNN-ALOHA | 15060332A-F15-RR-Munters Pad CSA | Munters Pad | 15060332A | Apr/28/2023 | Jun/05/2023 |  |  | F15 | F15-Munters 4 |  | RR | ROOM/AREA/BAY-READY | E-639744db359e60123612f6dc
Passed | STRUCT CC | JE DUNN-ALOHA | 15060332A-F15-RR-Munters Pad CSA | Munters Pad | 15060332A | Apr/20/2023 | Apr/20/2023 | Apr/24/2023 | Apr/24/2023 | F15 | F15-Munters 4 |  | RR | ROOM/AREA/BAY-READY | E-639744db359e60123612f6dc
Passed | ARCH DV | JE DUNN-ALOHA | 15060332A-F15-RR-Munters Pad CSA | Munters Pad | 15060332A | Apr/21/2023 | Apr/21/2023 | Apr/26/2023 | Apr/26/2023 | F15 | F15-Munters 4 |  | RR | ROOM/AREA/BAY-READY | E-639744db359e60123612f6dc
Passed | PROC CC | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Main | Recommission Main | 15058524-01 | Jan/13/2023 | Jan/13/2023 | Jan/17/2023 | Jan/18/2023 | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326a69cd2f5b
Passed | I&C DV | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Main | Recommission Main | 15058524-01 | Jan/02/2023 | Jan/02/2023 | Jan/06/2023 | Jan/06/2023 | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326a69cd2f5b
Not Started | I&C CC | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Main | Recommission Main | 15058524-01 | Jan/04/2024 | Jan/04/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326a69cd2f5b
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Main | Recommission Main | 15058524-01 | Jan/12/2024 | Feb/12/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326a69cd2f5b
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Main | Recommission Main | 15058524-01 | Jan/11/2024 | Jan/11/2024 |  |  | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326a69cd2f5b
In Progress | PROC DV | JE DUNN-ALOHA | 15058524-01-F15-278PSW-Main | Recommission Main | 15058524-01 | Jan/05/2024 | Jan/05/2024 | Jan/09/2023 |  | F15 | Polymide |  | 278 | WASTE | E-63975baa72d6326a69cd2f5b
Not Started | RR OA/BT | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker New Beam | New Support Beam | 15059929-01 | Jun/07/2023 | Jul/06/2023 |  |  | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6399f1ff2b21e559e137865f
Passed | STRUCT CC | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker New Beam | New Support Beam | 15059929-01 | Jan/02/2023 | Jan/02/2023 | Jan/04/2023 | Jan/04/2023 | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6399f1ff2b21e559e137865f
Passed | RR CC/GT | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker New Beam | New Support Beam | 15059929-01 | Jun/06/2023 | Jun/06/2023 | Apr/26/2023 | Apr/26/2023 | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6399f1ff2b21e559e137865f
Passed | STRUCT DV | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker New Beam | New Support Beam | 15059929-01 | Jan/03/2023 | Jan/03/2023 | Jan/03/2023 | Jan/03/2023 | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6399f1ff2b21e559e137865f
Passed | EHS | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker New Beam | New Support Beam | 15059929-01 | Jan/03/2023 | Jan/03/2023 | Jan/04/2023 | Jan/04/2023 | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6399f1ff2b21e559e137865f
Not Started | FAT | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker New Beam | New Support Beam | 15059929-01 | Jun/07/2023 | Jul/06/2023 |  |  | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6399f1ff2b21e559e137865f
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060021-02-F15-133EXSC-Rsn Tubing | Lateral | 15060021-02 | Jun/02/2023 | Jun/02/2023 |  |  | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 133 | MECHANICAL EXHAUST | E-639a057e2b21e5decc3797d0
Not Started | FAT | JE DUNN-ALOHA | 15060021-02-F15-133EXSC-Rsn Tubing | Lateral | 15060021-02 | Jun/05/2023 | Jul/03/2023 |  |  | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 133 | MECHANICAL EXHAUST | E-639a057e2b21e5decc3797d0
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060021-02-F15-133EXSC-Rsn Tubing | Lateral | 15060021-02 | Jun/05/2023 | Jul/03/2023 |  |  | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 133 | MECHANICAL EXHAUST | E-639a057e2b21e5decc3797d0
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15060021-02-F15-133EXSC-Rsn Tubing | Lateral | 15060021-02 | May/19/2023 | May/19/2023 | May/24/2023 | May/24/2023 | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 133 | MECHANICAL EXHAUST | E-639a057e2b21e5decc3797d0
In Progress | I&C CC | JE DUNN-ALOHA | 15060021-02-F15-133EXSC-Rsn Tubing | Lateral | 15060021-02 | May/26/2023 | May/26/2023 | Jun/01/2023 |  | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 133 | MECHANICAL EXHAUST | E-639a057e2b21e5decc3797d0
Not Started | FAT | JE DUNN-ALOHA | 15060021-02-F15-138EXVO-Rsn Tubing | Lateral | 15060021-02 | Jun/05/2023 | Jul/03/2023 |  |  | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 138 | MECHANICAL EXHAUST | E-639a057e2b21e544533797d1
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15060021-02-F15-138EXVO-Rsn Tubing | Lateral | 15060021-02 | Jun/02/2023 | Jun/02/2023 |  |  | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 138 | MECHANICAL EXHAUST | E-639a057e2b21e544533797d1
In Progress | I&C CC | JE DUNN-ALOHA | 15060021-02-F15-138EXVO-Rsn Tubing | Lateral | 15060021-02 | May/26/2023 | May/26/2023 | Jun/01/2023 |  | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 138 | MECHANICAL EXHAUST | E-639a057e2b21e544533797d1
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15060021-02-F15-138EXVO-Rsn Tubing | Lateral | 15060021-02 | Jun/05/2023 | Jul/03/2023 |  |  | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 138 | MECHANICAL EXHAUST | E-639a057e2b21e544533797d1
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15060021-02-F15-138EXVO-Rsn Tubing | Lateral | 15060021-02 | May/19/2023 | May/19/2023 | May/24/2023 | May/24/2023 | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 138 | MECHANICAL EXHAUST | E-639a057e2b21e544533797d1
Passed | EHS | JE DUNN-ALOHA | 15060021-01-F15-CSA-Anchorage Upgrade-CSA | Anchorage Upgrades | 15060021-01 | Feb/03/2023 | Feb/03/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 DST502 EXVO Lateral |  | RR | ROOM/AREA/BAY-READY | E-639a09312b21e5d9ec379b2f
Passed | RR CC/GT | JE DUNN-ALOHA | 15060021-01-F15-CSA-Anchorage Upgrade-CSA | Anchorage Upgrades | 15060021-01 | Feb/09/2023 | Feb/09/2023 | Feb/08/2023 | Feb/08/2023 | F15 | F15 DST502 EXVO Lateral |  | RR | ROOM/AREA/BAY-READY | E-639a09312b21e5d9ec379b2f
Passed | RR OA/BT | JE DUNN-ALOHA | 15060021-01-F15-CSA-Anchorage Upgrade-CSA | Anchorage Upgrades | 15060021-01 | Feb/08/2023 | Mar/03/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15 DST502 EXVO Lateral |  | RR | ROOM/AREA/BAY-READY | E-639a09312b21e5d9ec379b2f
Passed | FAT | JE DUNN-ALOHA | 15060021-01-F15-CSA-Anchorage Upgrade-CSA | Anchorage Upgrades | 15060021-01 | Feb/08/2023 | Mar/03/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15 DST502 EXVO Lateral |  | RR | ROOM/AREA/BAY-READY | E-639a09312b21e5d9ec379b2f
Passed | STRUCT CC | JE DUNN-ALOHA | 15060021-01-F15-CSA-Anchorage Upgrade-CSA | Anchorage Upgrades | 15060021-01 | Jan/16/2023 | Jan/16/2023 | Jan/18/2023 | Jan/18/2023 | F15 | F15 DST502 EXVO Lateral |  | RR | ROOM/AREA/BAY-READY | E-639a09312b21e5d9ec379b2f
Passed | STRUCT DV | JE DUNN-ALOHA | 15060021-01-F15-CSA-Anchorage Upgrade-CSA | Anchorage Upgrades | 15060021-01 | Jan/17/2023 | Jan/17/2023 | Jan/19/2023 | Jan/19/2023 | F15 | F15 DST502 EXVO Lateral |  | RR | ROOM/AREA/BAY-READY | E-639a09312b21e5d9ec379b2f
Passed | INST FAT | JE DUNN-ALOHA | 15060021-02-F15-PDIT133-0-15A | Differential Pressure Transmitter | 15060021-02 | May/22/2023 | May/22/2023 | May/30/2023 | May/30/2023 | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 133 | MECHANICAL EXHAUST | E-639a057e2b21e5bb823797ce
Passed | PROC CC | JE DUNN-ALOHA | 15060021-02-F15-PDIT133-0-15A | Differential Pressure Transmitter | 15060021-02 | May/15/2023 | May/15/2023 | May/24/2023 | May/30/2023 | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 133 | MECHANICAL EXHAUST | E-639a057e2b21e5bb823797ce
Passed | I&C OAT | JE DUNN-ALOHA | 15060021-02-F15-PDIT133-0-15A | Differential Pressure Transmitter | 15060021-02 | May/15/2023 | May/15/2023 | May/23/2023 | May/23/2023 | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 133 | MECHANICAL EXHAUST | E-639a057e2b21e5bb823797ce
Passed | INST FAT | JE DUNN-ALOHA | 15060021-02-F15-PDIT138-0-102A | Differential Pressure Transmitter | 15060021-02 | May/22/2023 | May/22/2023 | May/30/2023 | May/30/2023 | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 138 | MECHANICAL EXHAUST | E-639a057e2b21e5236e3797cf
Passed | PROC CC | JE DUNN-ALOHA | 15060021-02-F15-PDIT138-0-102A | Differential Pressure Transmitter | 15060021-02 | May/15/2023 | May/15/2023 | May/24/2023 | May/30/2023 | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 138 | MECHANICAL EXHAUST | E-639a057e2b21e5236e3797cf
Passed | I&C OAT | JE DUNN-ALOHA | 15060021-02-F15-PDIT138-0-102A | Differential Pressure Transmitter | 15060021-02 | May/15/2023 | May/15/2023 | May/23/2023 | May/23/2023 | F15 | EXVO/EXSC DST501 Monitoring Upgrade |  | 138 | MECHANICAL EXHAUST | E-639a057e2b21e5236e3797cf
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058484-03-F15-630LSS-CDM Project Flame Detector | New Flame Detector at X21 | 15058484-03 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 630 | LIFE SAFETY SYSTEM | E-639ca26f359e6050a81614f6
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058484-03-F15-630LSS-CDM Project Flame Detector | New Flame Detector at X21 | 15058484-03 | Aug/11/2023 | Aug/11/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 630 | LIFE SAFETY SYSTEM | E-639ca26f359e6050a81614f6
Not Started | FAT | JE DUNN-ALOHA | 15058484-03-F15-630LSS-CDM Project Flame Detector | New Flame Detector at X21 | 15058484-03 | Aug/14/2023 | Aug/22/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 630 | LIFE SAFETY SYSTEM | E-639ca26f359e6050a81614f6
Passed | LSS CC | JE DUNN-ALOHA | 15058484-03-F15-630LSS-CDM Project Flame Detector | New Flame Detector at X21 | 15058484-03 | Aug/02/2023 | Aug/02/2023 | May/25/2023 | May/25/2023 | F15 | F15 WW51 LOR:CDM |  | 630 | LIFE SAFETY SYSTEM | E-639ca26f359e6050a81614f6
Not Started | RR OA/BT | JE DUNN-ALOHA | 15052533-859 860-AL4-RR-Wall Penetration repeir | CSA | 15052533-859 860 | Jun/19/2023 | Jul/17/2023 |  |  | AL4 | Phase 4 Bays 859/860 |  | RR | ROOM/AREA/BAY-READY | E-63ab865662a14bafe1da71c9
Not Started | EHS | JE DUNN-ALOHA | 15052533-859 860-AL4-RR-Wall Penetration repeir | CSA | 15052533-859 860 | Jun/12/2023 | Jun/12/2023 |  |  | AL4 | Phase 4 Bays 859/860 |  | RR | ROOM/AREA/BAY-READY | E-63ab865662a14bafe1da71c9
Not Started | FAT | JE DUNN-ALOHA | 15052533-859 860-AL4-RR-Wall Penetration repeir | CSA | 15052533-859 860 | Jun/19/2023 | Jul/17/2023 |  |  | AL4 | Phase 4 Bays 859/860 |  | RR | ROOM/AREA/BAY-READY | E-63ab865662a14bafe1da71c9
Not Started | ARCH CC | JE DUNN-ALOHA | 15052533-859 860-AL4-RR-Wall Penetration repeir | CSA | 15052533-859 860 | Jun/09/2023 | Jun/09/2023 |  |  | AL4 | Phase 4 Bays 859/860 |  | RR | ROOM/AREA/BAY-READY | E-63ab865662a14bafe1da71c9
Not Started | RR CC/GT | JE DUNN-ALOHA | 15052533-859 860-AL4-RR-Wall Penetration repeir | CSA | 15052533-859 860 | Jun/16/2023 | Jun/16/2023 |  |  | AL4 | Phase 4 Bays 859/860 |  | RR | ROOM/AREA/BAY-READY | E-63ab865662a14bafe1da71c9
Not Started | RR OA/BT | JE DUNN-ALOHA | 15058484-03-F15-RR- CPE Tote Corral CSA | Tote Corral | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | RR | ROOM/AREA/BAY-READY | E-63add525b5bf067161e3dbbd
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-03-F15-RR- CPE Tote Corral CSA | Tote Corral | 15058484-03 | May/16/2023 | May/16/2023 | May/15/2023 | May/15/2023 | F15 | F15 WW51 LOR:CDM |  | RR | ROOM/AREA/BAY-READY | E-63add525b5bf067161e3dbbd
Passed | ARCH CC | JE DUNN-ALOHA | 15058484-03-F15-RR- CPE Tote Corral CSA | Tote Corral | 15058484-03 | May/26/2023 | May/26/2023 | Jun/01/2023 | Jun/01/2023 | F15 | F15 WW51 LOR:CDM |  | RR | ROOM/AREA/BAY-READY | E-63add525b5bf067161e3dbbd
Not Started | RR CC/GT | JE DUNN-ALOHA | 15058484-03-F15-RR- CPE Tote Corral CSA | Tote Corral | 15058484-03 | Jun/02/2023 | Jun/02/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | RR | ROOM/AREA/BAY-READY | E-63add525b5bf067161e3dbbd
Passed | ELECT DV | JE DUNN-ALOHA | 15058484-03-F15-RR- CPE Tote Corral CSA | Tote Corral | 15058484-03 | May/17/2023 | May/17/2023 | May/17/2023 | May/17/2023 | F15 | F15 WW51 LOR:CDM |  | RR | ROOM/AREA/BAY-READY | E-63add525b5bf067161e3dbbd
Not Started | FAT | JE DUNN-ALOHA | 15058484-03-F15-RR- CPE Tote Corral CSA | Tote Corral | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | RR | ROOM/AREA/BAY-READY | E-63add525b5bf067161e3dbbd
Passed | ARCH DV | JE DUNN-ALOHA | 15058484-03-F15-RR- CPE Tote Corral CSA | Tote Corral | 15058484-03 | May/03/2023 | May/03/2023 | May/09/2023 | May/09/2023 | F15 | F15 WW51 LOR:CDM |  | RR | ROOM/AREA/BAY-READY | E-63add525b5bf067161e3dbbd
In Progress | EHS | JE DUNN-ALOHA | 15058484-03-F15-RR- CPE Tote Corral CSA | Tote Corral | 15058484-03 | May/29/2023 | May/29/2023 | May/26/2023 |  | F15 | F15 WW51 LOR:CDM |  | RR | ROOM/AREA/BAY-READY | E-63add525b5bf067161e3dbbd
Passed | FAT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/21/2023 | Feb/20/2023 | Feb/23/2023 | Feb/23/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-63adca12284cd5642d3cb487
Passed | EQ OA/BT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/24/2023 | May/26/2023 | May/12/2023 | May/12/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-63adca12284cd5642d3cb487
Passed | I&C OAT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/03/2023 | Jan/03/2023 | Dec/29/2022 | Dec/29/2022 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-63adca12284cd5642d3cb487
Passed | EQ CC/GT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/20/2023 | Jan/20/2023 | Jan/24/2023 | Jan/24/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-63adca12284cd5642d3cb487
Passed | I&C CC | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/03/2023 | Jan/03/2023 | Dec/29/2022 | Dec/29/2022 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-63adca12284cd5642d3cb487
Passed | PROC CC | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/13/2023 | Jan/13/2023 | Jan/20/2023 | Jan/20/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-63adca12284cd5642d3cb487
Passed | I&C DV | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/04/2023 | Jan/04/2023 | Jan/16/2023 | Jan/16/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-63adca12284cd5642d3cb487
Passed | INST FAT | JE DUNN-ALOHA | 15048483-01-F15-PIT55-580-1B | UPW Dist. EOL | 15048483-01 | Jan/17/2023 | Feb/14/2023 | Jan/10/2023 | Feb/09/2023 | F15 | PLC5 Phase 1 |  | 245 | UPW | E-63adca12284cd5642d3cb487
Passed | EQ CC/GT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16B-10 | EXISTING VFD RELO | 15061734-01 | Apr/24/2023 | Apr/24/2023 | Apr/24/2023 | Apr/24/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4cdfdd0e6d
Passed | ELECT CC | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16B-10 | EXISTING VFD RELO | 15061734-01 | Apr/17/2023 | Apr/17/2023 | Apr/18/2023 | Apr/18/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4cdfdd0e6d
Passed | FAT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16B-10 | EXISTING VFD RELO | 15061734-01 | Apr/25/2023 | May/23/2023 | May/04/2023 | May/04/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4cdfdd0e6d
Passed | ELECT OAT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16B-10 | EXISTING VFD RELO | 15061734-01 | Apr/11/2023 | Apr/11/2023 | Apr/13/2023 | Apr/13/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4cdfdd0e6d
Passed | EQ OA/BT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16B-10 | EXISTING VFD RELO | 15061734-01 | Apr/25/2023 | May/23/2023 | May/04/2023 | May/04/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4cdfdd0e6d
Passed | ELECT CC | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-14A-10 (DEMO) | VFD DEMO | 15061734-01 | May/10/2023 | May/10/2023 | May/09/2023 | May/09/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b6084dd0e72
Passed | EQ CC/GT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-14A-10 (DEMO) | VFD DEMO | 15061734-01 | May/15/2023 | May/15/2023 | May/11/2023 | May/11/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b6084dd0e72
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-14A-10 (DEMO) | VFD DEMO | 15061734-01 | May/30/2023 | Jun/14/2023 |  |  | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b6084dd0e72
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061941-01-S1R1V18A-19 - SF6 Heater Controller | Heater Controller | 15061941-01 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | F15 WW25 LOR: Spec Gas Project PAT552-553 [SF6] |  | 500 | SPECIALTY GAS SYSTEMS | E-63b709d7284cd548853ec38b
Not Started | FAT | JE DUNN-ALOHA | 15061941-01-S1R1V18A-19 - SF6 Heater Controller | Heater Controller | 15061941-01 | Jun/30/2023 | Jul/31/2023 |  |  | F15 | F15 WW25 LOR: Spec Gas Project PAT552-553 [SF6] |  | 500 | SPECIALTY GAS SYSTEMS | E-63b709d7284cd548853ec38b
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061941-01-S1R1V18A-19 - SF6 Heater Controller | Heater Controller | 15061941-01 | Jun/30/2023 | Jul/31/2023 |  |  | F15 | F15 WW25 LOR: Spec Gas Project PAT552-553 [SF6] |  | 500 | SPECIALTY GAS SYSTEMS | E-63b709d7284cd548853ec38b
Not Started | ELECT CC | JE DUNN-ALOHA | 15061941-01-S1R1V18A-19 - SF6 Heater Controller | Heater Controller | 15061941-01 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | F15 WW25 LOR: Spec Gas Project PAT552-553 [SF6] |  | 500 | SPECIALTY GAS SYSTEMS | E-63b709d7284cd548853ec38b
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061941-01-S1R1V18A-19 - SF6 Heater Controller | Heater Controller | 15061941-01 | Jun/29/2023 | Jun/29/2023 |  |  | F15 | F15 WW25 LOR: Spec Gas Project PAT552-553 [SF6] |  | 500 | SPECIALTY GAS SYSTEMS | E-63b709d7284cd548853ec38b
Passed | PROC CC | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-14-10 (DEMO) | SKD DEMO | 15061734-01 | May/03/2023 | May/03/2023 | May/11/2023 | May/11/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b51bcdd0e71
Passed | ELECT CC | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-14-10 (DEMO) | SKD DEMO | 15061734-01 | May/10/2023 | May/10/2023 | May/08/2023 | May/08/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b51bcdd0e71
Passed | EQ CC/GT | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-14-10 (DEMO) | SKD DEMO | 15061734-01 | May/15/2023 | May/15/2023 | May/11/2023 | May/11/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b51bcdd0e71
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-14-10 (DEMO) | SKD DEMO | 15061734-01 | May/30/2023 | Jun/14/2023 |  |  | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b51bcdd0e71
Passed | I&C OAT | JE DUNN-ALOHA | 15061734-01-AL3-LSSH261-16-10A | AL3 AWN LIFT STATION 16 HI-HI LEVEL ALARM LSHH261-16-10A L1 - B/2.5 | 15061734-01 | Apr/11/2023 | Apr/11/2023 | Apr/18/2023 | Apr/18/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b616ddd0e6e
Not Started | INST FAT | JE DUNN-ALOHA | 15061734-01-AL3-LSSH261-16-10A | AL3 AWN LIFT STATION 16 HI-HI LEVEL ALARM LSHH261-16-10A L1 - B/2.5 | 15061734-01 | Apr/18/2023 | Apr/18/2023 |  |  | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b616ddd0e6e
Passed | PROC CC | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/17/2023 | Apr/17/2023 | Apr/24/2023 | Apr/24/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | I&C CC | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/17/2023 | Apr/17/2023 | Apr/18/2023 | Apr/18/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | PROC DV | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/12/2023 | Apr/12/2023 | Apr/13/2023 | Apr/13/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | I&C DV | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/18/2023 | Apr/18/2023 | Apr/14/2023 | Apr/17/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | SYS CC/GT | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/25/2023 | Apr/25/2023 | Apr/25/2023 | Apr/25/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/17/2023 | Apr/17/2023 | Apr/19/2023 | Apr/19/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | TELE CC | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/17/2023 | Apr/17/2023 | Apr/18/2023 | Apr/18/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | FAT | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/25/2023 | May/23/2023 | May/04/2023 | May/04/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | EHS | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/18/2023 | Apr/18/2023 | Apr/25/2023 | Apr/25/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Not Started | SYS OA/BT | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/25/2023 | Jun/05/2023 |  |  | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Passed | ELECT DV | JE DUNN-ALOHA | 15061734-01-AL3-SKD261-16-10 | EXISTING SKD RELO | 15061734-01 | Apr/18/2023 | Apr/18/2023 | Apr/17/2023 | Apr/17/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b4a2fdd0e70
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16B4-10 (DEMO) | VFD DEMO | 15061734-01 | May/30/2023 | Jun/14/2023 |  |  | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b3293dd0e73
Passed | ELECT CC | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16B4-10 (DEMO) | VFD DEMO | 15061734-01 | May/10/2023 | May/10/2023 | May/09/2023 | May/09/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b3293dd0e73
Passed | EQ CC/GT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16B4-10 (DEMO) | VFD DEMO | 15061734-01 | May/15/2023 | May/15/2023 | May/11/2023 | May/11/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14b3293dd0e73
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15058530-01-F15-212OFA-10" Header | 10" Header | 15058530-01 | Jun/19/2024 | Jun/19/2024 |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12fed4ea90806
Not Started | PROC CC | JE DUNN-ALOHA | 15058530-01-F15-212OFA-10" Header | 10" Header | 15058530-01 | Jun/12/2024 | Jun/12/2024 |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12fed4ea90806
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058530-01-F15-212OFA-10" Header | 10" Header | 15058530-01 | Jun/20/2024 | Jun/28/2024 |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12fed4ea90806
Not Started | MECH W CC | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-24-X (Future-Set Only) | RAH New Future | 15058567-01 | Aug/02/2023 | Aug/02/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63b751c9ba715d31d8ebbe87
Not Started | ARCH CC | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-24-X (Future-Set Only) | RAH New Future | 15058567-01 | Aug/02/2023 | Aug/02/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63b751c9ba715d31d8ebbe87
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-24-X (Future-Set Only) | RAH New Future | 15058567-01 | Aug/10/2023 | Sep/08/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63b751c9ba715d31d8ebbe87
Not Started | FAT | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-24-X (Future-Set Only) | RAH New Future | 15058567-01 | Aug/10/2023 | Sep/08/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63b751c9ba715d31d8ebbe87
Not Started | EHS | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-24-X (Future-Set Only) | RAH New Future | 15058567-01 | Aug/03/2023 | Aug/03/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63b751c9ba715d31d8ebbe87
Passed | MECH W DV | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-24-X (Future-Set Only) | RAH New Future | 15058567-01 | Aug/28/2023 | Aug/28/2023 | Mar/14/2023 | Mar/14/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63b751c9ba715d31d8ebbe87
Not Started | ARCH DV | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-24-X (Future-Set Only) | RAH New Future | 15058567-01 | Aug/03/2023 | Aug/03/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63b751c9ba715d31d8ebbe87
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15058567-01-F15-RAH-2-24-X (Future-Set Only) | RAH New Future | 15058567-01 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63b751c9ba715d31d8ebbe87
Passed | I&C OAT | JE DUNN-ALOHA | 15061734-01-AL3QS261-16-10A | AL3 AWN LIFT STATION 16 FAULT SIGNAL QS261-16-10A L1 - B/2.5 | 15061734-01 | Apr/17/2023 | Apr/17/2023 | Apr/18/2023 | Apr/18/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14bb10add0e6f
Passed | EQ CC/GT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16A-10 | EXISTING VFD RELO | 15061734-01 | Apr/24/2023 | Apr/24/2023 | Apr/24/2023 | Apr/24/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14bbe39dd0e6b
Passed | ELECT OAT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16A-10 | EXISTING VFD RELO | 15061734-01 | Apr/11/2023 | Apr/11/2023 | Apr/13/2023 | Apr/13/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14bbe39dd0e6b
Passed | ELECT CC | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16A-10 | EXISTING VFD RELO | 15061734-01 | Apr/17/2023 | Apr/17/2023 | Apr/18/2023 | Apr/18/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14bbe39dd0e6b
Passed | FAT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16A-10 | EXISTING VFD RELO | 15061734-01 | Apr/25/2023 | May/23/2023 | May/04/2023 | May/04/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14bbe39dd0e6b
Passed | EQ OA/BT | JE DUNN-ALOHA | 15061734-01-AL3-VFD261-16A-10 | EXISTING VFD RELO | 15061734-01 | Apr/25/2023 | May/23/2023 | May/04/2023 | May/04/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-63b6f56062a14bbe39dd0e6b
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15058530-01-F15-212OFA-8" Main | 8"Main | 15058530-01 | Jun/19/2024 | Jun/19/2024 |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12f8c18a90805
Not Started | PROC CC | JE DUNN-ALOHA | 15058530-01-F15-212OFA-8" Main | 8"Main | 15058530-01 | Jun/12/2024 | Jun/12/2024 |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12f8c18a90805
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15058530-01-F15-212OFA-8" Main | 8"Main | 15058530-01 | Jun/20/2024 | Jun/28/2024 |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12f8c18a90805
Not Started | PROC DV | JE DUNN-ALOHA | 15058530-01-F15-212OFA-8" Main | 8"Main | 15058530-01 | Jun/13/2024 | Jun/13/2024 |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12f8c18a90805
Not Started | FAT | JE DUNN-ALOHA | 15058530-01-F15-212OFA-8" Main | 8"Main | 15058530-01 | Jun/20/2024 | Jun/28/2024 |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12f8c18a90805
Not Started | MECH W DV | JE DUNN-ALOHA | 15058530-01-F15-212OFA-8" Main | 8"Main | 15058530-01 |  |  |  |  | F15 | F15 WW51 : OFA MAIN |  | 212 | MECHANICAL PROCESS | E-63b717774da12f8c18a90805
Passed | RR CC/GT | JE DUNN-ALOHA | 15059001-01-F15-CSA-Gas Laterals Anchorage Upgrade-CSA | Anchorage Upgrades | 15059001-01 | Feb/08/2023 | Feb/08/2023 | Feb/08/2023 | Feb/08/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | RR | ROOM/AREA/BAY-READY | E-63d161b58bd9027f490c9fd6
Passed | STRUCT CC | JE DUNN-ALOHA | 15059001-01-F15-CSA-Gas Laterals Anchorage Upgrade-CSA | Anchorage Upgrades | 15059001-01 | Jan/31/2023 | Jan/31/2023 | Feb/06/2023 | Feb/06/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | RR | ROOM/AREA/BAY-READY | E-63d161b58bd9027f490c9fd6
Passed | EHS | JE DUNN-ALOHA | 15059001-01-F15-CSA-Gas Laterals Anchorage Upgrade-CSA | Anchorage Upgrades | 15059001-01 | Feb/01/2023 | Feb/01/2023 | Feb/07/2023 | Feb/07/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | RR | ROOM/AREA/BAY-READY | E-63d161b58bd9027f490c9fd6
Passed | RR OA/BT | JE DUNN-ALOHA | 15059001-01-F15-CSA-Gas Laterals Anchorage Upgrade-CSA | Anchorage Upgrades | 15059001-01 | Feb/09/2023 | Mar/03/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | RR | ROOM/AREA/BAY-READY | E-63d161b58bd9027f490c9fd6
Passed | FAT | JE DUNN-ALOHA | 15059001-01-F15-CSA-Gas Laterals Anchorage Upgrade-CSA | Anchorage Upgrades | 15059001-01 | Feb/09/2023 | Mar/03/2023 | Mar/02/2023 | Mar/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | RR | ROOM/AREA/BAY-READY | E-63d161b58bd9027f490c9fd6
Passed | STRUCT DV | JE DUNN-ALOHA | 15059001-01-F15-CSA-Gas Laterals Anchorage Upgrade-CSA | Anchorage Upgrades | 15059001-01 | Feb/09/2023 | Feb/09/2023 | Feb/02/2023 | Feb/02/2023 | F15 | F15 WW51 LOR-Gas Laterals |  | RR | ROOM/AREA/BAY-READY | E-63d161b58bd9027f490c9fd6
Passed | I&C OAT | JE DUNN-ALOHA | 15058567-01-F15-QA-2-15-7 | FAN FAILED FROM VFD QA-2-15-7 | 15058567-01 | Apr/19/2023 | Apr/19/2023 | Apr/26/2023 | Apr/26/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63e26b2495a34501320c7667
Passed | I&C OAT | JE DUNN-ALOHA | 15058567-01-F15-HS-2-15-(5-8) | FAN RUN Command HS-2-15-(5-8) | 15058567-01 | Apr/19/2023 | Apr/19/2023 | Apr/27/2023 | Apr/27/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63e26b2495a345178e0c7665
Passed | I&C OAT | JE DUNN-ALOHA | 15058567-01-F15-QL-2-15-7 | FAN STATUS FROM VFD QL-2-15-7 | 15058567-01 | Apr/19/2023 | Apr/19/2023 | Apr/26/2023 | Apr/26/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63e26b2495a34507bd0c7668
Passed | INST FAT | JE DUNN-ALOHA | 15058567-01-F15-TET-2-15-7 | DISCH TEMP TET-2-15-7 | 15058567-01 | Apr/28/2023 | Apr/28/2023 | May/24/2023 | May/24/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63e26b2495a34561350c7664
Passed | I&C OAT | JE DUNN-ALOHA | 15058567-01-F15-TET-2-15-7 | DISCH TEMP TET-2-15-7 | 15058567-01 | Apr/13/2023 | Apr/13/2023 | Apr/26/2023 | Apr/26/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63e26b2495a34561350c7664
Passed | I&C OAT | JE DUNN-ALOHA | 15058567-01-F15-LSH-2-15-(5-8) | H LEVEL SW LSH-2-15-(5-8) | 15058567-01 | Apr/19/2023 | Apr/19/2023 | Apr/26/2023 | Apr/27/2023 | F15 | F15 Ballroom 555 Conversion |  | 102 | MECHANICAL DRY | E-63e26b2495a345ee210c7666
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15057901-01-AL4-106GMAH-Duct Install | Al3-AL4 Link GMAH Duct Tie In | 15057901-01 | Aug/02/2023 | Aug/30/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 103 | MECHANICAL DRY | E-63e3e908400f5006583bcd88
Not Started | MECH D CC | JE DUNN-ALOHA | 15057901-01-AL4-106GMAH-Duct Install | Al3-AL4 Link GMAH Duct Tie In | 15057901-01 | Jul/25/2023 | Jul/25/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 103 | MECHANICAL DRY | E-63e3e908400f5006583bcd88
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15057901-01-AL4-106GMAH-Duct Install | Al3-AL4 Link GMAH Duct Tie In | 15057901-01 | Aug/01/2023 | Aug/01/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 103 | MECHANICAL DRY | E-63e3e908400f5006583bcd88
Passed | I&C OAT | JE DUNN-ALOHA | 15057901-01-AL3-TET005-2-23 | TET Relocate | 15057901-01 | Jul/19/2023 | Jul/19/2023 | Jun/01/2023 | Jun/01/2023 | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 106 | MECHANICAL DRY | E-63e3e908400f5018e33bcd86
Passed | INST FAT | JE DUNN-ALOHA | 15057901-01-AL3-TET005-2-23 | TET Relocate | 15057901-01 | Jul/26/2023 | Jul/26/2023 | Jun/01/2023 | Jun/01/2023 | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 106 | MECHANICAL DRY | E-63e3e908400f5018e33bcd86
Passed | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15057901-01-AL3-TET005-2-23 | TET Relocate | 15057901-01 | Jul/19/2023 | Jul/19/2023 | Jun/01/2023 | Jun/01/2023 | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 106 | MECHANICAL DRY | E-63e3e908400f5018e33bcd86
Not Started | ELECT OAT | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/25/2023 | Jul/25/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | ELECT DV | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/26/2023 | Jul/26/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | ELECT CC | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/25/2023 | Jul/25/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | ARCH CC | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/25/2023 | Jul/25/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | ARCH DV | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/26/2023 | Jul/26/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | EHS | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/26/2023 | Jul/26/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | FAT | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Aug/02/2023 | Aug/30/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | RR CC/GT | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Aug/01/2023 | Aug/01/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | RR OA/BT | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Aug/02/2023 | Aug/30/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | MECH D CC | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/25/2023 | Jul/25/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | MECH D DV | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/26/2023 | Jul/26/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | LSS CC | JE DUNN-ALOHA | 15057901-01-AL3-CSA-Link to AL4 Mod | AL3-AL4 Link Mod | 15057901-01 | Jul/25/2023 | Jul/25/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f502e7c3bcd85
Not Started | ARCH DV | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/18/2023 | Oct/18/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | ELECT DV | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/18/2023 | Oct/18/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | ELECT OAT | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/17/2023 | Oct/17/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | ELECT CC | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/17/2023 | Oct/17/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | MECH D CC | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/17/2023 | Oct/17/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | ARCH CC | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/17/2023 | Oct/17/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | EHS | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/18/2023 | Oct/18/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | RR CC/GT | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/24/2023 | Oct/24/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | FAT | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/25/2023 | Nov/22/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | RR OA/BT | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/25/2023 | Nov/22/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | MECH D DV | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/18/2023 | Oct/18/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | LSS CC | JE DUNN-ALOHA | 15057901-01-AL4-CSA-TRDI COMM ROOM WALL MOD | TRDI COMM ROOM WALL MOD | 15057901-01 | Oct/17/2023 | Oct/17/2023 |  |  | AL4 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | RR | ROOM/AREA/BAY-READY | E-63e3e908400f50f0033bcd84
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15057901-01-AL3-106VAV-Duct Install | VVR Supply Duct Install(MECH Tower #1) | 15057901-01 | Aug/01/2023 | Aug/01/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 106 | MECHANICAL DRY | E-63e3e908400f5065833bcd87
Not Started | MECH D CC | JE DUNN-ALOHA | 15057901-01-AL3-106VAV-Duct Install | VVR Supply Duct Install(MECH Tower #1) | 15057901-01 | Jul/25/2023 | Jul/25/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 106 | MECHANICAL DRY | E-63e3e908400f5065833bcd87
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15057901-01-AL3-106VAV-Duct Install | VVR Supply Duct Install(MECH Tower #1) | 15057901-01 | Aug/02/2023 | Aug/30/2023 |  |  | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 106 | MECHANICAL DRY | E-63e3e908400f5065833bcd87
Passed | I&C CC | JE DUNN-ALOHA | 15057901-01-AL3-106VAV-Duct Install | VVR Supply Duct Install(MECH Tower #1) | 15057901-01 | Jul/25/2023 | Jul/25/2023 | Jun/01/2023 | Jun/01/2023 | AL3 | ODP WW42 LRP: AL3/AL4 Communications Wall and Link |  | 106 | MECHANICAL DRY | E-63e3e908400f5065833bcd87
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-376 | PIV RELO | 15054721-01 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a183c15c0f32
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-PIV 03-02-376 | PIV RELO | 15054721-01 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a183c15c0f32
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-376 | PIV RELO | 15054721-01 | Aug/28/2023 | Sep/21/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a183c15c0f32
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-376 | PIV RELO | 15054721-01 | Aug/28/2023 | Sep/21/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a183c15c0f32
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-PIV 03-02-376 | PIV RELO | 15054721-01 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a183c15c0f32
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-PIV 03-02-180 | PIV RELO | 15054721-01 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a17b4b5c0f31
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-180 | PIV RELO | 15054721-01 | Aug/28/2023 | Sep/21/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a17b4b5c0f31
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-180 | PIV RELO | 15054721-01 | Aug/28/2023 | Sep/21/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a17b4b5c0f31
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-180 | PIV RELO | 15054721-01 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a17b4b5c0f31
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-PIV 03-02-180 | PIV RELO | 15054721-01 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a17b4b5c0f31
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-179 | PIV RELO | 15054721-01 | Aug/28/2023 | Sep/21/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a13e6e5c0f30
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-179 | PIV RELO | 15054721-01 | Aug/28/2023 | Sep/21/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a13e6e5c0f30
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-PIV 03-02-179 | PIV RELO | 15054721-01 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a13e6e5c0f30
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-PIV 03-02-179 | PIV RELO | 15054721-01 | Aug/18/2023 | Aug/18/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a13e6e5c0f30
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-PIV 03-02-179 | PIV RELO | 15054721-01 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | AS1 Support Building |  | 153 | FIRE PROTECTION/SSH | E-63f7905ccc32a13e6e5c0f30
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-2-2B | CT CURRENT SWITCH | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54a050de5cfd4
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-2-2B | CT CURRENT SWITCH | 15048483-02 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54a050de5cfd4
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-1-2B | CT CURRENT SWITCH | 15048483-02 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54ae7ace5cfd0
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-1-2B | CT CURRENT SWITCH | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54ae7ace5cfd0
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-1-2A | CT CURRENT SWITCH | 15048483-02 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54a1ddde5cfcf
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-1-2A | CT CURRENT SWITCH | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54a1ddde5cfcf
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-1-1A | CT CURRENT SWITCH | 15048483-02 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54a267ae5cfcd
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-1-1A | CT CURRENT SWITCH | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54a267ae5cfcd
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-2-1B | CT CURRENT SWITCH | 15048483-02 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54ae87ce5cfd2
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-2-1B | CT CURRENT SWITCH | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54ae87ce5cfd2
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-2-2A | CT CURRENT SWITCH | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54aa35ce5cfd3
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-2-2A | CT CURRENT SWITCH | 15048483-02 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54aa35ce5cfd3
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-1-1B | CT CURRENT SWITCH | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54acd15e5cfce
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-1-1B | CT CURRENT SWITCH | 15048483-02 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54acd15e5cfce
Not Started | I&C OAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-2-1A | CT CURRENT SWITCH | 15048483-02 | Aug/09/2023 | Aug/09/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54a5225e5cfd1
Not Started | INST FAT | JE DUNN-ALOHA | 15048483-02-F15-IS29-2-1A | CT CURRENT SWITCH | 15048483-02 | Aug/16/2023 | Aug/16/2023 |  |  | F15 | PLC5-P2 |  | 650 | FACILITIES MONITORING SYSTEM | E-63ff83805cd54a5225e5cfd1
Not Started | INST FAT | JE DUNN-ALOHA | 15057901-02-AL3-FIT-212-0-05A | AL3 OFA FLOW [AL3 1H-01] FIT212-0-05A Level 1 - H/1 | 15057901-02 | Nov/28/2023 | Nov/28/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e0d7e25314e
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15057901-02-AL3-FIT-212-0-05A | AL3 OFA FLOW [AL3 1H-01] FIT212-0-05A Level 1 - H/1 | 15057901-02 | Nov/21/2023 | Nov/21/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e0d7e25314e
Not Started | I&C OAT | JE DUNN-ALOHA | 15057901-02-AL3-FIT-212-0-05A | AL3 OFA FLOW [AL3 1H-01] FIT212-0-05A Level 1 - H/1 | 15057901-02 | Nov/21/2023 | Nov/21/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e0d7e25314e
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main | AL3 Courtyard OFA Main | 15057901-02 | Dec/05/2023 | Dec/13/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e8d7e25314f
Not Started | FAT | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main | AL3 Courtyard OFA Main | 15057901-02 | Dec/05/2023 | Dec/13/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e8d7e25314f
Not Started | I&C CC | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main | AL3 Courtyard OFA Main | 15057901-02 | Nov/27/2023 | Nov/27/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e8d7e25314f
Not Started | PROC CC | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main | AL3 Courtyard OFA Main | 15057901-02 | Nov/27/2023 | Nov/27/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e8d7e25314f
Not Started | PROC DV | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main | AL3 Courtyard OFA Main | 15057901-02 | Nov/28/2023 | Nov/28/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e8d7e25314f
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main | AL3 Courtyard OFA Main | 15057901-02 | Dec/04/2023 | Dec/04/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e8d7e25314f
Not Started | I&C DV | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main | AL3 Courtyard OFA Main | 15057901-02 | Nov/28/2023 | Nov/28/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-641ca5f71e574e8d7e25314f
Not Started | FAT | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker DRB01-Fall Protection | New Support Beam | 15059929-01 | Jun/07/2023 | Jul/06/2023 |  |  | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6426ea3e849b2978fa6d0d0f
Passed | RR CC/GT | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker DRB01-Fall Protection | New Support Beam | 15059929-01 | Jun/06/2023 | Jun/06/2023 | Apr/28/2023 | Apr/28/2023 | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6426ea3e849b2978fa6d0d0f
Not Started | RR OA/BT | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker DRB01-Fall Protection | New Support Beam | 15059929-01 | Jun/07/2023 | Jul/06/2023 |  |  | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6426ea3e849b2978fa6d0d0f
Passed | STRUCT CC | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker DRB01-Fall Protection | New Support Beam | 15059929-01 | May/30/2023 | May/30/2023 | Apr/24/2023 | Apr/24/2023 | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6426ea3e849b2978fa6d0d0f
Passed | ARCH CC | JE DUNN-ALOHA | 15059929-01-AL4-CSA AL4 Interfloor Stocker DRB01-Fall Protection | New Support Beam | 15059929-01 | May/30/2023 | May/30/2023 | Apr/27/2023 | Apr/27/2023 | AL4 | AL4 Interfloor Stocker |  | RR | ROOM/AREA/BAY-READY | E-6426ea3e849b2978fa6d0d0f
Not Started | FAT | JE DUNN-ALOHA | 15061734-01-AL3-261AWN-Submain16 | Submain | 15061734-01 | May/30/2023 | Jun/14/2023 |  |  | AL3 |  |  | 261 | WASTE | E-642702df849b2989ed6d3e2a
Passed | DIST CC/GT | JE DUNN-ALOHA | 15061734-01-AL3-261AWN-Submain16 | Submain | 15061734-01 | May/17/2023 | May/17/2023 | Apr/26/2023 | Apr/26/2023 | AL3 |  |  | 261 | WASTE | E-642702df849b2989ed6d3e2a
Passed | PROC CC | JE DUNN-ALOHA | 15061734-01-AL3-261AWN-Submain16 | Submain | 15061734-01 | May/10/2023 | May/10/2023 | Apr/26/2023 | Apr/26/2023 | AL3 |  |  | 261 | WASTE | E-642702df849b2989ed6d3e2a
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061734-01-AL3-261AWN-Submain16 | Submain | 15061734-01 | May/30/2023 | Jun/14/2023 |  |  | AL3 |  |  | 261 | WASTE | E-642702df849b2989ed6d3e2a
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-20%He/Ar-BCI3-U/16.8 | Purge Panel | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be7f5dd9c614
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-20%He/Ar-BCI3-U/16.8 | Purge Panel | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be7f5dd9c614
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-20%He/Ar-BCI3-U/16.8 | Purge Panel | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be7f5dd9c614
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-20%He/Ar-BCI3-U/16.8 | Purge Panel | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be7f5dd9c614
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-20%He/Ar-BCI3-U/16.8 | Purge Panel | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be7f5dd9c614
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | MECH D CC | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | LSS CC | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | I&C CC | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | ELECT CC | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-BCl3-S.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be823dd9c61a
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | ELECT CC | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | I&C CC | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | MECH D CC | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | LSS CC | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-NG05-VMB-S.5/18 | VMB | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be88d3d9c61d
Not Started | EHS | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S.5-T/16.9-18 | CSA-EXGF Anchorage Upgrades | 15061939-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88f6d9c615
Not Started | RR CC/GT | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S.5-T/16.9-18 | CSA-EXGF Anchorage Upgrades | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88f6d9c615
Not Started | FAT | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S.5-T/16.9-18 | CSA-EXGF Anchorage Upgrades | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88f6d9c615
Not Started | STRUCT CC | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S.5-T/16.9-18 | CSA-EXGF Anchorage Upgrades | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88f6d9c615
Not Started | STRUCT DV | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S.5-T/16.9-18 | CSA-EXGF Anchorage Upgrades | 15061939-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88f6d9c615
Not Started | RR OA/BT | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S.5-T/16.9-18 | CSA-EXGF Anchorage Upgrades | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88f6d9c615
Not Started | TELE CC | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | LSS CC | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | MECH D CC | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | ELECT CC | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-C4F6-GC-C3-K/L | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be790ad9c61b
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-20%He/Ar-SiCI4-U/16.8 | Purge Panel | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be0e03d9c61e
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-20%He/Ar-SiCI4-U/16.8 | Purge Panel | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be0e03d9c61e
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-20%He/Ar-SiCI4-U/16.8 | Purge Panel | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be0e03d9c61e
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-20%He/Ar-SiCI4-U/16.8 | Purge Panel | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be0e03d9c61e
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-20%He/Ar-SiCI4-U/16.8 | Purge Panel | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be0e03d9c61e
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | MECH D CC | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | I&C CC | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | ELECT CC | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | LSS CC | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | TELE CC | JE DUNN-ALOHA | 15061939-01-SiCl4-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be013fd9c61f
Not Started | STRUCT DV | JE DUNN-ALOHA | 15061939-01-CSA-Anchorage Upgrades T.5-U/16.9-19.5 | Anchorage Upgrades | 15061939-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88afd9c616
Not Started | EHS | JE DUNN-ALOHA | 15061939-01-CSA-Anchorage Upgrades T.5-U/16.9-19.5 | Anchorage Upgrades | 15061939-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88afd9c616
Not Started | RR CC/GT | JE DUNN-ALOHA | 15061939-01-CSA-Anchorage Upgrades T.5-U/16.9-19.5 | Anchorage Upgrades | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88afd9c616
Not Started | FAT | JE DUNN-ALOHA | 15061939-01-CSA-Anchorage Upgrades T.5-U/16.9-19.5 | Anchorage Upgrades | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88afd9c616
Not Started | RR OA/BT | JE DUNN-ALOHA | 15061939-01-CSA-Anchorage Upgrades T.5-U/16.9-19.5 | Anchorage Upgrades | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88afd9c616
Not Started | STRUCT CC | JE DUNN-ALOHA | 15061939-01-CSA-Anchorage Upgrades T.5-U/16.9-19.5 | Anchorage Upgrades | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be88afd9c616
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | ELECT CC | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | LSS CC | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | I&C CC | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | MECH D CC | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-SiCl4-S.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48bed31fd9c620
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | MECH D CC | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | LSS CC | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | ELECT CC | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | I&C CC | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-BCl3-T.5/17 | Gas Cabinet | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2f82d9c619
Not Started | STRUCT CC | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S-S.5/18-18.5 | CSA-OFA Anchorage Upgrades | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be4103d9c617
Not Started | EHS | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S-S.5/18-18.5 | CSA-OFA Anchorage Upgrades | 15061939-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be4103d9c617
Not Started | RR CC/GT | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S-S.5/18-18.5 | CSA-OFA Anchorage Upgrades | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be4103d9c617
Not Started | FAT | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S-S.5/18-18.5 | CSA-OFA Anchorage Upgrades | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be4103d9c617
Not Started | STRUCT DV | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S-S.5/18-18.5 | CSA-OFA Anchorage Upgrades | 15061939-01 | Nov/15/2023 | Nov/15/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be4103d9c617
Not Started | RR OA/BT | JE DUNN-ALOHA | 15061939-01-CSA- Anchorage Upgrades S-S.5/18-18.5 | CSA-OFA Anchorage Upgrades | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | RR | ROOM/AREA/BAY-READY | E-642c4cf87f48be4103d9c617
Not Started | PROC CC | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Not Started | MECH D CC | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Not Started | ELECT CC | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Not Started | LSS CC | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/21/2023 | Nov/21/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Not Started | SL2 | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Not Started | SL1 | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/22/2023 | Dec/04/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Not Started | I&C CC | JE DUNN-ALOHA | 15061939-01-C4F6-VMB-C3-K/L-S.5/18 | VMB | 15061939-01 | Nov/14/2023 | Nov/14/2023 |  |  | F15 | F15 WW25 LOR: RIH501, CNP504 & CNP505 |  | 500 | SPECIALTY GAS SYSTEMS | E-642c4cf87f48be2b47d9c61c
Passed | DIST CC/GT | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-CDM-1 (Relabel) | Solvent Valve Box(Repurposed) | 15058484-03 | Apr/18/2023 | Apr/18/2023 | Apr/17/2023 | Apr/17/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-642ee79de070f7c4efb14c2f
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-CDM-1 (Relabel) | Solvent Valve Box(Repurposed) | 15058484-03 | Apr/07/2023 | Apr/07/2023 | Apr/13/2023 | Apr/13/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-642ee79de070f7c4efb14c2f
Passed | SL2 | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-CDM-1 (Relabel) | Solvent Valve Box(Repurposed) | 15058484-03 | Apr/19/2023 | Apr/28/2023 | Apr/28/2023 | May/08/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-642ee79de070f7c4efb14c2f
Passed | SL1 | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-CDM-1 (Relabel) | Solvent Valve Box(Repurposed) | 15058484-03 | Apr/19/2023 | Apr/28/2023 | Apr/28/2023 | May/08/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-642ee79de070f7c4efb14c2f
Passed | DIST OA/BT | JE DUNN-ALOHA | 15058484-03-F15-PGMEA-CDM-1 (Relabel) | Solvent Valve Box(Repurposed) | 15058484-03 | Apr/19/2023 | Apr/28/2023 | May/08/2023 | May/08/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-642ee79de070f7c4efb14c2f
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main-DEMO | AL3 Courtyard OFA Main | 15057901-02 | Dec/04/2023 | Dec/04/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-643db43ef81044753d2f9bd1
Not Started | PROC CC | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main-DEMO | AL3 Courtyard OFA Main | 15057901-02 | Nov/27/2023 | Nov/27/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-643db43ef81044753d2f9bd1
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15057901-02-AL3-OFA212-Main-DEMO | AL3 Courtyard OFA Main | 15057901-02 | Dec/05/2023 | Dec/13/2023 |  |  | AL3 | ODP WW42 LRP:AL3 OFA (Purple Rain) |  | 212 | MECHANICAL PROCESS | E-643db43ef81044753d2f9bd1
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15058484-03-1R1M18A-2 (P-Trap Primer) | UNSTAB30%H2O2-M.1/17.3-S P Trap Primer | 15058484-03 | Jun/05/2023 | Jun/09/2023 |  |  | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-6447fb2238a60c6c1e0ae08c
Passed | ELECT OAT | JE DUNN-ALOHA | 15058484-03-1R1M18A-2 (P-Trap Primer) | UNSTAB30%H2O2-M.1/17.3-S P Trap Primer | 15058484-03 |  |  | Apr/25/2023 | Apr/25/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-6447fb2238a60c6c1e0ae08c
Passed | EQ CC/GT | JE DUNN-ALOHA | 15058484-03-1R1M18A-2 (P-Trap Primer) | UNSTAB30%H2O2-M.1/17.3-S P Trap Primer | 15058484-03 | May/18/2023 | May/18/2023 | May/11/2023 | May/11/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-6447fb2238a60c6c1e0ae08c
Passed | ELECT CC | JE DUNN-ALOHA | 15058484-03-1R1M18A-2 (P-Trap Primer) | UNSTAB30%H2O2-M.1/17.3-S P Trap Primer | 15058484-03 |  |  | Apr/25/2023 | Apr/25/2023 | F15 | F15 WW51 LOR:CDM |  | 300 | BULK CHEMICAL DELIVERY | E-6447fb2238a60c6c1e0ae08c
Passed | I&C OAT | JE DUNN-ALOHA | 15061734-01-AL3-LIT261-16-10A | AL3-LIT261-16-10A | 15061734-01 |  |  | May/08/2023 | May/08/2023 | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-645512eb38a60c077815c9fd
Not Started | INST FAT | JE DUNN-ALOHA | 15061734-01-AL3-LIT261-16-10A | AL3-LIT261-16-10A | 15061734-01 | Apr/18/2023 | Apr/18/2023 |  |  | AL3 | F15 WW05 AWN Lift Station RELO |  | 261 | WASTE | E-645512eb38a60c077815c9fd
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-AIT55-160-4 | AIT55-160-4 UPW Makeup RO Unit 160 Feed Turbidity 0-2 NTU SCADA | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900207698e89e0
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-AIT55-160-4 | AIT55-160-4 UPW Makeup RO Unit 160 Feed Turbidity 0-2 NTU SCADA | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900207698e89e0
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-143 | UPW Makeup Pre-RO Prefilters 143: Housing Replacements | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900273618e89ea
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-143 | UPW Makeup Pre-RO Prefilters 143: Housing Replacements | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900273618e89ea
Not Started | PROC CC | JE DUNN-ALOHA | 15061938-01-F15-FL-55-143 | UPW Makeup Pre-RO Prefilters 143: Housing Replacements | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900273618e89ea
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-143 | UPW Makeup Pre-RO Prefilters 143: Housing Replacements | 15061938-01 | Oct/26/2023 | Oct/26/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900273618e89ea
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-AIT241-1 | AIT-241-1 Makeup RO Feed Chlorine Analyzer 0-5 ppm SCADA | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90025aca8e89e1
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-AIT241-1 | AIT-241-1 Makeup RO Feed Chlorine Analyzer 0-5 ppm SCADA | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90025aca8e89e1
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-PCV245-0-02B | Pressure Control Valve | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900255c88e89ef
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-PCV245-0-02B | Pressure Control Valve | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900255c88e89ef
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-FIT245-0-02A | Flow Indicating Transmitter | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002fbb68e89ed
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-FIT245-0-02A | Flow Indicating Transmitter | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002fbb68e89ed
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-142 | UPW Makeup Pre-RO Prefilters 142: Housing Replacements | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002599c8e89e9
Not Started | PROC CC | JE DUNN-ALOHA | 15061938-01-F15-FL-55-142 | UPW Makeup Pre-RO Prefilters 142: Housing Replacements | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002599c8e89e9
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-142 | UPW Makeup Pre-RO Prefilters 142: Housing Replacements | 15061938-01 | Oct/26/2023 | Oct/26/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002599c8e89e9
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-142 | UPW Makeup Pre-RO Prefilters 142: Housing Replacements | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002599c8e89e9
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-141 | UPW Makeup Pre-RO Prefilters 141: Housing Replacements | 15061938-01 | Oct/26/2023 | Oct/26/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90023f138e89e8
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-141 | UPW Makeup Pre-RO Prefilters 141: Housing Replacements | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90023f138e89e8
Not Started | PROC CC | JE DUNN-ALOHA | 15061938-01-F15-FL-55-141 | UPW Makeup Pre-RO Prefilters 141: Housing Replacements | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90023f138e89e8
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-F15-FL-55-141 | UPW Makeup Pre-RO Prefilters 141: Housing Replacements | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90023f138e89e8
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061938-01-F15-HX-55-121 | UPW Makeup RO Pre-Heat Heat Exchanger: New 58-Plate Pack and all new gaskets | 15061938-01 | Oct/26/2023 | Oct/26/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90027b508e89de
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061938-01-F15-HX-55-121 | UPW Makeup RO Pre-Heat Heat Exchanger: New 58-Plate Pack and all new gaskets | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90027b508e89de
Not Started | PROC CC | JE DUNN-ALOHA | 15061938-01-F15-HX-55-121 | UPW Makeup RO Pre-Heat Heat Exchanger: New 58-Plate Pack and all new gaskets | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90027b508e89de
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-F15-HX-55-121 | UPW Makeup RO Pre-Heat Heat Exchanger: New 58-Plate Pack and all new gaskets | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90027b508e89de
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-PDIT55-140-1 | Instrument Re-wire | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90025bd48e89e2
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-PDIT55-140-1 | Instrument Re-wire | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90025bd48e89e2
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-PIT245-0-02A | Pressure Indicating Transmitter | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002880c8e89eb
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-PIT245-0-02A | Pressure Indicating Transmitter | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002880c8e89eb
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-PIT55-140-1 | Instrument Re-wire | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90021a328e89e3
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-PIT55-140-1 | Instrument Re-wire | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90021a328e89e3
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061938-01-AIT55-160-05 | Instrument Re-wire | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020b2d8e89e5
Not Started | I&C CC | JE DUNN-ALOHA | 15061938-01-AIT55-160-05 | Instrument Re-wire | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020b2d8e89e5
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-AIT55-160-05 | Instrument Re-wire | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020b2d8e89e5
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061938-01-AIT55-160-05 | Instrument Re-wire | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020b2d8e89e5
Not Started | PROC CC | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | I&C CC | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | I&C DV | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/26/2023 | Oct/26/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/23/2023 | Nov/22/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15061938-01-F15-241UPW-Ethernet Rewire | Header | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90020de88e89e7
Not Started | MECH W CC | JE DUNN-ALOHA | 15061938-01-F15-CSA-UPW Upgrade-Filter Platform | Platform Rebuild | 15061938-01 |  |  |  |  | F15 | F15 WW51 : UPW Upgrades |  | RR | ROOM/AREA/BAY-READY | E-645baf737d90024f0b8e89e6
Not Started | STRUCT DV | JE DUNN-ALOHA | 15061938-01-F15-CSA-UPW Upgrade-Filter Platform | Platform Rebuild | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | RR | ROOM/AREA/BAY-READY | E-645baf737d90024f0b8e89e6
Not Started | STRUCT CC | JE DUNN-ALOHA | 15061938-01-F15-CSA-UPW Upgrade-Filter Platform | Platform Rebuild | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | RR | ROOM/AREA/BAY-READY | E-645baf737d90024f0b8e89e6
Not Started | RR CC/GT | JE DUNN-ALOHA | 15061938-01-F15-CSA-UPW Upgrade-Filter Platform | Platform Rebuild | 15061938-01 | Oct/26/2023 | Oct/26/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | RR | ROOM/AREA/BAY-READY | E-645baf737d90024f0b8e89e6
Not Started | EHS | JE DUNN-ALOHA | 15061938-01-F15-CSA-UPW Upgrade-Filter Platform | Platform Rebuild | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | RR | ROOM/AREA/BAY-READY | E-645baf737d90024f0b8e89e6
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-F15-CSA-UPW Upgrade-Filter Platform | Platform Rebuild | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | RR | ROOM/AREA/BAY-READY | E-645baf737d90024f0b8e89e6
Not Started | RR OA/BT | JE DUNN-ALOHA | 15061938-01-F15-CSA-UPW Upgrade-Filter Platform | Platform Rebuild | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | RR | ROOM/AREA/BAY-READY | E-645baf737d90024f0b8e89e6
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-CIT55-160-02 | Instrument Re-wire | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900255e28e89e4
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061938-01-CIT55-160-02 | Instrument Re-wire | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900255e28e89e4
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061938-01-CIT55-160-02 | Instrument Re-wire | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900255e28e89e4
Not Started | I&C CC | JE DUNN-ALOHA | 15061938-01-CIT55-160-02 | Instrument Re-wire | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900255e28e89e4
Not Started | PROC CC | JE DUNN-ALOHA | 15061938-01-F15-245UPW-Monitoring Tubing | F15-245UPW-Monitoring Tubing | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90024f838e89df
Not Started | I&C DV | JE DUNN-ALOHA | 15061938-01-F15-245UPW-Monitoring Tubing | F15-245UPW-Monitoring Tubing | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90024f838e89df
Not Started | FAT | JE DUNN-ALOHA | 15061938-01-F15-245UPW-Monitoring Tubing | F15-245UPW-Monitoring Tubing | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90024f838e89df
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061938-01-F15-245UPW-Monitoring Tubing | F15-245UPW-Monitoring Tubing | 15061938-01 | Oct/27/2023 | Nov/28/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90024f838e89df
Not Started | I&C CC | JE DUNN-ALOHA | 15061938-01-F15-245UPW-Monitoring Tubing | F15-245UPW-Monitoring Tubing | 15061938-01 | Oct/19/2023 | Oct/19/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90024f838e89df
Not Started | PROC DV | JE DUNN-ALOHA | 15061938-01-F15-245UPW-Monitoring Tubing | F15-245UPW-Monitoring Tubing | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90024f838e89df
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061938-01-F15-245UPW-Monitoring Tubing | F15-245UPW-Monitoring Tubing | 15061938-01 | Oct/26/2023 | Oct/26/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90024f838e89df
Not Started | EHS | JE DUNN-ALOHA | 15061938-01-F15-245UPW-Monitoring Tubing | F15-245UPW-Monitoring Tubing | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d90024f838e89df
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-PIT245-0-02B | Pressure Indicating Transmitter | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900269e38e89ec
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-PIT245-0-02B | Pressure Indicating Transmitter | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d900269e38e89ec
Not Started | I&C OAT | JE DUNN-ALOHA | 15061938-01-F15-PCV245-0-02A | Pressure Control Valve | 15061938-01 | Oct/13/2023 | Oct/13/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002151c8e89ee
Not Started | INST FAT | JE DUNN-ALOHA | 15061938-01-F15-PCV245-0-02A | Pressure Control Valve | 15061938-01 | Oct/20/2023 | Oct/20/2023 |  |  | F15 | F15 WW51 : UPW Upgrades |  | 241 | UPW | E-645baf737d9002151c8e89ee
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-1D1M18B | Distribution Panel | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f56cded64f6
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-1D1M18B | Distribution Panel | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f56cded64f6
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-1D1M18B | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f56cded64f6
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-1D1M18B | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f56cded64f6
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-1D1K18A | Distribution Panel | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fbf25ed64f5
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-1D1K18A | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fbf25ed64f5
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-1D1K18A | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fbf25ed64f5
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-1D1K18A | Distribution Panel | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fbf25ed64f5
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-1D1U16C | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f7104ed64f8
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-1D1U16C | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f7104ed64f8
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-1D1U16C | Distribution Panel | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f7104ed64f8
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-1D1U16C | Distribution Panel | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f7104ed64f8
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-1D1G14A | Distribution Panel | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fea8fed64f1
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-1D1G14A | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fea8fed64f1
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-1D1G14A | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fea8fed64f1
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-1D1G14A | Distribution Panel | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fea8fed64f1
Not Started | FAT | JE DUNN-ALOHA | 15061902-01-CB-1D1G14A | Circuit Breaker | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fe78eed64fc
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-CB-1D1G14A | Circuit Breaker | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fe78eed64fc
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-CB-1D1G14A | Circuit Breaker | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fe78eed64fc
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-CB-1D1G14A | Circuit Breaker | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fe78eed64fc
Not Started | ELECT DV | JE DUNN-ALOHA | 15061902-01-CB-1D1G14A | Circuit Breaker | 15061902-01 | Sep/09/2024 | Sep/09/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fe78eed64fc
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-CB-1D1G14A | Circuit Breaker | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fe78eed64fc
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-1T0R15A | K4 Transformer | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fa5e1ed64fb
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-1T0R15A | K4 Transformer | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fa5e1ed64fb
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-1T0R15A | K4 Transformer | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fa5e1ed64fb
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-1T0R15A | K4 Transformer | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fa5e1ed64fb
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-1T0J17A | K4 Transformer | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f489aed64fa
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-1T0J17A | K4 Transformer | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f489aed64fa
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-1T0J17A | K4 Transformer | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f489aed64fa
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-1T0J17A | K4 Transformer | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f489aed64fa
Not Started | ELECT DV | JE DUNN-ALOHA | 15061902-01-CB-1T0R15A | Circuit Breaker | 15061902-01 | Sep/09/2024 | Sep/09/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f499fed64f4
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-CB-1T0R15A | Circuit Breaker | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f499fed64f4
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-CB-1T0R15A | Circuit Breaker | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f499fed64f4
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-CB-1T0R15A | Circuit Breaker | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f499fed64f4
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-CB-1T0R15A | Circuit Breaker | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f499fed64f4
Not Started | FAT | JE DUNN-ALOHA | 15061902-01-CB-1T0R15A | Circuit Breaker | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f499fed64f4
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-1T0J16A | K4 Transformer | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fbae1ed64f9
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-1T0J16A | K4 Transformer | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fbae1ed64f9
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-1T0J16A | K4 Transformer | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fbae1ed64f9
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-1T0J16A | K4 Transformer | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30fbae1ed64f9
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-1D1R12D | Distribution Panel | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f8009ed64f7
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-1D1R12D | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f8009ed64f7
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-1D1R12D | Distribution Panel | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f8009ed64f7
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-1D1R12D | Distribution Panel | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f8009ed64f7
Not Started | ELECT DV | JE DUNN-ALOHA | 15061902-01-CB-1T0J17A | Circuit Breaker | 15061902-01 | Sep/09/2024 | Sep/09/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f500aed64f3
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-CB-1T0J17A | Circuit Breaker | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f500aed64f3
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-CB-1T0J17A | Circuit Breaker | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f500aed64f3
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-CB-1T0J17A | Circuit Breaker | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f500aed64f3
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-CB-1T0J17A | Circuit Breaker | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f500aed64f3
Not Started | FAT | JE DUNN-ALOHA | 15061902-01-CB-1T0J17A | Circuit Breaker | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f500aed64f3
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15061902-01-CB-1T0J16A | Circuit Breaker | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f006ded64f2
Not Started | ELECT CC | JE DUNN-ALOHA | 15061902-01-CB-1T0J16A | Circuit Breaker | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f006ded64f2
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15061902-01-CB-1T0J16A | Circuit Breaker | 15061902-01 | Sep/13/2024 | Sep/13/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f006ded64f2
Not Started | FAT | JE DUNN-ALOHA | 15061902-01-CB-1T0J16A | Circuit Breaker | 15061902-01 | Sep/16/2024 | Oct/03/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f006ded64f2
Not Started | ELECT DV | JE DUNN-ALOHA | 15061902-01-CB-1T0J16A | Circuit Breaker | 15061902-01 | Sep/09/2024 | Sep/09/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f006ded64f2
Not Started | ELECT OAT | JE DUNN-ALOHA | 15061902-01-CB-1T0J16A | Circuit Breaker | 15061902-01 | Sep/06/2024 | Sep/06/2024 |  |  | F15 | DST Enabling: Electrical Cluster |  | 603 | ELECTRICAL | E-645d455920f30f006ded64f2
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Break Room | AS1 Break Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848843b935d4484
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Bathrooms | AS1 Bathroom CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848840c665d4482
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-BCR Room | New Guard Shack | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842bd35d4483
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-LINK Exterior Shell | AS1 LINK Exterior CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842d845d447b
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-LINK Exterior Shell | AS1 LINK Exterior CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842d845d447b
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-LINK Exterior Shell | AS1 LINK Exterior CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842d845d447b
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-LINK Exterior Shell | AS1 LINK Exterior CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842d845d447b
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-LINK Exterior Shell | AS1 LINK Exterior CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842d845d447b
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-LINK Exterior Shell | AS1 LINK Exterior CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842d845d447b
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-LINK Exterior Shell | AS1 LINK Exterior CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842d845d447b
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-LINK Exterior Shell | AS1 LINK Exterior CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848842d845d447b
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | LSS OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Interior | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d255d447f
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-SCR Room | AS1 SCR Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884cee85d447d
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/15/2024 | Feb/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | LSS OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Elevator-149 | New Elevator | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d584884c5105d4486
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | LSS OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR- Building Exterior Shell | AS1 Exterior Shell CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488461f25d4481
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-LINK Interior | New Link CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488403595d4480
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Electrical Room | AS1 Electrical Room CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480555d4485
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Mezanine | AS1 Mezanine CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488467bc5d4487
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Pump Room | AS1 Pump CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d58488480395d447c
Not Started | ARCH CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | RR CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/15/2024 | Mar/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | RR OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/18/2024 | Apr/15/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | ARCH DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | STRUCT CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | TELE DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | STRUCT DV | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | TELE CC | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/08/2024 | Mar/08/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-RR-Stairway 146 | AS1 Stairway CSA | 15054721-01 | Mar/11/2024 | Mar/11/2024 |  |  | AS1 | AS1 Support Building |  | RR | ROOM/AREA/BAY-READY | E-6463ed2d5848841d735d447e
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-3-40 | MINI DX SPLIT EVAPORATOR UNIT-SCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bac6d86f021
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-2-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b312a86f024
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-1-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b82c286f022
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-FIT104-2-10A | GAS INLET FLOW INDICATING TRANSMITTER FOR AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b8cc686f071
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-FIT104-2-10A | GAS INLET FLOW INDICATING TRANSMITTER FOR AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b8cc686f071
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1T1A6A | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b97de86f053
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1T1A6A | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b97de86f053
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1T1A6A | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b97de86f053
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1T1A6A | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b97de86f053
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-TI104-2-00A | AS1 EAST SIDE WAREHOUSE AVERAGE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b480d86f01c
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-TI104-2-00A | AS1 EAST SIDE WAREHOUSE AVERAGE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b480d86f01c
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-2-00 | EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b820986f034
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-171SAN- Drain Piping | Sanitary Drain System | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 171 | WASTE | E-647605040d6f4b1aac86f03d
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-171SAN- Drain Piping | Sanitary Drain System | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 171 | WASTE | E-647605040d6f4b1aac86f03d
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-171SAN- Drain Piping | Sanitary Drain System | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 171 | WASTE | E-647605040d6f4b1aac86f03d
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-171SAN- Drain Piping | Sanitary Drain System | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 171 | WASTE | E-647605040d6f4b1aac86f03d
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-171SAN- Drain Piping | Sanitary Drain System | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 171 | WASTE | E-647605040d6f4b1aac86f03d
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-002 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b7a3786f06e
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-002 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b7a3786f06e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-002 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b7a3786f06e
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-002 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b7a3786f06e
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-002 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b7a3786f06e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-002 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b7a3786f06e
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-002 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b7a3786f06e
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-002 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b7a3786f06e
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-9,11 | ARU104-2-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4bf01f86f01e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-9,11 | ARU104-2-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4bf01f86f01e
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-9,11 | ARU104-2-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4bf01f86f01e
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-9,11 | ARU104-2-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4bf01f86f01e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-9,11 | ARU104-2-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4bf01f86f01e
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1D1A6C | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b25bb86f049
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1D1A6C | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b25bb86f049
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1D1A6C | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b25bb86f049
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1D1A6C | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b25bb86f049
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 MBUS-Card Install | New MOD BUS Card | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bb7d486f064
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 MBUS-Card Install | New MOD BUS Card | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bb7d486f064
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 MBUS-Card Install | New MOD BUS Card | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bb7d486f064
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 MBUS-Card Install | New MOD BUS Card | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bb7d486f064
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-LCP272-1-00 | LOCAL CONTROL PANEL WITH HOA SWITCH FOR ELEVATOR SUMP PUMP CONTROL | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4badb886f046
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-LCP272-1-00 | LOCAL CONTROL PANEL WITH HOA SWITCH FOR ELEVATOR SUMP PUMP CONTROL | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4badb886f046
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-LCP272-1-00 | LOCAL CONTROL PANEL WITH HOA SWITCH FOR ELEVATOR SUMP PUMP CONTROL | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4badb886f046
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-LCP272-1-00 | LOCAL CONTROL PANEL WITH HOA SWITCH FOR ELEVATOR SUMP PUMP CONTROL | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4badb886f046
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-LCP272-1-00 | LOCAL CONTROL PANEL WITH HOA SWITCH FOR ELEVATOR SUMP PUMP CONTROL | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4badb886f046
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-LCP272-1-00 | LOCAL CONTROL PANEL WITH HOA SWITCH FOR ELEVATOR SUMP PUMP CONTROL | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4badb886f046
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-LCP272-1-00 | LOCAL CONTROL PANEL WITH HOA SWITCH FOR ELEVATOR SUMP PUMP CONTROL | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4badb886f046
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-LCP272-1-00 | LOCAL CONTROL PANEL WITH HOA SWITCH FOR ELEVATOR SUMP PUMP CONTROL | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4badb886f046
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1R1A6D | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b341d86f04f
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1R1A6D | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b341d86f04f
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1R1A6D | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b341d86f04f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1R1A6D | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b341d86f04f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-1,3 | Link Condensate Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b136286f028
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-1,3 | Link Condensate Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b136286f028
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-1,3 | Link Condensate Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b136286f028
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-1,3 | Link Condensate Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b136286f028
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-1,3 | Link Condensate Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b136286f028
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-A7-002 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bd75586f06c
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-A7-002 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bd75586f06c
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-A7-002 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bd75586f06c
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-A7-002 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/15/2024 | Feb/15/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bd75586f06c
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-A7-002 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bd75586f06c
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-2-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4bb28e86f02d
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-TET104-0-00D | TEMPERATURE TRANSMITTER MONITORING WAREHOUSE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b111c86f045
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-TET104-0-00D | TEMPERATURE TRANSMITTER MONITORING WAREHOUSE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b111c86f045
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-BDA-1-H2-004 | RADIO BI-DIRECTIONAL AMPLIFIER | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b986986f06a
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-BDA-1-H2-004 | RADIO BI-DIRECTIONAL AMPLIFIER | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b986986f06a
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-BDA-1-H2-004 | RADIO BI-DIRECTIONAL AMPLIFIER | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b986986f06a
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-BDA-1-H2-004 | RADIO BI-DIRECTIONAL AMPLIFIER | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b986986f06a
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-BDA-1-H2-004 | RADIO BI-DIRECTIONAL AMPLIFIER | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b986986f06a
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-BDA-1-H2-004 | RADIO BI-DIRECTIONAL AMPLIFIER | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b986986f06a
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-BDA-1-H2-004 | RADIO BI-DIRECTIONAL AMPLIFIER | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b986986f06a
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-BDA-1-H2-004 | RADIO BI-DIRECTIONAL AMPLIFIER | 15054721-01 | Feb/15/2024 | Feb/15/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b986986f06a
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-FIT104-1-10A | GAS INLET FLOW INDICATING TRANSMITTER FOR AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4ba25686f02f
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-FIT104-1-10A | GAS INLET FLOW INDICATING TRANSMITTER FOR AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4ba25686f02f
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-SSH708-01 | New Safety Shower | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 708 | WASTE | E-647605040d6f4bc9df86f065
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-SSH708-01 | New Safety Shower | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 708 | WASTE | E-647605040d6f4bc9df86f065
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-SSH708-01 | New Safety Shower | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 708 | WASTE | E-647605040d6f4bc9df86f065
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-SSH708-01 | New Safety Shower | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 708 | WASTE | E-647605040d6f4bc9df86f065
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-SSH708-01 | New Safety Shower | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 708 | WASTE | E-647605040d6f4bc9df86f065
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-SSH708-01 | New Safety Shower | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 708 | WASTE | E-647605040d6f4bc9df86f065
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-SSH708-01 | New Safety Shower | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 708 | WASTE | E-647605040d6f4bc9df86f065
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-SSH708-01 | New Safety Shower | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 708 | WASTE | E-647605040d6f4bc9df86f065
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1R1H1A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b467f86f051
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1R1H1A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b467f86f051
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1R1H1A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b467f86f051
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1R1H1A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b467f86f051
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1T1A6C | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4bf11786f055
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1T1A6C | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4bf11786f055
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1T1A6C | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4bf11786f055
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1T1A6C | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4bf11786f055
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | FMS | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-02-00 | AS1-ARU104-2-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b09db86f062
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 604 | ELECTRICAL | E-647605040d6f4b3b2786f056
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 604 | ELECTRICAL | E-647605040d6f4b3b2786f056
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 604 | ELECTRICAL | E-647605040d6f4b3b2786f056
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 604 | ELECTRICAL | E-647605040d6f4b3b2786f056
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-TET104-0-00B | TEMPERATURE TRANSMITTER MONITORING WAREHOUSE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4ba5ba86f03a
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-TET104-0-00B | TEMPERATURE TRANSMITTER MONITORING WAREHOUSE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4ba5ba86f03a
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1R1A6B | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b8be886f04d
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1R1A6B | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b8be886f04d
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1R1A6B | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b8be886f04d
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1R1A6B | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b8be886f04d
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-2-40 | MINI DX SPLIT EVAPORATOR UNIT-ELECT Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b1c9986f020
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-1-40 | MINI DX SPLIT EVAPORATOR UNIT-BCR Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b786886f01f
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-115HW-Piping | Heating Water Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 115 | MECHANICAL WET | E-647605040d6f4bf35986f032
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-115HW-Piping | Heating Water Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 115 | MECHANICAL WET | E-647605040d6f4bf35986f032
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-115HW-Piping | Heating Water Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 115 | MECHANICAL WET | E-647605040d6f4bf35986f032
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-115HW-Piping | Heating Water Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 115 | MECHANICAL WET | E-647605040d6f4bf35986f032
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-115HW-Piping | Heating Water Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 115 | MECHANICAL WET | E-647605040d6f4bf35986f032
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-UH105-1-20 | UNIT HEATER-Pump Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b566886f027
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-OIT650-XX-XX | Operator Interface Terminal (Cabinet) | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b7ba486f063
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-OIT650-XX-XX | Operator Interface Terminal (Cabinet) | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b7ba486f063
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-OIT650-XX-XX | Operator Interface Terminal (Cabinet) | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b7ba486f063
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-OIT650-XX-XX | Operator Interface Terminal (Cabinet) | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b7ba486f063
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-OIT650-XX-XX | Operator Interface Terminal (Cabinet) | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b7ba486f063
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-OIT650-XX-XX | Operator Interface Terminal (Cabinet) | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b7ba486f063
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-OIT650-XX-XX | Operator Interface Terminal (Cabinet) | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b7ba486f063
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-OIT650-XX-XX | Operator Interface Terminal (Cabinet) | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b7ba486f063
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-1-00 | Atrium-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b34c086f033
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-CR131-3-00A | AS1 BATTERY CHARGING STATION STATUS FAN STATUS EF131-3-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b851b86f038
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-CR131-3-00A | AS1 BATTERY CHARGING STATION STATUS FAN STATUS EF131-3-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b851b86f038
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | FMS | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-501-00 | PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf78886f060
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-162NG-Piping | Natural Gas Piping To ARU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 162 | MECHANICAL MISC | E-647605040d6f4bb39f86f03c
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-162NG-Piping | Natural Gas Piping To ARU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 162 | MECHANICAL MISC | E-647605040d6f4bb39f86f03c
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-162NG-Piping | Natural Gas Piping To ARU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 162 | MECHANICAL MISC | E-647605040d6f4bb39f86f03c
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-162NG-Piping | Natural Gas Piping To ARU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 162 | MECHANICAL MISC | E-647605040d6f4bb39f86f03c
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-162NG-Piping | Natural Gas Piping To ARU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 162 | MECHANICAL MISC | E-647605040d6f4bb39f86f03c
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-162NG-Piping | Natural Gas Piping To ARU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 162 | MECHANICAL MISC | E-647605040d6f4bb39f86f03c
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-LSHH272-1-00A | AS1 ELEVATOR SUMP DRAIN LEVEL HIGH HIGH | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b97d486f043
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-LSHH272-1-00A | AS1 ELEVATOR SUMP DRAIN LEVEL HIGH HIGH | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b97d486f043
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-EF131-3-00 | Battery Charging station-EXHAUST FAN | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4bf86c86f035
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-Duct Install | AS1-ACU105-1-40 Breack room/rest room duct | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b630486f029
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-Duct Install | AS1-ACU105-1-40 Breack room/rest room duct | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b630486f029
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-ACU105-Duct Install | AS1-ACU105-1-40 Breack room/rest room duct | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b630486f029
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-3-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b7c4c86f02e
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-EF131-4-00 | Fire Pump Room- Exhaust Fan | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b3dc786f036
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1T1A6B | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b78b986f054
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1T1A6B | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b78b986f054
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1T1A6B | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b78b986f054
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1T1A6B | DRY-TYPE TRANSFORMER | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b78b986f054
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1D1A6D | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b5b0686f04a
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1D1A6D | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b5b0686f04a
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1D1A6D | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b5b0686f04a
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1D1A6D | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b5b0686f04a
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-151DW-Piping S/R | Condenser Water Line | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 154 | MECHANICAL WET | E-647605040d6f4b99e386f03b
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-151DW-Piping S/R | Condenser Water Line | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 154 | MECHANICAL WET | E-647605040d6f4b99e386f03b
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-151DW-Piping S/R | Condenser Water Line | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 154 | MECHANICAL WET | E-647605040d6f4b99e386f03b
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-151DW-Piping S/R | Condenser Water Line | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 154 | MECHANICAL WET | E-647605040d6f4b99e386f03b
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-151DW-Piping S/R | Condenser Water Line | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 154 | MECHANICAL WET | E-647605040d6f4b99e386f03b
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | FMS | JE DUNN-ALOHA | 15054721-01-AS1-PLC650-401-01-00 | AS1-ARU104-1-00 PLC | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4bf7b686f061
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-HSI272-1-00A | AS1 ELEVATOR SUMP PUMP HOA AUTO STATUS | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b35a786f040
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-HSI272-1-00A | AS1 ELEVATOR SUMP PUMP HOA AUTO STATUS | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b35a786f040
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-TET105-1-10A | TEMPERATURE ELEMENT TRANSMITTER FOR MONITORING AIR IN BREAK ROOM | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bf08c86f02a
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-TET105-1-10A | TEMPERATURE ELEMENT TRANSMITTER FOR MONITORING AIR IN BREAK ROOM | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4bf08c86f02a
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-HP105-1-10 | DUCTED HP INDOOR UNIT- Break Room | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b0c9f86f025
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-HS272-1-00A | AS1 SUMP PUMP HAND SWITCH | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4bff3886f03f
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-HS272-1-00A | AS1 SUMP PUMP HAND SWITCH | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4bff3886f03f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-H2-001 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b6f3c86f06b
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-H2-001 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b6f3c86f06b
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-H2-001 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b6f3c86f06b
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-H2-001 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/15/2024 | Feb/15/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b6f3c86f06b
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-FDU-1-H2-001 | CCTV FIBER DISTRIBUTION UNIT | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b6f3c86f06b
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-SCP-0-0-04 | Security Control Panel: Guard Booth | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9c2586f070
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-SCP-0-0-04 | Security Control Panel: Guard Booth | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9c2586f070
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-SCP-0-0-04 | Security Control Panel: Guard Booth | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9c2586f070
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-SCP-0-0-04 | Security Control Panel: Guard Booth | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9c2586f070
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-0-0-04 | Security Control Panel: Guard Booth | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9c2586f070
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-0-0-04 | Security Control Panel: Guard Booth | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9c2586f070
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-0-0-04 | Security Control Panel: Guard Booth | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9c2586f070
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-0-0-04 | Security Control Panel: Guard Booth | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9c2586f070
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-YS104-1-10A | AS1 SMOKE DETECTION STATUS LSS FOR ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4bea0486f05b
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-YS104-1-10A | AS1 SMOKE DETECTION STATUS LSS FOR ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4bea0486f05b
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-LCP650-1-00 | AS1-SWU650-1-00 Stratix Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b3e4b86f05f
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-LCP650-1-00 | AS1-SWU650-1-00 Stratix Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b3e4b86f05f
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-LCP650-1-00 | AS1-SWU650-1-00 Stratix Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b3e4b86f05f
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-LCP650-1-00 | AS1-SWU650-1-00 Stratix Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b3e4b86f05f
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-LCP650-1-00 | AS1-SWU650-1-00 Stratix Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b3e4b86f05f
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-LCP650-1-00 | AS1-SWU650-1-00 Stratix Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b3e4b86f05f
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-LCP650-1-00 | AS1-SWU650-1-00 Stratix Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b3e4b86f05f
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-LCP650-1-00 | AS1-SWU650-1-00 Stratix Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b3e4b86f05f
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-SCP-A-A8-003 | Security Control Panel: SCR Room 111 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bc13986f06d
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-SCP-A-A8-003 | Security Control Panel: SCR Room 111 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bc13986f06d
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-A-A8-003 | Security Control Panel: SCR Room 111 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bc13986f06d
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-SCP-A-A8-003 | Security Control Panel: SCR Room 111 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bc13986f06d
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-A-A8-003 | Security Control Panel: SCR Room 111 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bc13986f06d
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-SCP-A-A8-003 | Security Control Panel: SCR Room 111 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bc13986f06d
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-A-A8-003 | Security Control Panel: SCR Room 111 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bc13986f06d
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-A-A8-003 | Security Control Panel: SCR Room 111 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4bc13986f06d
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-FDU650-1A-101 | FDU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b346c86f05e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-FDU650-1A-101 | FDU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b346c86f05e
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-FDU650-1A-101 | FDU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b346c86f05e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-FDU650-1A-101 | FDU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b346c86f05e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-FDU650-1A-100 | FDU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b4ad086f05d
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-FDU650-1A-100 | FDU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b4ad086f05d
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-FDU650-1A-100 | FDU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b4ad086f05d
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-FDU650-1A-100 | FDU | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b4ad086f05d
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-RBC-1-H2-003 | RADIO BATTERY CABINET | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b5e9e86f069
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-RBC-1-H2-003 | RADIO BATTERY CABINET | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b5e9e86f069
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RBC-1-H2-003 | RADIO BATTERY CABINET | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b5e9e86f069
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RBC-1-H2-003 | RADIO BATTERY CABINET | 15054721-01 | Feb/15/2024 | Feb/15/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b5e9e86f069
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RBC-1-H2-003 | RADIO BATTERY CABINET | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b5e9e86f069
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RBC-1-H2-003 | RADIO BATTERY CABINET | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b5e9e86f069
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RBC-1-H2-003 | RADIO BATTERY CABINET | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b5e9e86f069
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RBC-1-H2-003 | RADIO BATTERY CABINET | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b5e9e86f069
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-001 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b08c486f06f
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-001 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b08c486f06f
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-001 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b08c486f06f
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-001 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b08c486f06f
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-001 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b08c486f06f
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-001 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b08c486f06f
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-001 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b08c486f06f
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-SCP-1-H2-001 | Security Control Panel: BCR Room 140 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b08c486f06f
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-YS104-2-10A | AS1 SMOKE DETECTION STATUS LSS FOR ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b075e86f01d
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-YS104-2-10A | AS1 SMOKE DETECTION STATUS LSS FOR ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b075e86f01d
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-ARU104-1-00 | AIR ROTATING UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b600c86f019
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-UAS1R1B7A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 605 | ELECTRICAL | E-647605040d6f4b35fa86f057
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-UAS1R1B7A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 605 | ELECTRICAL | E-647605040d6f4b35fa86f057
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-UAS1R1B7A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 605 | ELECTRICAL | E-647605040d6f4b35fa86f057
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-UAS1R1B7A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 605 | ELECTRICAL | E-647605040d6f4b35fa86f057
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-CHW (R/S)-Piping | Chilled water supply and return piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 111 | MECHANICAL WET | E-647605040d6f4b793f86f031
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-CHW (R/S)-Piping | Chilled water supply and return piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 111 | MECHANICAL WET | E-647605040d6f4b793f86f031
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-CHW (R/S)-Piping | Chilled water supply and return piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 111 | MECHANICAL WET | E-647605040d6f4b793f86f031
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-CHW (R/S)-Piping | Chilled water supply and return piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 111 | MECHANICAL WET | E-647605040d6f4b793f86f031
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-CHW (R/S)-Piping | Chilled water supply and return piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 111 | MECHANICAL WET | E-647605040d6f4b793f86f031
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1R1H1B | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b619586f052
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1R1H1B | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b619586f052
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1R1H1B | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b619586f052
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1R1H1B | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b619586f052
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1D1A6A | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b41b586f047
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1D1A6A | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b41b586f047
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1D1A6A | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b41b586f047
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1D1A6A | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b41b586f047
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-TET104-0-00A | TEMPERATURE TRANSMITTER MONITORING WAREHOUSE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b736886f01a
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-TET104-0-00A | TEMPERATURE TRANSMITTER MONITORING WAREHOUSE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b736886f01a
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-5,7 | ARU104-1-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b978a86f066
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-5,7 | ARU104-1-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b978a86f066
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-5,7 | ARU104-1-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b978a86f066
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-5,7 | ARU104-1-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b978a86f066
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-XAS1R1A6A-5,7 | ARU104-1-00 Heat Trace | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b978a86f066
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RRU-H2-002 | REMOTE RADIO UNIT | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b0bce86f068
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RRU-H2-002 | REMOTE RADIO UNIT | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b0bce86f068
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-RRU-H2-002 | REMOTE RADIO UNIT | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b0bce86f068
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RRU-H2-002 | REMOTE RADIO UNIT | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b0bce86f068
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RRU-H2-002 | REMOTE RADIO UNIT | 15054721-01 | Feb/15/2024 | Feb/15/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b0bce86f068
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-RRU-H2-002 | REMOTE RADIO UNIT | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b0bce86f068
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RRU-H2-002 | REMOTE RADIO UNIT | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b0bce86f068
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RRU-H2-002 | REMOTE RADIO UNIT | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b0bce86f068
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-PMP272-1-00 | Elevator Sump pump | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b2cac86f03e
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-PMP272-1-00 | Elevator Sump pump | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b2cac86f03e
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-PMP272-1-00 | Elevator Sump pump | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b2cac86f03e
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-PMP272-1-00 | Elevator Sump pump | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b2cac86f03e
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-PMP272-1-00 | Elevator Sump pump | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b2cac86f03e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-PMP272-1-00 | Elevator Sump pump | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b2cac86f03e
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-PMP272-1-00 | Elevator Sump pump | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b2cac86f03e
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-PMP272-1-00 | Elevator Sump pump | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b2cac86f03e
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-153FP-Sprinkler Piping | Fire Sprinkler Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 153 | FIRE PROTECTION/SSH | E-647605040d6f4b07e186f039
Not Started | MECH W CC | JE DUNN-ALOHA | 15054721-01-AS1-153FP-Sprinkler Piping | Fire Sprinkler Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 153 | FIRE PROTECTION/SSH | E-647605040d6f4b07e186f039
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-153FP-Sprinkler Piping | Fire Sprinkler Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 153 | FIRE PROTECTION/SSH | E-647605040d6f4b07e186f039
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-153FP-Sprinkler Piping | Fire Sprinkler Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 153 | FIRE PROTECTION/SSH | E-647605040d6f4b07e186f039
Not Started | MECH W DV | JE DUNN-ALOHA | 15054721-01-AS1-153FP-Sprinkler Piping | Fire Sprinkler Piping | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 153 | FIRE PROTECTION/SSH | E-647605040d6f4b07e186f039
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-HP105-2-10 | MINI HP EVAPORATOR UNIT- Elevator | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b955d86f026
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-4-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b1bfa86f030
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1R1A6C | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b23e186f04e
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1R1A6C | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b23e186f04e
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1R1A6C | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b23e186f04e
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1R1A6C | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b23e186f04e
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-UAS1R1H1A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 605 | ELECTRICAL | E-647605040d6f4b374e86f058
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-UAS1R1H1A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 605 | ELECTRICAL | E-647605040d6f4b374e86f058
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-UAS1R1H1A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 605 | ELECTRICAL | E-647605040d6f4b374e86f058
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-UAS1R1H1A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 605 | ELECTRICAL | E-647605040d6f4b374e86f058
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-LSH272-1-00A | AS1 ELEVATOR SUMP DRAIN LEVEL HIGH | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b249d86f042
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-LSH272-1-00A | AS1 ELEVATOR SUMP DRAIN LEVEL HIGH | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b249d86f042
Not Started | DIST CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-131EXGB-Main | Main Duct to EF131-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b35ac86f037
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-131EXGB-Main | Main Duct to EF131-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b35ac86f037
Not Started | DIST OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-131EXGB-Main | Main Duct to EF131-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 131 | MECHANICAL EXHAUST | E-647605040d6f4b35ac86f037
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-AC109-1-10 | Air Curtain | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 109 | MECHANICAL DRY | E-647605040d6f4b081c86f02c
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | LSS OAT | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-FAP-1-A7-01 | Fire Alarm Control Panel | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 630 | LIFE SAFETY SYSTEM | E-647605040d6f4bc27f86f059
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-TI104-1-00A | AS1 EAST SIDE WAREHOUSE AVERAGE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b1fad86f050
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-TI104-1-00A | AS1 EAST SIDE WAREHOUSE AVERAGE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b1fad86f050
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | EHS | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | PROC DV | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | EER Final Approval | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | MECH D DV | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | MECH D CC | JE DUNN-ALOHA | 15054721-01-AS1-FCU105-2-30 | LINK FAN COIL UNIT | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b6c9586f023
Not Started | FMS | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-1-00 | PLC for AS1-ARU104-1-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b512086f05a
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-LSL272-1-00A | AS1 ELEVATOR SUMP DRAIN LEVEL LOW | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4bc9a586f044
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-LSL272-1-00A | AS1 ELEVATOR SUMP DRAIN LEVEL LOW | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4bc9a586f044
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-TET104-0-00C | TEMPERATURE TRANSMITTER MONITORING WAREHOUSE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b786586f01b
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-TET104-0-00C | TEMPERATURE TRANSMITTER MONITORING WAREHOUSE TEMPERATURE | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 104 | MECHANICAL DRY | E-647605040d6f4b786586f01b
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-LS272-1-00A | ELEVATOR SUMP DRAIN LEVEL Switch | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b04ee86f041
Not Started | PROC CC | JE DUNN-ALOHA | 15054721-01-AS1-LS272-1-00A | ELEVATOR SUMP DRAIN LEVEL Switch | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b04ee86f041
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-LS272-1-00A | ELEVATOR SUMP DRAIN LEVEL Switch | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 272 | WASTE | E-647605040d6f4b04ee86f041
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1L1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b107386f04b
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1L1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b107386f04b
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1L1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b107386f04b
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1L1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b107386f04b
Not Started | I&C CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | I&C DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | SI CC (OTS3/RTL) | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | FMS | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-PLC104-2-00 | PLC for AS1-ARU104-2-00 | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 650 | FACILITIES MONITORING SYSTEM | E-647605040d6f4b27b086f05c
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1R1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b37aa86f04c
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1R1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b37aa86f04c
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1R1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b37aa86f04c
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1R1A6A | PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4b37aa86f04c
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1D1A6B | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4bffca86f048
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1D1A6B | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4bffca86f048
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1D1A6B | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4bffca86f048
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1D1A6B | DISTRIBUTION PANELBOARD | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 603 | ELECTRICAL | E-647605040d6f4bffca86f048
Not Started | LSS DV | JE DUNN-ALOHA | 15054721-01-AS1-RCP-1-H2-001 | RADIO COMMUNICATIONS PANEL | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9a6b86f067
Not Started | EQ OA/BT | JE DUNN-ALOHA | 15054721-01-AS1-RCP-1-H2-001 | RADIO COMMUNICATIONS PANEL | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9a6b86f067
Not Started | EQ CC/GT | JE DUNN-ALOHA | 15054721-01-AS1-RCP-1-H2-001 | RADIO COMMUNICATIONS PANEL | 15054721-01 | Feb/15/2024 | Feb/15/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9a6b86f067
Not Started | ELECT OAT | JE DUNN-ALOHA | 15054721-01-AS1-RCP-1-H2-001 | RADIO COMMUNICATIONS PANEL | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9a6b86f067
Not Started | ELECT DV | JE DUNN-ALOHA | 15054721-01-AS1-RCP-1-H2-001 | RADIO COMMUNICATIONS PANEL | 15054721-01 | Feb/09/2024 | Feb/09/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9a6b86f067
Not Started | LSS CC | JE DUNN-ALOHA | 15054721-01-AS1-RCP-1-H2-001 | RADIO COMMUNICATIONS PANEL | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9a6b86f067
Not Started | FAT | JE DUNN-ALOHA | 15054721-01-AS1-RCP-1-H2-001 | RADIO COMMUNICATIONS PANEL | 15054721-01 | Feb/16/2024 | Mar/18/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9a6b86f067
Not Started | ELECT CC | JE DUNN-ALOHA | 15054721-01-AS1-RCP-1-H2-001 | RADIO COMMUNICATIONS PANEL | 15054721-01 | Feb/08/2024 | Feb/08/2024 |  |  | AS1 | AS1 Support Building | Logistings And Support Building | SEC | SECURITY | E-647605040d6f4b9a6b86f067
Not Started | I&C OAT | JE DUNN-ALOHA | 15054721-01-AS1-TET105-1-20A | TEMPERATURE ELEMENT TRANSMITTER FOR MONITORING AIR IN PUMP ROOM | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b81d186f02b
Not Started | INST FAT | JE DUNN-ALOHA | 15054721-01-AS1-TET105-1-20A | TEMPERATURE ELEMENT TRANSMITTER FOR MONITORING AIR IN PUMP ROOM | 15054721-01 |  |  |  |  | AS1 | AS1 Support Building | Logistings And Support Building | 105 | MECHANICAL DRY | E-647605040d6f4b81d186f02b
Not Started | MECH W DV | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | ELECT CC | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | I&C CC | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | EQ CC/GT | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | FAT | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | EQ OA/BT | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
In Progress | MECH W CC | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  | Oct/10/2022 |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | SI CC (OTS3/RTL) | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
In Progress | EHS | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  | Oct/10/2022 |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | I&C DV | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | ELECT DV | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | ELECT OAT | Exto Troubleshoot | 1234-Test Equipment | Test | 1234 |  |  |  |  | AL3 |  |  | 101 | BULK CHEMICAL DELIVERY | E-7da94926ea14cc2468f12ad4843c965e50d14638
Not Started | ELECT CC | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Passed | MECH W DV | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  | Aug/20/2023 | Aug/20/2023 | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Not Started | SI CC (OTS3/RTL) | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Not Started | FAT | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Not Started | EQ CC/GT | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Not Started | EQ OA/BT | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Not Started | I&C CC | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Not Started | I&C DV | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Passed | MECH W CC | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  | Aug/20/2023 | Aug/21/2023 | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Not Started | EER Final Approval | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Not Started | EHS | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  |  |  | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Passed | ELECT OAT | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  | Aug/20/2023 | Aug/20/2023 | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Passed | ELECT DV | Exto Troubleshoot | 123-123-112 | abc | 123 |  |  | Aug/21/2023 | Aug/21/2023 | F15 |  |  | 135 | UPW | E-623c77ce82a1a6250c9cc4a6
Passed | MECH W DV | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  | Jul/13/2023 | Jul/13/2023 | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
In Progress | ELECT CC | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  | Jul/13/2023 |  | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Not Started | SI CC (OTS3/RTL) | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  |  |  | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Not Started | EQ OA/BT | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  |  |  | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Passed | ELECT OAT | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  | Jul/13/2023 | Jul/13/2023 | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Not Started | I&C CC | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  |  |  | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Not Started | EHS | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  |  |  | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Passed | MECH W CC | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  | Jul/13/2023 | Jul/13/2023 | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Not Started | EQ CC/GT | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  |  |  | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Not Started | FAT | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  |  |  | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Not Started | I&C DV | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  |  |  | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Passed | ELECT DV | Exto Troubleshoot | 123-TEST101 | abc | 123 |  |  | Jul/13/2023 | Jul/13/2023 | F15 |  |  | 111 | UPW | E-642c0cbdc87b6349e41db268
Passed | FAT | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 | Feb/01/2023 | Mar/15/2023 | Apr/21/2023 | Apr/21/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | EQ OA/BT | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 | Feb/01/2023 | Mar/15/2023 | May/02/2023 | May/02/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | ELECT DV | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 |  |  | Nov/15/2022 | Nov/15/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | EQ CC/GT | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 | Jan/23/2023 | Jan/26/2023 | Jan/31/2023 | Jan/31/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | ELECT OAT | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 |  |  | Nov/07/2022 | Nov/07/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | I&C CC | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | MECH W DV | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 |  |  | Nov/15/2022 | Nov/15/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | ELECT CC | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 | Jan/16/2023 | Jan/19/2023 | Nov/07/2022 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 |  |  | Dec/16/2022 | Dec/16/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | MECH W CC | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 | Jan/16/2023 | Jan/19/2023 | Nov/17/2022 | Jan/26/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | I&C DV | SKANSKA -SPGC | 15048266-ALC-PMP172-1-00 | 750 GPM PUMP | 15048266 |  |  | Nov/15/2022 | Nov/15/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a246efdfa98
Passed | FAT | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 | Feb/01/2023 | Feb/07/2023 | Feb/06/2023 | Feb/06/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | I&C CC | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 | Jan/05/2023 | Jan/10/2023 | Jan/23/2023 | Jan/23/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | EQ CC/GT | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 | Jan/12/2023 | Jan/17/2023 | Jan/30/2023 | Jan/31/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | EQ OA/BT | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 | Feb/01/2023 | Feb/08/2023 | Feb/09/2023 | Feb/09/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | ELECT OAT | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 |  |  | Nov/02/2022 | Nov/07/2022 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | I&C DV | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 |  |  | Nov/15/2022 | Nov/15/2022 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 |  |  | Dec/16/2022 | Dec/16/2022 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | INST FAT | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 | Jan/31/2023 | Feb/06/2023 | Feb/06/2023 | Feb/06/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | ELECT DV | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 |  |  | Nov/15/2022 | Nov/15/2022 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | ELECT CC | SKANSKA -SPGC | 15048266-ALC-RIO650-103-02 | LDRIO PANEL (OUTDOOR) | 15048266 | Jan/05/2023 | Jan/10/2023 | Jan/19/2023 | Jan/23/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-6286c38abe713a0c95fdfa8f
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QS172-1-00A | ALC East Parking Stormwater Lift Station Pump 1 Fault Status | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713ada16fdfa92
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-LAHH172-1-00A | ALC East Parking Stormwater Lift Station Wet Well Level Alarm High High | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a2bcffdfa95
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QS172-2-00A | ALC East Parking Stormwater Lift Station Pump 2 Fault Status | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a49cbfdfa93
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QS172-1-03D | ALC East Parking Stormwater Lift Station Interlock | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a1878fdfa9e
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QA172-1-03B | ALC East Parking Stormwater Treatment Skid Pump Alarm Fault | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a1dfafdfa9c
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QA172-1-03E | ALC East Parking Stormwater Treatment Skid Loss of Power | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713afd9bfdfa9f
Passed | ELECT CC | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | I&C DV | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 |  |  | Nov/15/2022 | Nov/15/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | EQ CC/GT | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 | Jan/23/2023 | Jan/26/2023 | Jan/31/2023 | Jan/31/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | FAT | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 | Feb/01/2023 | Mar/15/2023 | Apr/21/2023 | Apr/21/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | MECH W CC | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 | Jan/16/2023 | Jan/19/2023 | Nov/17/2022 | Jan/26/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | MECH W DV | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 |  |  | Nov/15/2022 | Nov/15/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | ELECT OAT | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 |  |  | Nov/07/2022 | Nov/07/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | ELECT DV | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 |  |  | Nov/15/2022 | Nov/15/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | I&C CC | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | EQ OA/BT | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 | Feb/01/2023 | Mar/15/2023 | May/02/2023 | May/02/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15048266-ALC-PMP172-2-00 | 750 GPM PUMP | 15048266 |  |  | Dec/16/2022 | Dec/16/2022 | F15 |  |  | 172 | WASTE | E-6286c38abe713a7faafdfa99
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QA172-1-03A | ALC East Parking Stormwater Treatment Skid Recirculation Time Out | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/23/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713a0184fdfa9b
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QA172-1-03C | ALC East Parking Stormwater Treatment Skid High Vault Alarm | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6286c38abe713ad17cfdfa9d
Passed | LSS DV | SKANSKA -SPGC | 15048266-ALC Cameras | CCTV equipment | 15048266 |  |  | Nov/29/2022 | Nov/29/2022 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631eb2e0dcc6510b9c92fe59
Passed | EQ CC/GT | SKANSKA -SPGC | 15048266-ALC Cameras | CCTV equipment | 15048266 |  |  | Dec/29/2022 | Dec/29/2022 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631eb2e0dcc6510b9c92fe59
Passed | EQ OA/BT | SKANSKA -SPGC | 15048266-ALC Cameras | CCTV equipment | 15048266 | Feb/01/2023 | Feb/17/2023 | Mar/02/2023 | Mar/02/2023 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631eb2e0dcc6510b9c92fe59
Passed | FAT | SKANSKA -SPGC | 15048266-ALC Cameras | CCTV equipment | 15048266 | Feb/01/2023 | Feb/17/2023 | Mar/02/2023 | Mar/02/2023 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631eb2e0dcc6510b9c92fe59
Passed | LSS CC | SKANSKA -SPGC | 15048266-ALC Cameras | CCTV equipment | 15048266 |  |  | Dec/15/2022 | Dec/15/2022 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631eb2e0dcc6510b9c92fe59
Passed | FAT | SKANSKA -SPGC | 15048266-ALC-Stormwater Treatment Door Switch | New Door Switch | 15048266 | Feb/02/2023 | Feb/17/2023 | Mar/02/2023 | Mar/02/2023 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631ebcaa1cb2a23b1240f2a9
Passed | EQ OA/BT | SKANSKA -SPGC | 15048266-ALC-Stormwater Treatment Door Switch | New Door Switch | 15048266 | Feb/02/2023 | Feb/17/2023 | Mar/02/2023 | Mar/02/2023 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631ebcaa1cb2a23b1240f2a9
Passed | EQ CC/GT | SKANSKA -SPGC | 15048266-ALC-Stormwater Treatment Door Switch | New Door Switch | 15048266 |  |  | Dec/29/2022 | Jan/03/2023 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631ebcaa1cb2a23b1240f2a9
Passed | LSS CC | SKANSKA -SPGC | 15048266-ALC-Stormwater Treatment Door Switch | New Door Switch | 15048266 |  |  | Dec/15/2022 | Dec/15/2022 | F15 |  |  | 630 | LIFE SAFETY SYSTEM | E-631ebcaa1cb2a23b1240f2a9
Passed | MECH W CC | SKANSKA -SPGC | 15048266-ALC-SKD172-1-03 | Vendor Skid | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/26/2023 | Jan/26/2023 | F15 |  |  | 172 | WASTE | E-6356ae658503ab2a68e40596
Passed | FAT | SKANSKA -SPGC | 15048266-ALC-SKD172-1-03 | Vendor Skid | 15048266 | Feb/01/2023 | Mar/15/2023 | Apr/21/2023 | Apr/21/2023 | F15 |  |  | 172 | WASTE | E-6356ae658503ab2a68e40596
Passed | ELECT OAT | SKANSKA -SPGC | 15048266-ALC-SKD172-1-03 | Vendor Skid | 15048266 |  |  | Nov/07/2022 | Nov/07/2022 | F15 |  |  | 172 | WASTE | E-6356ae658503ab2a68e40596
Passed | ELECT CC | SKANSKA -SPGC | 15048266-ALC-SKD172-1-03 | Vendor Skid | 15048266 | Jan/16/2023 | Jan/19/2023 | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-6356ae658503ab2a68e40596
Passed | EQ CC/GT | SKANSKA -SPGC | 15048266-ALC-SKD172-1-03 | Vendor Skid | 15048266 | Jan/23/2023 | Jan/26/2023 | Jan/31/2023 | Jan/31/2023 | F15 |  |  | 172 | WASTE | E-6356ae658503ab2a68e40596
Passed | EQ OA/BT | SKANSKA -SPGC | 15048266-ALC-SKD172-1-03 | Vendor Skid | 15048266 | Feb/01/2023 | Mar/15/2023 | May/02/2023 | May/02/2023 | F15 |  |  | 172 | WASTE | E-6356ae658503ab2a68e40596
Not Started | ELECT DV | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/21/2023 | Jun/30/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | I&C CC | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | ELECT CC | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | MECH D CC | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | PROC DV | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/21/2023 | Jun/30/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | EQ CC/GT | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/27/2023 | Jul/06/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | FAT | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jul/14/2023 | Jul/20/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | MECH D DV | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/21/2023 | Jun/30/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
In Progress | PROC CC | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 | Dec/13/2022 |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | EQ OA/BT | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jul/14/2023 | Jul/20/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Passed | ELECT OAT | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/01/2023 | Jun/08/2023 | May/23/2023 | May/23/2023 | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | I&C DV | SKANSKA -SPGC | 15053730-AL3-MAH101-1-10 | Cleanroom Makeup Air System | 15053730 | Jun/21/2023 | Jun/30/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e3e13437ee
Not Started | PROC CC | SKANSKA -SPGC | 15053730-AL3-XV101-1-02B | Cleanroom Makeup Air System | 15053730 | Jun/13/2023 | Jun/22/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e59c4b3437ef
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-XV101-1-02B | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e59c4b3437ef
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-FS101-1-02B | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5a2463437f2
Passed | PROC CC | SKANSKA -SPGC | 15053730-AL3-XV101-2-02B | Cleanroom Makeup Air System | 15053730 | Mar/27/2023 | Apr/04/2023 | Feb/28/2023 | Feb/28/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e57cf63437fe
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-XV101-2-02B | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/11/2023 | Mar/08/2023 | Mar/08/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e57cf63437fe
Passed | INST FAT | SKANSKA -SPGC | 15053730-AL3-LIT101-2-02A | Cleanroom Makeup Air System | 15053730 | Jun/02/2023 | Jun/09/2023 | May/11/2023 | May/11/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e50916343802
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-LIT101-2-02A | Cleanroom Makeup Air System | 15053730 | Mar/28/2023 | Apr/05/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e50916343802
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053730-AL3-NET101-1-11A | Cleanroom Makeup Air System | 15053730 | Aug/09/2023 | Aug/14/2023 | Mar/09/2023 | Mar/09/2023 | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e57994343803
Not Started | INST FAT | SKANSKA -SPGC | 15053730-AL3-NET101-1-11A | Cleanroom Makeup Air System | 15053730 | Jun/21/2023 | Jun/30/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e57994343803
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-NET101-1-11A | Cleanroom Makeup Air System | 15053730 | Jun/14/2023 | Jun/23/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e57994343803
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-HS101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5b5ac343806
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-IS101-1-02B | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5d996343808
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053730-AL3-AIT101-1-02A | Cleanroom Makeup Air System | 15053730 | Aug/10/2023 | Aug/15/2023 | Mar/09/2023 | Mar/09/2023 | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e528ba3437f0
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-AIT101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/14/2023 | Jun/23/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e528ba3437f0
Not Started | INST FAT | SKANSKA -SPGC | 15053730-AL3-AIT101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/21/2023 | Jun/30/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e528ba3437f0
Not Started | INST FAT | SKANSKA -SPGC | 15053730-AL3-LIT101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/21/2023 | Jun/30/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5c6313437f3
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-LIT101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/14/2023 | Jun/23/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5c6313437f3
Passed | ELECT CC | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/11/2023 | Mar/07/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | MECH D CC | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/11/2023 | Feb/28/2023 | Feb/28/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | EQ CC/GT | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Jun/08/2023 | Jun/15/2023 | Mar/10/2023 | May/01/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Not Started | FAT | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Jun/09/2023 | Jun/15/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | ELECT OAT | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/11/2023 | Mar/07/2023 | Mar/07/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Not Started | EQ OA/BT | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Jun/09/2023 | Jun/15/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | ELECT DV | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Apr/04/2023 | Apr/12/2023 | Mar/10/2023 | Mar/10/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | I&C DV | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Apr/04/2023 | Apr/12/2023 | Mar/10/2023 | Mar/10/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | PROC CC | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 |  |  | Dec/19/2022 | Dec/19/2022 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | PROC DV | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Apr/04/2023 | Apr/12/2023 | Mar/06/2023 | Mar/06/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | MECH D DV | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Apr/04/2023 | Apr/12/2023 | Mar/06/2023 | Mar/06/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | I&C CC | SKANSKA -SPGC | 15053730-AL3-MAH101-2-10 | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/11/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55eff3437f4
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-HSI101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e51bcf3437f8
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053730-AL3-LCP101-1-02A | Cleanroom Makeup Air System | 15053730 | Aug/16/2023 | Aug/21/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5195e3437f9
Not Started | I&C CC | SKANSKA -SPGC | 15053730-AL3-LCP101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5195e3437f9
Not Started | ELECT OAT | SKANSKA -SPGC | 15053730-AL3-LCP101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5195e3437f9
Not Started | FAT | SKANSKA -SPGC | 15053730-AL3-LCP101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/09/2023 | Jun/15/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5195e3437f9
Not Started | ELECT CC | SKANSKA -SPGC | 15053730-AL3-LCP101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5195e3437f9
Not Started | EQ CC/GT | SKANSKA -SPGC | 15053730-AL3-LCP101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/27/2023 | Jul/06/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5195e3437f9
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-LCP101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5195e3437f9
Not Started | EQ OA/BT | SKANSKA -SPGC | 15053730-AL3-LCP101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/09/2023 | Jun/15/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5195e3437f9
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-HS101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5654e3437fa
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-IS101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e508333437fb
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-IS101-2-02B | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e571003437fc
Not Started | INST FAT | SKANSKA -SPGC | 15053730-AL3-TET101-1-11A | Cleanroom Makeup Air System | 15053730 | Jun/21/2023 | Jun/30/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e58a3c343804
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053730-AL3-TET101-1-11A | Cleanroom Makeup Air System | 15053730 | Aug/10/2023 | Aug/15/2023 | Mar/09/2023 | Mar/09/2023 | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e58a3c343804
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-TET101-1-11A | Cleanroom Makeup Air System | 15053730 | Jun/14/2023 | Jun/23/2023 |  |  | AL3 | AL3 Humid Retrofit |  | 101 | MECHANICAL DRY | E-6390f9d52b21e58a3c343804
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-IS101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e507da343807
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-XV101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e505c1343809
Not Started | PROC CC | SKANSKA -SPGC | 15053730-AL3-XV101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/13/2023 | Jun/22/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e505c1343809
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-FS101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e55dfa3437f1
Not Started | EQ OA/BT | SKANSKA -SPGC | 15053730-AL3-LCP101-2-02A | Cleanroom Makeup Air System | 15053730 | Jun/09/2023 | Jun/15/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e500c23437f5
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-LCP101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e500c23437f5
Passed | ELECT OAT | SKANSKA -SPGC | 15053730-AL3-LCP101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/07/2023 | Mar/07/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e500c23437f5
Passed | ELECT CC | SKANSKA -SPGC | 15053730-AL3-LCP101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e500c23437f5
Not Started | FAT | SKANSKA -SPGC | 15053730-AL3-LCP101-2-02A | Cleanroom Makeup Air System | 15053730 | Jun/09/2023 | Jun/15/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e500c23437f5
Passed | I&C CC | SKANSKA -SPGC | 15053730-AL3-LCP101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e500c23437f5
Passed | EQ CC/GT | SKANSKA -SPGC | 15053730-AL3-LCP101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/10/2023 | Apr/17/2023 | Mar/10/2023 | Mar/10/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e500c23437f5
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053730-AL3-LCP101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/10/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e500c23437f5
Passed | INST FAT | SKANSKA -SPGC | 15053730-AL3-NET101-2-11A | Cleanroom Makeup Air System | 15053730 | Jun/02/2023 | Jun/09/2023 | May/11/2023 | May/11/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e570cf3437f6
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053730-AL3-NET101-2-11A | Cleanroom Makeup Air System | 15053730 | Mar/28/2023 | Apr/05/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e570cf3437f6
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-NET101-2-11A | Cleanroom Makeup Air System | 15053730 | Mar/28/2023 | Apr/05/2023 | Mar/08/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e570cf3437f6
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053730-AL3-TET101-2-11A | Cleanroom Makeup Air System | 15053730 | Mar/28/2023 | Apr/05/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e5a63437f7
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-TET101-2-11A | Cleanroom Makeup Air System | 15053730 | Mar/28/2023 | Apr/05/2023 | Mar/08/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e5a63437f7
Passed | INST FAT | SKANSKA -SPGC | 15053730-AL3-TET101-2-11A | Cleanroom Makeup Air System | 15053730 | Jun/02/2023 | Jun/09/2023 | May/11/2023 | May/11/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5e5a63437f7
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-FS101-2-02A | Cleanroom Makeup Air System | 15053730 | Mar/28/2023 | Apr/05/2023 | Mar/09/2023 | Mar/10/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5112d343800
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-XV101-2-02A | Cleanroom Makeup Air System | 15053730 | Apr/03/2023 | Apr/11/2023 | Mar/08/2023 | Mar/08/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e54db73437fd
Passed | PROC CC | SKANSKA -SPGC | 15053730-AL3-XV101-2-02A | Cleanroom Makeup Air System | 15053730 | Mar/27/2023 | Apr/04/2023 | Feb/28/2023 | Feb/28/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e54db73437fd
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-AIT101-2-02A | Cleanroom Makeup Air System | 15053730 | Mar/28/2023 | Apr/05/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e502e73437ff
Passed | INST FAT | SKANSKA -SPGC | 15053730-AL3-AIT101-2-02A | Cleanroom Makeup Air System | 15053730 | Jun/02/2023 | Jun/09/2023 | May/11/2023 | May/11/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e502e73437ff
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053730-AL3-AIT101-2-02A | Cleanroom Makeup Air System | 15053730 | Mar/28/2023 | Apr/05/2023 | Mar/09/2023 | Mar/09/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e502e73437ff
Passed | I&C OAT | SKANSKA -SPGC | 15053730-AL3-FS101-2-02B | Cleanroom Makeup Air System | 15053730 | Jun/01/2023 | Jun/08/2023 | Mar/09/2023 | May/01/2023 | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e52283343801
Not Started | I&C OAT | SKANSKA -SPGC | 15053730-AL3-HSI101-1-02A | Cleanroom Makeup Air System | 15053730 | Jun/20/2023 | Jun/29/2023 |  |  | AL3 |  |  | 101 | MECHANICAL DRY | E-6390f9d52b21e5c025343805
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QS650-103-02B | ALC RIO650-103-02 Power Supply B Status - 24V PS#2 | 15048266 |  |  | Jan/23/2023 | Jan/25/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-63ceda7d6dca01ed6703ee48
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QS650-103-02A | ALC RIO650-103-02 Power Supply A Status - 24V PS#1 | 15048266 |  |  | Jan/23/2023 | Jan/25/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-63ceda7d6dca01058903ee47
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QS650-103-02D | ALC RIO650-103-02 Power Supply D Status - Rack PS #2 | 15048266 |  |  | Jan/23/2023 | Jan/25/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-63ceda7d6dca012bc103ee4a
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QS650-103-02E | ALC RIO650-103-02 Thermostat Status | 15048266 |  |  | Jan/23/2023 | Jan/25/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-63ceda7d6dca010c1403ee4b
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-IS172-2-00A | ALC East Parking Stormwater Lift Station Pump 2 Run Status | 15048266 |  |  | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-63ceda7d6dca0184d603ee46
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-IS172-1-00A | ALC East Parking Stormwater Lift Station Pump 1 Run Status | 15048266 |  |  | Jan/24/2023 | Jan/25/2023 | F15 |  |  | 172 | WASTE | E-63ceda7d6dca01531f03ee45
Passed | I&C OAT | SKANSKA -SPGC | 15048266-ALC-QS650-103-02C | ALC RIO650-103-02 Power Supply C Status - Rack PS#1 | 15048266 |  |  | Jan/23/2023 | Jan/25/2023 | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-63ceda7d6dca01e5e003ee49
Not Started | FAT | SKANSKA -SPGC | 15048266-172STRM DRN treatment System | SYSTEM SO STORM DRAIN TREATMENT | 15048266 | May/27/2023 | Jun/19/2023 |  |  | F15 |  |  | 172 | WASTE | E-63d95a40972a6e8a2a52e9bf
Not Started | SYS CC/GT | SKANSKA -SPGC | 15048266-172STRM DRN treatment System | SYSTEM SO STORM DRAIN TREATMENT | 15048266 | May/22/2023 | May/26/2023 |  |  | F15 |  |  | 172 | WASTE | E-63d95a40972a6e8a2a52e9bf
Not Started | SYS OA/BT | SKANSKA -SPGC | 15048266-172STRM DRN treatment System | SYSTEM SO STORM DRAIN TREATMENT | 15048266 | May/27/2023 | Jun/19/2023 |  |  | F15 |  |  | 172 | WASTE | E-63d95a40972a6e8a2a52e9bf
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-IS001-2-02A | AL4 MAH#2 D-EVAP PUP STATUS | 15053691 |  |  | Mar/13/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4fbc365c43f9
Passed | PROC CC | SKANSKA -SPGC | 15053691-AL4-XV001-1-02A | AL4 MAH#1 D-EVAP SUMP FILL VALVE | 15053691 | May/26/2023 | Jun/02/2023 | Apr/24/2023 | Apr/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6ce55c4406
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-XV001-1-02A | AL4 MAH#1 D-EVAP SUMP FILL VALVE | 15053691 | May/26/2023 | Jun/02/2023 | Apr/24/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6ce55c4406
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-HSI001-2-02A | AL4 MAH#2 D-EVAP LCP HOA | 15053691 |  |  | Mar/13/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f63ce5c43f7
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-FS001-2-02B | AL4 MAH#2 D-EVAP DRAIN SW | 15053691 | Jun/01/2023 | Jun/08/2023 | May/04/2023 | May/04/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4fa3df5c43ff
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-HSI001-1-02A | AL4 MAH#1 D-EVAP LCP HOA | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f3f6e5c43fd
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-FS001-2-02A | AL4 MAH#2 D-EVAP PUMP SW | 15053691 |  |  | Mar/15/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4fba345c4402
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-IS001-1-02B | AL4 MAH#1 D-EVAP UV STATUS | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f5ef95c4405
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-HS001-2-02A | AL4 MAH#2 D-EVAP PUMP RUN | 15053691 |  |  | Mar/13/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4fa4b45c43f8
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-IS001-2-02B | AL4 MAH#2 D-EVAP UV STATUS | 15053691 |  |  | Mar/13/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f21ec5c43fa
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-XV001-2-02B | AL4 MAH#2 D-EVAP SUMP DRAIN VALVE | 15053691 |  |  | Mar/08/2023 | Mar/10/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f4b675c43fc
Passed | PROC CC | SKANSKA -SPGC | 15053691-AL4-XV001-2-02B | AL4 MAH#2 D-EVAP SUMP DRAIN VALVE | 15053691 |  |  | Mar/13/2023 | Mar/13/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f4b675c43fc
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-HS001-1-02A | AL4 MAH#1 D-EVAP PUMP RUN | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f82645c4403
Passed | PROC CC | SKANSKA -SPGC | 15053691-AL4-XV001-2-02A | AL4 MAH#2 D-EVAP SUMP FILL VALVE | 15053691 |  |  | Mar/13/2023 | Mar/13/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6f935c43fb
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-XV001-2-02A | AL4 MAH#2 D-EVAP SUMP FILL VALVE | 15053691 |  |  | Mar/08/2023 | Mar/10/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6f935c43fb
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-FS001-1-02B | AL4 MAH#1 D-EVAP DRAIN SW | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f79885c4409
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-AIT001-2-02A | AL4 MAH#2 D-EVAP COND | 15053691 |  |  | Mar/13/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f55285c43fe
Passed | INST FAT | SKANSKA -SPGC | 15053691-AL4-AIT001-2-02A | AL4 MAH#2 D-EVAP COND | 15053691 | Jun/02/2023 | Jun/09/2023 | May/11/2023 | May/11/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f55285c43fe
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053691-AL4-AIT001-2-02A | AL4 MAH#2 D-EVAP COND | 15053691 |  |  | Mar/09/2023 | Mar/09/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f55285c43fe
Passed | EQ CC/GT | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/08/2023 | Jun/15/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | PROC CC | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/24/2023 | Apr/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | FAT | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Apr/27/2023 | May/04/2023 | May/08/2023 | May/08/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | EQ OA/BT | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Apr/27/2023 | May/15/2023 | May/08/2023 | May/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | ELECT DV | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/21/2023 | Apr/21/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | MECH D DV | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/24/2023 | Apr/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | ELECT OAT | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | PROC DV | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/24/2023 | Apr/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | I&C CC | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | I&C DV | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/21/2023 | Apr/21/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | MECH D CC | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/24/2023 | Apr/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | ELECT CC | SKANSKA -SPGC | 15053691-AL4-MAH101-1-10 | Makeup Air Handler | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f6db25c43f2
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-TET001-1-02A | AL4 MAH#1 D-EVAP HUMID. WATER TEMPERATURE | 15053691 | May/26/2023 | Jun/02/2023 | Apr/24/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f19265c43f4
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053691-AL4-TET001-1-02A | AL4 MAH#1 D-EVAP HUMID. WATER TEMPERATURE | 15053691 |  |  | Mar/09/2023 | Mar/09/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f19265c43f4
Passed | INST FAT | SKANSKA -SPGC | 15053691-AL4-TET001-1-02A | AL4 MAH#1 D-EVAP HUMID. WATER TEMPERATURE | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/26/2023 | Apr/26/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f19265c43f4
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-IS001-1-02A | AL4 MAH#1 D-EVAP PUP STATUS | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f1b645c4404
Passed | ELECT CC | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/15/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | EQ CC/GT | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 | Jun/08/2023 | Jun/15/2023 | May/04/2023 | May/04/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | EQ OA/BT | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 | Apr/27/2023 | May/15/2023 | May/08/2023 | May/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | ELECT DV | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/10/2023 | Mar/10/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | EER Final Approval | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/15/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | MECH D CC | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/07/2023 | Mar/07/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | ELECT OAT | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/15/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | I&C DV | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/10/2023 | Mar/10/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | FAT | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 | Apr/27/2023 | May/04/2023 | May/08/2023 | May/08/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | I&C CC | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 | Jun/01/2023 | Jun/08/2023 | Mar/15/2023 | May/04/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | MECH D DV | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/06/2023 | Mar/06/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | PROC CC | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/07/2023 | Mar/07/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | PROC DV | SKANSKA -SPGC | 15053691-AL4-MAH101-2-10 | Cleanroom Makeup Air System | 15053691 |  |  | Mar/06/2023 | Mar/06/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f05fa5c43f6
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-FS001-1-02A | AL4 MAH#1 D-EVAP PUMP SW | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f1cf65c43f5
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-XV001-1-02B | AL4 MAH#1 D-EVAP SUMP DRAIN VALVE | 15053691 | May/26/2023 | Jun/02/2023 | Apr/24/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f2dd55c4407
Passed | PROC CC | SKANSKA -SPGC | 15053691-AL4-XV001-1-02B | AL4 MAH#1 D-EVAP SUMP DRAIN VALVE | 15053691 | May/26/2023 | Jun/02/2023 | Apr/24/2023 | Apr/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f2dd55c4407
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-LIT001-1-02A | AL4 MAH#1 D-EVAP SUMP LEVEL | 15053691 | May/26/2023 | Jun/02/2023 | Apr/24/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f43415c43f3
Passed | INST FAT | SKANSKA -SPGC | 15053691-AL4-LIT001-1-02A | AL4 MAH#1 D-EVAP SUMP LEVEL | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/26/2023 | Apr/26/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f43415c43f3
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053691-AL4-LIT001-1-02A | AL4 MAH#1 D-EVAP SUMP LEVEL | 15053691 |  |  | Mar/09/2023 | Mar/09/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f43415c43f3
Passed | INST FAT | SKANSKA -SPGC | 15053691-AL4-TET001-2-02A | AL4 MAH#2 D-EVAP HUMID. WATER TEMPERATURE | 15053691 | Jun/02/2023 | Jun/09/2023 | May/11/2023 | May/11/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f79bb5c4401
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053691-AL4-TET001-2-02A | AL4 MAH#2 D-EVAP HUMID. WATER TEMPERATURE | 15053691 |  |  | Mar/08/2023 | Mar/08/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f79bb5c4401
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-TET001-2-02A | AL4 MAH#2 D-EVAP HUMID. WATER TEMPERATURE | 15053691 |  |  | Mar/08/2023 | Mar/10/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f79bb5c4401
Passed | INST FAT | SKANSKA -SPGC | 15053691-AL4-LIT001-2-02A | AL4 MAH#2 D-EVAP SUMP LEVEL | 15053691 | Jun/02/2023 | Jun/09/2023 | May/11/2023 | May/11/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f2ee35c4400
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-LIT001-2-02A | AL4 MAH#2 D-EVAP SUMP LEVEL | 15053691 |  |  | Mar/08/2023 | Mar/10/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f2ee35c4400
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053691-AL4-LIT001-2-02A | AL4 MAH#2 D-EVAP SUMP LEVEL | 15053691 |  |  | Mar/08/2023 | Mar/08/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f2ee35c4400
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053691-AL4-AIT001-1-02A | AL4 MAH#1 D-EVAP COND | 15053691 |  |  | Mar/09/2023 | Mar/09/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f66d95c4408
Passed | I&C OAT | SKANSKA -SPGC | 15053691-AL4-AIT001-1-02A | AL4 MAH#1 D-EVAP COND | 15053691 | May/26/2023 | Jun/02/2023 | Apr/23/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f66d95c4408
Passed | INST FAT | SKANSKA -SPGC | 15053691-AL4-AIT001-1-02A | AL4 MAH#1 D-EVAP COND | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/26/2023 | Apr/26/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63f4ef8991dd4f66d95c4408
Passed | ELECT OAT | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/24/2023 | Apr/24/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Passed | ELECT CC | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/24/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Passed | I&C CC | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 | Jun/01/2023 | Jun/08/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Not Started | EQ OA/BT | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 | Apr/27/2023 | Jun/01/2023 |  |  | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 |  |  | Mar/09/2023 | Mar/09/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Not Started | FAT | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 | Apr/27/2023 | Jun/01/2023 |  |  | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Passed | ELECT DV | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/21/2023 | Apr/21/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Passed | I&C DV | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 | Jun/02/2023 | Jun/09/2023 | Apr/21/2023 | Apr/21/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Passed | EQ CC/GT | SKANSKA -SPGC | 15053691-AL4-LCP001-1-02A | LCP | 15053691 | Jun/08/2023 | Jun/15/2023 | Apr/25/2023 | Apr/25/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a572414301312f7
Passed | ELECT DV | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 |  |  | Mar/13/2023 | Mar/13/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Passed | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 |  |  | Mar/09/2023 | Mar/09/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Not Started | FAT | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 | Apr/27/2023 | Jun/01/2023 |  |  | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Passed | I&C DV | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 |  |  | Mar/13/2023 | Mar/13/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Passed | ELECT OAT | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 |  |  | Mar/15/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Passed | ELECT CC | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 |  |  | Mar/15/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Not Started | EQ OA/BT | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 | Apr/27/2023 | Jun/01/2023 |  |  | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Passed | I&C CC | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 |  |  | Mar/15/2023 | Mar/15/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Passed | EQ CC/GT | SKANSKA -SPGC | 15053691-AL4-LCP001-2-02A | LCP | 15053691 | Apr/25/2023 | Apr/25/2023 | May/04/2023 | May/04/2023 | AL4 |  |  | 101 | MECHANICAL DRY | E-63ffe3ff2a5724c4f61312f8
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-HS138-1-130 | FAN 1 BDD CLOSE COMMAND -HS138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ad6deb81c1
Not Started | I&C DV | SKANSKA -SPGC | 15054743-F15-VFD138-1-100 | VFD | 15054743 | Jul/31/2023 | Jul/31/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593377251eb81bd
Not Started | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15054743-F15-VFD138-1-100 | VFD | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593377251eb81bd
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-VFD138-1-100 | VFD | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593377251eb81bd
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-VFD138-1-100 | VFD | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593377251eb81bd
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-VFD138-1-100 | VFD | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593377251eb81bd
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-VFD138-1-100 | VFD | 15054743 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593377251eb81bd
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-VFD138-1-100 | VFD | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593377251eb81bd
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-VFD138-1-100 | VFD | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593377251eb81bd
Not Started | I&C DV | SKANSKA -SPGC | 15054743-F15-VFD138-3-100 | VFD | 15054743 | Jun/23/2023 | Jun/23/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337305ceb81bf
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-VFD138-3-100 | VFD | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337305ceb81bf
Not Started | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15054743-F15-VFD138-3-100 | VFD | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337305ceb81bf
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-VFD138-3-100 | VFD | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337305ceb81bf
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-VFD138-3-100 | VFD | 15054743 | Jun/29/2023 | Jun/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337305ceb81bf
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-VFD138-3-100 | VFD | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337305ceb81bf
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-VFD138-3-100 | VFD | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337305ceb81bf
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-VFD138-3-100 | VFD | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337305ceb81bf
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-EXVO System Get-Well | Damper | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337a487eb81c0
Not Started | SYS CC/GT | SKANSKA -SPGC | 15054743-F15-EXVO System Get-Well | Damper | 15054743 | Sep/22/2023 | Sep/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337a487eb81c0
Not Started | SYS OA/BT | SKANSKA -SPGC | 15054743-F15-EXVO System Get-Well | Damper | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337a487eb81c0
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-HS138-2-130 | FAN 2 BDD CLOSE COMMAND HS138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337d52deb81c7
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-FE138-1-101A | EXVO FALSE LOAD DAMPER Flow Element | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337567deb81b9
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-PCZ138-3-130 | FAN 3 BDD POSITION COMMAND CZ138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593372fa7eb81b1
Not Started | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15054743-F15-PCZ138-3-130 | FAN 3 BDD POSITION COMMAND CZ138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593372fa7eb81b1
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-PCZ138-3-130 | FAN 3 BDD POSITION COMMAND CZ138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593372fa7eb81b1
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-PCZ138-3-130 | FAN 3 BDD POSITION COMMAND CZ138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593372fa7eb81b1
Not Started | MECH D CC | SKANSKA -SPGC | 15054743-F15-PCZ138-3-130 | FAN 3 BDD POSITION COMMAND CZ138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593372fa7eb81b1
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-PCZ138-3-130 | FAN 3 BDD POSITION COMMAND CZ138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/29/2023 | Jun/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593372fa7eb81b1
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-PCZ138-3-130 | FAN 3 BDD POSITION COMMAND CZ138-3-130 Level 4 - W.4/24.3 | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593372fa7eb81b1
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-PCZ138-3-130 | FAN 3 BDD POSITION COMMAND CZ138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f72593372fa7eb81b1
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZSC138-0-101A | EXVO FALSE LOAD DAMPER CLOSE STATUS F15_ZSC138_1_101A | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337eeb6eb81bb
Not Started | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15054743-F15-FIT138-1-101A | EXVO FALSE LOAD DAMPER F15_FIT138_1_101A | 15054743 | Sep/11/2023 | Sep/11/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337284deb81b7
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-FIT138-1-101A | EXVO FALSE LOAD DAMPER F15_FIT138_1_101A | 15054743 | Sep/11/2023 | Sep/11/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337284deb81b7
Not Started | INST FAT | SKANSKA -SPGC | 15054743-F15-FIT138-1-101A | EXVO FALSE LOAD DAMPER F15_FIT138_1_101A | 15054743 | Sep/18/2023 | Sep/18/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337284deb81b7
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZSO138-3-130 | EXVO POSITION DAMPER OPEN ZSO138-3-130 Level 4 - W.4/24.5 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337556ceb81b6
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-QS138-3-130 | FAN 3 STATUS -QS138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f725933781ebeb81b5
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-PCZ138-2-130 | FAN 2 BDD POSITION COMMAND CZ138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ecaeeb81c5
Not Started | MECH D CC | SKANSKA -SPGC | 15054743-F15-PCZ138-2-130 | FAN 2 BDD POSITION COMMAND CZ138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ecaeeb81c5
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-PCZ138-2-130 | FAN 2 BDD POSITION COMMAND CZ138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/31/2023 | Aug/31/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ecaeeb81c5
Not Started | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15054743-F15-PCZ138-2-130 | FAN 2 BDD POSITION COMMAND CZ138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ecaeeb81c5
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-PCZ138-2-130 | FAN 2 BDD POSITION COMMAND CZ138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ecaeeb81c5
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-PCZ138-2-130 | FAN 2 BDD POSITION COMMAND CZ138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ecaeeb81c5
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-PCZ138-2-130 | FAN 2 BDD POSITION COMMAND CZ138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ecaeeb81c5
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-PCZ138-2-130 | FAN 2 BDD POSITION COMMAND CZ138-2-130 Level 4 - X.5/24.3 | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337ecaeeb81c5
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZT138-2-130 | FAN 2 BDD POSITION FEEDBACK ZT138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f72593378e0aeb81ae
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZSO138-2-130 | FAN 2 POSITION DAMPER OPEN SO138-2-130 Level 4 - W.4/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f72593374db1eb81b0
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-QS138-2-130 | FAN 2 BDD STATUS -QS138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f72593370754eb81af
Not Started | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15054743-F15-VFD138-2-100 | VFD | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337925ceb81be
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-VFD138-2-100 | VFD | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337925ceb81be
Not Started | I&C DV | SKANSKA -SPGC | 15054743-F15-VFD138-2-100 | VFD | 15054743 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337925ceb81be
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-VFD138-2-100 | VFD | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337925ceb81be
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-VFD138-2-100 | VFD | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337925ceb81be
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-VFD138-2-100 | VFD | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337925ceb81be
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-VFD138-2-100 | VFD | 15054743 | Aug/31/2023 | Aug/31/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337925ceb81be
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-VFD138-2-100 | VFD | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337925ceb81be
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZT138-1-101A | EXVO FALSE LOAD DAMPER POSITION FEEDBACK F15_ZT138_1_101A | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f725933737b4eb81bc
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZSC138-1-130 | FAN 1 BDD CLOSE STATUS ZSC138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337492beb81b8
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZSC138-3-130 | FAN 3 CLOSE STATUS ZSC138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337b8ddeb81b2
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZSC138-2-130 | FAN 2 BDD CLOSE STATUS SC138-2-130 Level 4 - X.5/24.3 | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f72593377ed3eb81c6
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZSO138-1-130 | EXVO POSITION DAMPER OPEN SO138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337b09feb81c4
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-QS138-1-130 | FAN 1 BDD STATUS QS138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337f0eaeb81c3
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | INST FAT | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/19/2023 | Sep/25/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | MECH D CC | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-FCZ138-0-101A | EXVO FALSE LOAD DAMPER F15_POSITION COMMAND FCZ138_1_101A | 15054743 | Sep/22/2023 | Sep/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f725933720f4eb81ba
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZT138-1-130 | FAN 1 BDD POSITION FEEDBACK -ZT138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337f252eb81c2
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-HS138-3-130 | FAN 3 CLOSE COMMAND -HS138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337dccfeb81b3
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-PCZ138-1-130 | FAN 1 BDD POSITION COMMAND PCZ138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c87beb81ad
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-PCZ138-1-130 | FAN 1 BDD POSITION COMMAND PCZ138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c87beb81ad
Not Started | SI CC (OTS3/RTL) | SKANSKA -SPGC | 15054743-F15-PCZ138-1-130 | FAN 1 BDD POSITION COMMAND PCZ138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c87beb81ad
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-PCZ138-1-130 | FAN 1 BDD POSITION COMMAND PCZ138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c87beb81ad
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-PCZ138-1-130 | FAN 1 BDD POSITION COMMAND PCZ138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c87beb81ad
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-PCZ138-1-130 | FAN 1 BDD POSITION COMMAND PCZ138-1-130 Level 4 - W/24.3 | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c87beb81ad
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-PCZ138-1-130 | FAN 1 BDD POSITION COMMAND PCZ138-1-130 Level 4 - W/24.3 | 15054743 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c87beb81ad
Not Started | MECH D CC | SKANSKA -SPGC | 15054743-F15-PCZ138-1-130 | FAN 1 BDD POSITION COMMAND PCZ138-1-130 Level 4 - W/24.3 | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c87beb81ad
Not Started | I&C OAT | SKANSKA -SPGC | 15054743-F15-ZT138-3-130 | FAN 3 POSITION FEEDBACK -ZT138-3-130 Level 4 - W.4/24.3 | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 |  |  | 138 | MECHANICAL EXHAUST | E-640171f7259337c22beb81b4
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | ELECT DV | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Jul/31/2023 | Jul/31/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | I&C DV | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Jul/31/2023 | Jul/31/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Aug/04/2023 | Aug/04/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | MECH D CC | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Jul/28/2023 | Jul/28/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | MECH D DV | SKANSKA -SPGC | 15054743-F15-EF138-1-100 | Fan | 15054743 | Jul/31/2023 | Jul/31/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c921708ea03
Not Started | MECH D CC | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | I&C DV | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Jun/23/2023 | Jun/23/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Jun/29/2023 | Jun/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | MECH D DV | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Jun/23/2023 | Jun/23/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Jun/22/2023 | Jun/22/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | ELECT DV | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Jun/23/2023 | Jun/23/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-EF138-3-100 | Fan | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60c850e08ea01
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-RIO650-202-01-Card Install | Slot 07 Card Install | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-644579e338a60c8ddf08ea04
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-RIO650-202-01-Card Install | Slot 07 Card Install | 15054743 | Sep/15/2023 | Sep/15/2023 |  |  | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-644579e338a60c8ddf08ea04
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-RIO650-202-01-Card Install | Slot 07 Card Install | 15054743 | Sep/22/2023 | Sep/22/2023 |  |  | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-644579e338a60c8ddf08ea04
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-RIO650-202-01-Card Install | Slot 07 Card Install | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 |  |  | 650 | FACILITIES MONITORING SYSTEM | E-644579e338a60c8ddf08ea04
Not Started | MECH D DV | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | ELECT OAT | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | MECH D CC | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | ELECT DV | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | I&C CC | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | I&C DV | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Aug/25/2023 | Aug/25/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | EQ CC/GT | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Aug/31/2023 | Aug/31/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | EQ OA/BT | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | ELECT CC | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Aug/24/2023 | Aug/24/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02
Not Started | FAT | SKANSKA -SPGC | 15054743-F15-EF138-2-100 | Fan | 15054743 | Sep/25/2023 | Sep/29/2023 |  |  | F15 | EXVO System Get-Well |  | 138 | MECHANICAL EXHAUST | E-644579e338a60ce6a308ea02